## Schedule
Test phase | Purpose | Variation | Measurements | Plots? | Expected duration / days | Start date | End date | Priority | Status | Due / completed date
System installation at Aarhus University. Local technicians will assist | Basic mechanical installation and system verification | N/A | N/A | N/A | 7 | 2017-11-14 | 2017-11-21 | 1 | 1 | 2017-12-22
System IO | Verify basic IO: system configuration, state and parameters. Interface to timing system | N/A | N/A | N/A | 7 | 2017-11-21 | 2017-11-28 | 1 | 1 | 2018-01-22
Bdot characterization | Verify that the Bdot signal represents the system output with acceptable signal-to-noise, etc. This signal is vital in monitoring the system output. | System setpoints (frequency and amplitude), system rep. rate | Should vary with frequency and amplitude (identical frequency, Bdot amplitude ~ triangle amplitude * freq). Bdot should ideally not depend on rep. rate | Bdot shape vs. rep. rate. Bdot amplitude vs. amplitude * freq | 7 | 2017-11-28 | 2017-12-05 | 1 | 1 | 2018-02-01
Synchronization | Verify that the two raster magnets can by reasonably synchronized (within ±200 ns) | Possibly delays of pre-trig signals etc. | Check Bdot rising edges from the loops in the two magnets | Scope screen dumps | 7 | 2017-12-05 | 2017-12-12 | 3 | 1 | 2018-02-01
Magnetic field crosstalk | Verify that there is very limited magnetic field cross talk | Operate magnet 1 at e.g. 40 kHz, 14 Hz, low amplitude. Slowly rampup magnet 2 in amplitude plateaux, operated at 40 kHz (would a different frequency be better?) | Check changes in Bdot waveform shape from magnet 1 (a few periods in mid-burst) | Scope screen dumps | 4 | 2017-12-12 | 2017-12-16 | 2 | 1 | 2018-04-03
Polarity | Verify that polarity variation can be controlled | Polarity input: will polarity master be delivered in time by ESS ICS (incorporated in timing EVR)? | Bdot polarity | Scope screen dumps | 3 | 2017-12-16 | 2017-12-19 | 3 | 1 | 2018-04-03
Temperature stability | Verify that the amplitude regulation works although the inductance varies (due to temperature) | Uncontrolled ambient temperature in room | Bdot amplitudes vs. thermocouples on supply, cables, magnets | Bdot level residuals vs. temperatures. Thermography? | 7 | 2017-12-19 | 2017-12-26 | Could be part of long-term stability test | 0.5 | 2018-04-04
Stress test of supply | Verify that the supply can continue operation (although perhaps setting warning bits) despite frequent changes in setpoints, e.g. a tuning scenario | A script changes system configuration (frequency and/or amplitude) at a frequency similar to the applied rep. rate. | Bdot amplitudes (deviation from current setpoint, if possible?), system state | Occurrence of system errors? | 7 | 2017-12-26 | 2018-01-02 | 2 | 0 | 2017-12-22
Long-term stability, reliability run | Verify that the system can perform over a period comparable to the ESS operation runs without excessive failures |  | System warnings/failures. Bdot (is system still rastering?) | Occurrence of system errors vs. time. Thermography? | 60 | 2018-01-02 | 2018-03-03 | 1 | 0.7 | 2018-04-03
|  |  |  | Test days scheduled (incl. weekends) | 95
|  |  |  | Months scheduled | 3.1233
Formulas:
End date = [Start date]+[Expected duration / days]
Start date = [End date, row above]

## Equipment
Equipment | Purpose | Preparations? | Responsible | Heine's To-Dos | Status | Comments | Last updated
2Ch scope, triggered on pre-trig | Measure Bdot amplitudes + perhaps main freq. from FFT | Put scope on network | AU | Ask JSN for scope | Completed |  | 2017.08.31
|  | Setup data acquisition + storage | AU | Ask TW. Would like to capture numerous waveforms per day | Not commenced |  | 2017.08.31
Software | Bdot waveform data reduction script. Extract statistical parameters. | Make script | AU | Ask JSN + TW | Not commenced |  | 2017.08.31
Thermocouples | Measure equipment and ambient temperatures |  | AU | Ask JSN for ~6 thermocouples | Completed | PLC still to be assembled | 2017.08.31
EPICS Input-Output Controller (IOC) | For configuring the supplies and retrieving system data |  | ESS ICS | Ask ESS ICS for likelihood of delivering IOC. Not later than April, 2017 | Completed | Will control supplies directly from AU control system (ConSys) | 2017.08.31
Local control sys | Interface to EPICS IOC (if available) or directly to raster power supply | If IOC is not available, local experts should implement supply as a device (register task ASAP?) | AU |  | Tentatively discussed |  | 2017.08.31
Timing Event Receiver (EVR) | For generating Pre-Trig signal and the external clock reference. |  | ESS ICS |  | Commenced | Will be delivered by ESS ICS (Han). Includes optical fiber, EVG and IOC | 2017.08.29
Fault Detection Unit (FDU) | For monitoring the state of the supplies and delivering clear | Design and ship unit | ESS ICS |  | Completed | Is not expected to be completed in time for the pre-series testing | 2017.08.31
Tool cart, etc. | Assembly etc. |  | AU |  | Completed |  | 2017.08.31
1 x 19" rack, ~> 20 U | For supplies etc. |  | AU | Ask for rack | Completed | Will not be provided by Danfysik | 2017.01.31
Electrical power source in lab |  |  | AU | Ask Danfysik for plug specification | Completed | Although inrush is ~25A this is typically gone within a few 50 Hz periods. It is expected to be possible to operate both supplies on a single 13 A C-type breaker | 2017.02.06
Bdot cables, 35 m | Test of full-length cables | Buy / manufacture cables | AU | Ask JSN + SPM | Completed | Danfysik will provide cables | 2017.03.27
Thermal breaker cables, 35 m | Test of full-length cables | Buy / manufacture cables | AU | Ask JSN + SPM | Completed | Danfysik will provide cables | 2017.03.27
Semi-automatic characterization tool | Operate the system in several modes during reliability run | Make script (MATLAB?) | AU | Discuss with JSN | Not commenced | Define parameter space | 2017.08.31