## Slide 1
  ESS Project Status
  Roland Garoby – Technical Director
  October 2018

## Slide 2: ESS is more than 50% complete
2018 is the peak of construction activity
In-kind deliveries of high tech equipment arriving
Commissioning of ion source has started
All staff moved out to site in June this year…
Ion source skid
TMCP compressors
Prototype cryomodule
and its transport
vehicle
~600 Work places
~10 000 m2

## Slide 3: Progress with respect to the Goals for 2018
Goals for 2018 | Status in October 2018
Submit to SSM the application for the trial operations of the Warm Linac | Delayed till April 2019
Move ESS Lund organisation to site | Done
A detailed plan for first two years (2019 & 2020) of Initial Operations | In progress (budget defined)
Start of commissioning of ion source and LEBT, temporary control room operational | Done
Complete manufacturing and Factory Acceptance Tests of Moderator plug, Cryo-Moderator System and Cryoplant. | Done
All instruments start Tollgate 3 process and begun procurement | ?
First joint user meeting with the ILL | Done
Secure Spain as an ERIC member | Done
Work with ILL to establish a neutron initiative recognised by the European commission in their planning for FP9 | Done

## Slide 4: The ESS Council has approved the new baseline schedule in June 2018
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float to BOT
Accelerator RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker and Test Beam Line RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
SOUP
Instrument Hall Access for Start of Installation
Hi-Beta Install
1.3 GeV Capability Installed

## Slide 5: New schedule of Accelerator
New Baseline
2019
2020
2021
ISrc to LEBT
25 Jun '18
ISrc to RFQ/MEBT/DTL1
4 Nov '19
ISrc to DTL4
27 Apr '20
ISrc to Beam Dump (BOD)
8 Feb '21
RBOT
24 May '21
Beam to RFQ/MEBT Delay
18.8 months
Beam to DTL4 Delay
21.8 months
BOD Delay
21.2 months
RBOT Delay
23.9 months
Old Baseline
2019
2020
2021
ISrc to RFQ/MEBT
11 Apr '18
ISrc to DTL4
5 Jul '18
ISrc to Beam Dump (BOD)
30 Apr '19
RBOT
28 May '19

## Slide 6: New schedule of Target and Instruments
2018
2019
2020
2021
2022
BOT
Target Building (D02) Access for Monolith Installation
Target RBOT
Monolith and A2T Concrete
Monolith Installation & Testing
Target Integrated Bunker Scope
Bunker Construction and Installation
High Bay Infrastructure Installation
Monolith Area Superstructure
Testing and Readiness Review
NSS RBOT
Target Wheel & MR Installed
Monolith inserts & shutters installed
Final testing and Readiness Review
3 months float
CF D01/D03 Build-out to weather tight
Parallel Works
Ready for parallel bunker and monolith works

## Slide 7: Licensing timeline
2019
2021
ESS
SSM
Intentional neutron production trial operation review
2022
2020
RBoT
RFQ Beam
BoD
Conditional permit
SRR5
SRR4
Submission 2021-04-15
SC LINAC trial operation review
Conditional permit
Submission 2020-04-30
SRR2
Submission 2019-04-30
Conditional permit
Warm LINAC trial operation review
BoT
Ref Doc ready 2018-10-15
PSAR updated
Self Assessment
Independent Safety Review
Ref Doc ready 2019-11-15
PSAR updated
Self Assessment
Independent Safety Review
Ref Doc ready 2020-10-30
PSAR updated
Self Assessment
Independent Safety Review
IoS
permit
IoS Beam
SRR1
IoS
Extension
For Klystron test
IoS Extension
For cavity test
Response to
questions
TS2
Extension
RFQ – Radio Frequency Quadrupole
BoD – Beam on Dump
BoT - Beam on Target
RBoT - Ready for Beam on Target
PSAR – Preliminary Safety Analysis Report
SRR - Safety Readiness Review
SSM – Swedish Radiation Safety Authority
Submission
Submission
Subm.
SRR

## Slide 8: Transition to Operations
Updated description of “Early Operations of the ESS Neutron Instruments and first scientific results” (ESS-0420218) distinguishing successive stages:
Up to Beam on Target (-July 2022)
ESS initial stages (July 2022-December 2023)
  Early Days: BOT to (BOT + 3 months) (July – September 2022)
  Consolidation Days: The next 3 months: (BOT + 3 months) to (BOT + 6 months) (October – December 2022)
  Performance Assessment days: (BOT + 6 months) to (BOT + 9 months) (January – March 2023).
  First Performance Demonstration Days: (BOT + 9 months) to (BOT + 12 months) (April – June 2023)
  Ramp up and Early Science: (BOT + 12 months) to (BOT + 18 months) (July – December 2023)
Start of the ESS User programme SOUP (2024-2027)

## Slide 9: Organisation and People
471
Employees
50
Nationalities
~ 100
Collaborating Institutions
+ 146
Contracted
Notes: Updated September 2017

## Slide 10: ESS high level structure during Initial Operations
DG
Three Directors
  Science plus Deputy focused on Operations
  Technical plus Deputy focused on Operations
  Administration plus Deputy
Two Associate Directors
  ESH&Q
  Strategy
Matrixed responsibilities
  Installation manager
  Engineering Manager
  Operations Manager

## Slide 11: Changes/new senior staff positions since April 2018
Associate Director for Strategy:
  Sharon Cosgrove
Head of Communications:
Martin Sjöstrand
Deputy Technical Director (Operations Manager):
Carlo Bocchetta
Engineering Manager:
Peter Radahl

## Slide 12: Civil Construction Groundbreaking
September 2014

## Slide 13
September 2018

## Slide 14: Experimental Hall (E01)

## Slide 15: Target building (D02)

## Slide 16: A2T (junction G02 – D02)

## Slide 17: Active Cell in D02

## Slide 18: Ion source & LEBT are under commissioning

## Slide 19: The temporary control room is operational
For commissioning
the ion source…
…and for commissioning
the cryoplants.

## Slide 20
Lund Tramway Depot
Permanent
Office Campus
2021
New 2018 ESS offices for all staff
New Bus Stop

## Slide 21: Campus
Labs and Workshops
Offices, auditorium canteen
Entrance Building
Signed construction and financing agreements in February
Now in detailed design before target cost is agreed
Cost of the lease is included in the operations costs
Campus construction started in September 2018

## Slide 23
SPACE Building: Reception, exhibition space, guest house for MAX IV and ESS (~100 rooms), office and meeting space, restaurant
Tramway from Lund C station
Swedish Government approval
August 2018
Modelled on the Harwell Campus

## Slide 24: Funding decisions in 2018
AFC.07
Budget Plan 19/20 (R)
Indicative Plan 21-25 (I)
Construction Budget 2019 (I)
10-11 Apr
Council.13
Budget Plan 19/20 (A)
Indicative Plan 21-25 (I)
Commitments from Members for 2019/20 initial ops funding
4-5 June
Council.12
Workshop
Budget plan 19/20 (I)
Indicative plan 21-25 (I)
High-Level Document (D)
Sharing Policy (D)
8 Feb
Schedule Review
Focus on re-baselining
Will mostly impact indicative plan 21-25
22-24 May
3-4 Dec
Council.14
Constr. budget 2019 (A)
Init ops budget 2019 (A)
Indicative plan 2021-2025 (A)
Commitments from Members for 2021-2025
Commitments from Members to completion of construction
AFC.08
Constr. budget 2019 (R)
Init ops budget 2019 (R)
Indicative planning 2021-2025 (R)
30-31 Oct
Political decision-making
High level meeting
Aug
Annual Review
Project review
11-14 Dec