## Slide 1
  ESS Project Status
  Roland Garoby – Technical Director
  August 2018

## Slide 2: ESS is close to 50% complete
2018 is the peak of construction activity
First buildings have been handed over
In-kind deliveries of high tech equipment arriving
All our staff moved out to site in June this year

## Slide 3: Organisation and People
447
Employees
50
Nationalities
~ 100
Collaborating Institutions
Notes: Updated September 2017

## Slide 4: Civil Construction Groundbreaking
September 2014

## Slide 6
Lund Tramway Depot
Permanent
Office Campus
2021
New 2018 ESS offices for all staff
New Bus Stop

## Slide 7: Campus
Labs and Workshops
Offices, auditorium canteen
Entrance Building
Signed construction and financing agreements in February
Now in detailed design before target cost is agreed
Cost of the lease is included in the operations costs

## Slide 8: Target building (1/2)

## Slide 9: Target building (2/2)

## Slide 10: Experimental Hall (E01)

## Slide 11: Accelerator & Klystron Gallery

## Slide 12: Dummy elliptical cryomodule in TS-2

## Slide 13: Ion source & LEBT are about to start

## Slide 14
SPACE Building: Reception, exhibition space, guest house for MAX IV and ESS (~100 rooms), office and meeting space, restaurant
Tramway from Lund C station
Swedish Government approval
August 2018
Modelled on the Harwell Campus

## Slide 16: Rebaselined ESS schedule
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float to BOT
Accelerator RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker and Test Beam Line RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
SOUP
Instrument Hall Access for Start of Installation
Hi-Beta Install
1.3 GeV Capability Installed

## Slide 17: Main delays for the Accelerator are due to in-kind partners…
New Baseline
2019
2020
2021
ISrc to LEBT
25 Jun '18
ISrc to RFQ/MEBT/DTL1
4 Nov '19
ISrc to DTL4
27 Apr '20
ISrc to Beam Dump (BOD)
8 Feb '21
RBOT
24 May '21
Beam to RFQ/MEBT Delay
18.8 months
Beam to DTL4 Delay
21.8 months
BOD Delay
21.2 months
RBOT Delay
23.9 months
Old Baseline
2019
2020
2021
ISrc to RFQ/MEBT
11 Apr '18
ISrc to DTL4
5 Jul '18
ISrc to Beam Dump (BOD)
30 Apr '19
RBOT
28 May '19

## Slide 18: Main delays for the Target are due to the Target Building, but in-kind contributions are critical…
2018
2019
2020
2021
2022
BOT
Target Building (D02) Access for Monolith Installation
Target RBOT
Monolith and A2T Concrete
Monolith Installation & Testing
Target Integrated Bunker Scope
Bunker Construction and Installation
High Bay Infrastructure Installation
Monolith Area Superstructure
Testing and Readiness Review
NSS RBOT
Target Wheel & MR Installed
Monolith inserts & shutters installed
Final testing and Readiness Review
3 months float
CF D01/D03 Build-out to weather tight
Parallel Works
Ready for parallel bunker and monolith works

## Slide 19: Funding decisions in 2018
AFC.07
Budget Plan 19/20 (R)
Indicative Plan 21-25 (I)
Construction Budget 2019 (I)
10-11 Apr
Council.13
Budget Plan 19/20 (A)
Indicative Plan 21-25 (I)
Commitments from Members for 2019/20 initial ops funding
4-5 June
AFC.08
Constr. budget 2019 (R)
Init ops budget 2019 (R)
Indicative planning 2021-2025 (R)
30-31 Oct
Council.12
Workshop
Budget plan 19/20 (I)
Indicative plan 21-25 (I)
High-Level Document (D)
Sharing Policy (D)
8 Feb
Schedule Review
Focus on re-baselining
Will mostly impact indicative plan 21-25
22-24 May
Annual Review
Project review
Sep
Council.14
Constr. budget 2019 (A)
Init ops budget 2019 (A)
Indicative plan 2021-2025 (A)
Commitments from Members for 2021-2025
Commitments from Members to completion of construction
3-4 Dec
Political decision-making
Minister level