## Slide 1
  ESS Project Status
  Roland Garoby – Technical Director
  October 2018

## Slide 2: ESS is close to 50% complete
2018 is the peak of construction activity
First buildings have been handed over
In-kind deliveries of high tech equipment arriving
All staff moved out to site in June this year
Ion source skid
TMCP compressors
Prototype cryomodule
and its transport
vehicle

## Slide 3: Organisation and People
>480
Employees
50
Nationalities
~ 100
Collaborating Institutions
Notes: Updated September 2017

## Slide 4: Civil Construction Groundbreaking
September 2014

## Slide 5
September 2018

## Slide 6: Experimental Hall (E01)

## Slide 7: Target building (D02)

## Slide 8: Technical Progress: WP2 Target Systems 1(2)
Target wheel and drive unit
Manufacturing of cassettes and spallation material in progress
CDR Target Drive Unit held 24 April.
Manufacturing of the target wheel prototype close to be finalized. Lessons learned to be used for the final Target Wheel
CDR for Target Wheel and Shaft postponed to Sept 2018. However, early procurement of material in progress
Complete Target Wheel Drive & Shaft delivery on site November 2019
Target Helium Cooling System
Manufacturing of the Helium Circulators in progress
CDR Target Helium Cooling System performed. Piping in the Connection Cell needs to be redesigned and remote handling of the helium filters elaborated
Target monitoring
PDR for the Target Monitoring Plug performed. Contract signed with FZJ to perform the final design and manufacturing
Tungsten Bricks in Cassette

## Slide 9: Technical Progress: WP2 Target Systems 2(2)
Monolith Shielding
  Manufacturing of the Ground Shielding in progress, signed contract May 2018
  Procurement of the Outer Shielding in progress
  CDR for the Inner Shielding performed
  Budget underestimated
Tuning Beam Dump
  CDR for the Tuning Beam Dump Shielding performed
  CDR for the Tuning Beam Dump System performed
  Procurements published, award expected October
Outer Shielding
Inner Shielding
Ground Shielding
Tuning Beam Dump

## Slide 10: Technical Progress WP3 Moderator and Reflector Systems,
Moderator & Reflector Plug
  Cold Moderators finished manufactured
  Reflector, Thermal Moderator et al in manufacturing
Cryogenic Hydrogen System
  Manufacturing ongoing
  LH2 pumps delivered
Helium Cryoplant
  Delivery of Compressor Skids 18Q2 and coldbox 18Q3
Irradiation module
  Manufacturing completed
MR Plug
Cryogenic moderator prototype
Part of Reflector Vessel
Helium Coldbox delivery

## Slide 11: Technical Progress WP4 Monolith systems
proton beam window
proton beam instrumentation plug
monolith vessel
Monolith vessel
  Design finalized for lower parts and contract awarded to AVS/Cadinox for fabrication
  Final design on-going for connection ring and covers
Proton beam window
  Final design on-going
  Tests on PBW and inflatable seals are on-going.
Proton beam instrumentation plug
  Specifications of instrumentation equipment in progress by ACCSYS and their Norwegian in-kind partner
Monolith port block package
  Preliminary design finalized February 2018
  Procurement in progress
  Contract awarded for the monolith base plate
Monolith Atmosphere System
  Decision taken for pursuing rough vacuum (< 100Pa) with PBW in place as primary operation mode.
  Preliminary design performed by Target and then hand-over to ACCSYS for final design
Proton Beam Window
Monolith port block package

## Slide 12: Technical Progress WP4 Monolith Systems
Neutron beam extraction system
  Detailed design on-going
  Discussions on-going with FZJ to take on parts of the scope
  Material ordered for manufacturing one prototype insert
  System split into several Critical Design Reviews due to complexity. Prototypes ongoing for plugs and planned for Light Shutter System.
Neutron Beam Windows
  Excellent results on vacuum seal tests on prototypes.
12
BBG
NBPI
Handling tooling
NBW
GBS
Target level floor
Instrument position

## Slide 13: Technical Progress WP5 Fluid Systems
Primary and intermediate water cooling systems
  Safety classification not ready for primary water cooling systems
    Procurement delayed
  Procurement started for intermediate water cooling systems
Target Station HVAC system
  Detailed design finalized – procurement ongoing
Offgas/monolith vessel relief
  Preliminary design ongoing
Electrical Infrastructure & automation cabinets
  Preliminary design ongoing
All other utility and process systems
  Completion of detailed designs are imminent
  Drain tanks procured and in fabrication
Other
  Procurement preparation of HVAC & Piping installation ongoing
  Turn-key procurement ongoing for Helium purification & Radiolysis Gas Handling systems

## Slide 14: The temporary control room is operational
For commissioning
the ion source…
…and for commissioning
the cryoplants.

## Slide 15: Accelerator & Klystron Gallery (G02)

## Slide 16: Ion source & LEBT are under commissioning

## Slide 17
Lund Tramway Depot
Permanent
Office Campus
2021
New 2018 ESS offices for all staff
New Bus Stop

## Slide 18: Campus
Labs and Workshops
Offices, auditorium canteen
Entrance Building
Signed construction and financing agreements in February
Now in detailed design before target cost is agreed
Cost of the lease is included in the operations costs

## Slide 20
SPACE Building: Reception, exhibition space, guest house for MAX IV and ESS (~100 rooms), office and meeting space, restaurant
Tramway from Lund C station
Swedish Government approval
August 2018
Modelled on the Harwell Campus

## Slide 21: Rebaselined ESS schedule (as approved by ESS Council in June 2018)
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float to BOT
Accelerator RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker and Test Beam Line RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
SOUP
Instrument Hall Access for Start of Installation
Hi-Beta Install
1.3 GeV Capability Installed

## Slide 22: New schedule of Accelerator
New Baseline
2019
2020
2021
ISrc to LEBT
25 Jun '18
ISrc to RFQ/MEBT/DTL1
4 Nov '19
ISrc to DTL4
27 Apr '20
ISrc to Beam Dump (BOD)
8 Feb '21
RBOT
24 May '21
Beam to RFQ/MEBT Delay
18.8 months
Beam to DTL4 Delay
21.8 months
BOD Delay
21.2 months
RBOT Delay
23.9 months
Old Baseline
2019
2020
2021
ISrc to RFQ/MEBT
11 Apr '18
ISrc to DTL4
5 Jul '18
ISrc to Beam Dump (BOD)
30 Apr '19
RBOT
28 May '19

## Slide 23: New schedule of Target and Instruments
2018
2019
2020
2021
2022
BOT
Target Building (D02) Access for Monolith Installation
Target RBOT
Monolith and A2T Concrete
Monolith Installation & Testing
Target Integrated Bunker Scope
Bunker Construction and Installation
High Bay Infrastructure Installation
Monolith Area Superstructure
Testing and Readiness Review
NSS RBOT
Target Wheel & MR Installed
Monolith inserts & shutters installed
Final testing and Readiness Review
3 months float
CF D01/D03 Build-out to weather tight
Parallel Works
Ready for parallel bunker and monolith works

## Slide 24: Funding decisions in 2018
AFC.07
Budget Plan 19/20 (R)
Indicative Plan 21-25 (I)
Construction Budget 2019 (I)
10-11 Apr
Council.13
Budget Plan 19/20 (A)
Indicative Plan 21-25 (I)
Commitments from Members for 2019/20 initial ops funding
4-5 June
AFC.08
Constr. budget 2019 (R)
Init ops budget 2019 (R)
Indicative planning 2021-2025 (R)
30-31 Oct
Council.12
Workshop
Budget plan 19/20 (I)
Indicative plan 21-25 (I)
High-Level Document (D)
Sharing Policy (D)
8 Feb
Schedule Review
Focus on re-baselining
Will mostly impact indicative plan 21-25
22-24 May
Annual Review
Project review
Sep
Council.14
Constr. budget 2019 (A)
Init ops budget 2019 (A)
Indicative plan 2021-2025 (A)
Commitments from Members for 2021-2025
Commitments from Members to completion of construction
3-4 Dec
Political decision-making
Minister level