## Slide 1
S. Gammino for INFN
Oct .3rd, 2018
STATUS of INFN contribution to ESS-accelerator

## Slide 2
WP2 Regional Hubs
ITALY
I.N.F.N.
LNS-Catania: Ion Source and Low-Energy Beam Transport;
LNL-Legnaro: Drift Tube LINAC;
LASA-Milano: Medium Beta Cavities;
LNL-Legnaro: DTL Control System
Elettra Sincrotrone Linac Magnets;
Wire scanner Acquisition;
Spoke RF Power Stations;
Linac Magnets Power Converters;
C.N.R. T-Rex
VESPA

## Slide 3: Milestones 1/3
2017-11-09 Source fully commissioned at INFN-LNS

## Slide 4: Site Acceptance Review
Stable EMU was not provided in time
Back tracing simulation under going

## Slide 5: Milestones 2/3
2018-02-01 Source fully assembled in Lund by INFN-LNS team

## Slide 6: Milestones 3/3
2018-08-03 Source ready for commissioning in Lund

## Slide 7: Installation in Lund

## Slide 8: ISRC&LEBT Documentations
INFN is providing a shared folder collecting:
Drawings
Diagrams
Cable specifications
Manuals
Factory acceptance test
Guides
Certification of conformities
Interface drawings
Non conformity reports
The documentation is collected in folders organized following the Product Breackdown Structure.
700 MB of documentations
Notes: product breackdown structure e visione sito cloud: isrc-estrazione-drawings+ps+certificato rame, insulating column-drawings+certificato vuoto, magneti sorgente con documento completo, magnetron con manuale, lebt solenoidi drawings+ps+fat, chopper+disegni+diagramma blocchi+schematics+signal list, irisdisegni+manuale,supporti-disegni, base-disegni, fug, cavi,
Interfacce documento edgar, cartella interfacce
Standard dentro i disegni, guide, slide andrea+ornella^2

## Slide 9: Summer’18 till now
Safety procedures approved
Plasma on
Beam tests under way
Beam commissioning to be completed in mid-November
Long run test in January

## Slide 10: DTL IK contribution

## Slide 11: DTL Layout
3.6 MeV
89 MeV

## Slide 12: DTL layout
6
6
2
2
2
2
2
2

## Slide 13: RFI dates (2018)
Tank | RFI
Tank 4 | 20/03/2019
Tank 1 | 5/06/2019
Tank 3 | 3/10/2019
Tank 2 | 13/01/2020
Tank 5 | 19/03/2020
Note: the tank 4 completion is not critical, since the first tank to see RF will be tank 1

## Slide 14: Tank Production
Module | Forged | Deep drilling rough machining | Drilling holes and heat treatment | Final fine machining | Metrology | Delivery | Cu-plating
T4-M1 |  |  |  |  |  |  | 
T4-M2 |  |  |  |  |  |  | @ CERN
T4-M3 |  |  |  |  |  |  | 
T4-M4 |  |  |  |  |  |  | 
T1-M1 |  |  |  |  |  |  | 
T1-M2 |  |  |  |  |  |  | 
T1-M3 |  |  |  |  |  |  | 
T1-M4 |  |  |  |  |  |  | 
T3-M1 |  |  |  |  |  |  | 
T3-M2 |  |  |  |  |  |  | 
T3-M3 |  |  |  |  |  |  | 
T3-M4 |  |  |  |  |  |  | 
T2-M1 |  |  |  |  |  |  | 
T2-M2 |  |  |  |  |  |  | 
T2-M3 |  |  |  |  |  |  | 
T2-M4 |  |  |  |  |  |  | 
T5-M1 |  |  |  |  |  |  | 
T5-M2 |  |  |  |  |  |  | 
T5-M3 |  |  |  |  |  |  | 
T5-M4 |  |  |  |  |  |  | 
Comment:
Delivery Rate from CINEL approx. 1module/month

## Slide 16: DT production
DT batch | Machinining Copper parts | Machining SS parts | Machining Stems (UMAS) | Cu plating stems (Tobaldini) | Brazing | Test and metrology | Re-machining | EBW (Zanon) | Final Machining, test, Metrology
T4-1 (1-8) |  |  |  |  |  |  |  |  | 
T4-2 (9-16) |  |  |  |  |  |  |  |  | 
T4-3 (17-23) |  |  |  |  |  |  |  |  | 
T1-1 (1-8) |  |  |  |  |  |  |  |  | 
T1-2 (16-24) |  |  |  |  |  |  |  |  | 
T1-3 (25-32) |  |  |  |  |  |  |  |  | 
T1-4 (33-40) |  |  |  |  |  |  |  |  | 
T1-5 (41-48) |  |  |  |  |  |  |  |  | 
T1-6 (49-54) |  |  |  |  |  |  |  |  | 
T3 (26 DTs) |  |  |  |  |  |  |  |  | 
T2 (30 DTs) |  |  |  |  |  |  |  |  | 
T5 (20 DTs) |  |  |  |  |  |  |  |  | 
Comments:
8 DT batches based on brazing oven capability
Machining optimized to 1 part/day
Some delay from Stem cu-plating supplier
Last 5 steps (BrazingFinal test) to be optimized to 3 weeks
DT-BPM outsourced (CINEL)

## Slide 17: Main Tenders
 | Done | On-going | To be Done
Forged Tubes |  |  | 
Tank & Girder Machining |  |  | 
Cu-Plating Tank |  |  | 
RF windows |  |  | 
LNL and TO milling machine |  |  | 
Power couplers |  |  | 2018
BPM connectors |  |  | 
BPM cables |  |  | 2018
DT – BPM |  |  | 
DT-EBW |  |  | 
CMM @LNL |  |  | 
Stems |  |  | 2019
Trolley |  |  | 
Skid |  |  | 
Tuners, Posts |  |  | 2019
Movable tuners |  |  | 2019
End Plates |  |  | 2018
Brazing, sealing material |  |  | 2018
Cooling material |  |  | 2019

## Slide 18: Other activities
Assembly test at LNL
  Sealing
  Alignment
  Mounting procedures

## Slide 19: Other activities
Bead pull on full scale DTL model
  Bead pull hardware and procedures
  personnel trained to measurements
  Stabilization and tuning demonstration

## Slide 20: Conclusions
The tank 1 RF tests are foreseen in fall 2019. To achieve this
  The high precision tank module and girder machining is proceeding and seems not critical in the schedule.
  The DT production has started, all the main beam elements are delivered, the exact production rate is being consolidated.
  The RF window tender is ongoing (summer 2018 we should have the two windows necessary).
  Concerning power couplers, end plates and other minor components the specs are ready and tenders are programmed within the end of 2018.
  The DTLW has been specified (and ESS is realizing it) while the logistic components (supports, trolley, dummy tuners…….) are under control.
  The tuning procedure was debugged on a low power model of tank2, and the sealing test has been mounted.
  The copper plating of the tanks is critical, since GSI has not accepted the contract.
The production schedule for the other tanks fits with RFI dates (except for copper plating)

## Slide 21: DTL MB contribution

## Slide 22
ESS Medium Beta – Niobium Procurement
The Niobium procurement was completed in September 2018.
All the 482 sheets were scanned at DESY for inclusion of foreign materials and geometrical defects before delivery to cavity manufacturing company.
The first batch was delivered to the company in January 2018.
The second batch was delivered to the company in April 2018.
Niobium Ingot
Niobium Batch Boxes
Water Cut Sheets
Surface Roughness

## Slide 23
ESS Medium Beta – Cavity fabrication
Subcomponents production in full progress
  Half-Cells: IC, PC, EC
  Dumb-Bell: ID, TD
  End Group: EGP, EGC
First cavities foreseen by November 2018
Ancilleries all in house
Dumb Bells
End Group Coupler side
COmponent COntrol DEvice
EGP Tuner rings
EGC Details
Pick Up Antennas

## Slide 24
ESS Medium Beta Preliminary test and documentation
Successful test on MBLG002 cavity (already tested at LASA) done at DESY to test the infrastructure
  Incoming control
  Cold test and related data exchange
  Outgoing control
Successful test of documentation portal and data display dashboard om first half-cells and dumb-bells
  Document Management System based on INFN Alfresco
  ESS Dashboard developed in the framework of the European Brightness Program in collaboration with LNS colleagues

## Slide 25
ESS Medium Beta - Planning
2018
First two cavities
available
First six cavities
(for the M-ECCTD)
First two cavities
test at DESY
Cavities manufacturing at the company
2019
Last cavity delivered
2020
2017