## Slide 1: SRF Planning at ESS, Overview and Status
Nuno Elias on behalf of
Paolo Pierini
Superconducting RF Section, Linac Group, Accelerator Division
European Spallation Source ERIC
September 26st 2019 – SLHIPP9, LANZHOU

## Slide 2: Outline
ESS Intro
  From construction to operation in a (former) ”green-field” organization
High Level Accelerator Milestones
SRF Activities at ESS
  Elliptical test stand preparation
  Incoming cryomodule reception
  (Preparation of) testing
Status of SRF infrastructure
  Tunnel installations
  Power RF installation activities in the service gallery
  Cryoplants status
Summary

## Slide 3: The ESS Accelerator
Scope, Parameters, Technical Performances
Design Drivers:
High Average Beam Power
5 MW (Initially 2 MW)
High Peak Beam Power
125 MW
High Availability (User Facility)
95%
Key parameters & Design criteria:
    Pulse length: 2.86 ms pulses
    Max Energy: 2 GeV
    Pulse peak current: 62.5 mA
    Pulse Repetition rate: 14 Hz
    Particles: Protons (H+)
    Low losses
    Minimize energy use
    Flexible design for risk mitigation and future upgrades
Staged: 1.3 GeV capacity with 2 MW on target for 2025
remaining RF sources (40) installed after 2026
b=0.5
b=0.67
b=0.86

## Slide 4: ESS, large in kind scope
Almost all components of the linac are designed and provided as in kind contributions
After handover scope transferred to ESS
For the SRF linac, the partners are organized in the ESS SRF Collaboration with the workshare:
  Spoke cavities and cryomodules (including prototype) by IPNO, F
  Testing of spokes modules by FREIA laboratory of Uppsala University, S
  Medium beta cavity production, by INFN, I
  High beta cavity production, by STFC, UK
  Cryomodule assembly and prototyping, CEA, F
  Testing of elliptical module at TS2@ESS
Construction project:
  External WP4 (IPNO) WP5 (CEA) for preparation and delivery of components
  Internal WP19 for testing, installation, commissioning and initial operation
ESS Organization: Accelerator Division/Linac Group/SRF Section
Technical SRF work so far at IK, shift to ESS for test/install/commissioning

## Slide 5: From Construction to installation and operation
In Construction Phase (Past)
  Most of the SRF activities during the Construction Phase so far has been performed by the In-Kind partners at the home institutions (CEA, IPNO, INFN and STFC)
  Design, construction and prototyping of cavities and modules
  ESS in charge of the CM “interface” agreements towards neighboring WPs
Installation & Testing is getting very close (Now)
  Delivery of prototypes at test stand happened and first series components in Fall 2019
  Start of the Test Stand 2 operation for the Elliptical CM testing (summer)
  Start of the FREIA Test Stand operation at UU for Spoke CM testing (UU running!)
Getting ready for testing and commissioning (Now & Future)
  Transfer know-how from IK, capture design intent, get ownership of SRF components
  Ramp up of local “hands-on” SRF activities at ESS
(from IK to ESS)
Construction to Test and Operation

## Slide 6: ESS Site Layout

## Slide 7: The ESS site
Target area more advanced now, Tunnel and Gallery transferred to ESS
Klystron Gallery and Technical Areas
Cryo Compressor Building
Cold Boxes
Loading Bay
Temporary Offices/Labs
(all staff on site)
ESS Office Complex
Target
(Laboratories)
LINAC
Experimental Hall (Far)
Exp. Halls
(Near)
Future Campus Area

## Slide 8: Major Accelerator milestones
Source installed and commissioned, MEBT under installation
RFQ and DTL sections delivered in 2019
Staged NC Linac beam commissioning in 2020
  First to DTL1, then to DTL4
  Shielding wall in tunnel will allow concurrent installation of SPK and MB CM
Beam on Dump (BOD) commissioning with Linac up to MB Linac
  Floats in schedule managed centrally
First Science end 2023
Today
2018
2019
2020
2021
2022
2023
2024
2025
ISrc to LEBT
ISrc to DTL1
ISrc to DTL4
Beam on Dump (BOD)
Accelerator Ready for Beam on Target (RBOT)
Beam on Target (BOT)
End of Construction
Start Of User Program (SOUP)

## Slide 9: Installation and Commissioning activities
BOD with Linac up to MBL
HB CM installation until Target is ready for Beam, Not all HB modules RF powered for BOT
Today
2019
2020
2021
2022
ISrc to DTL1
ISrc to DTL4
ISrc to Beam Dump (BOD)
RBOT
ISrc to DTL1 Beam Commissioning
ISrc to DTL4 Beam Commissioning
ISrc to DMPL Beam Commissioning
NCL Installation (RFQ/MEBT/DTL1)
NCL Installation (DTLs)
NCL RF System Installation
SPK CDS Installation
SPK CM Installation
SPK LWU Installation
SPK RF System Installation
Elliptical CDS Installation
MBL CM Installation
MBL LWU Installation
MBL RF System Installation
HBL CM Installation
HBL RF System Installation
HEBT/A2T LWU Installation
Infrastructure
SRF

## Slide 10: Preparation for elliptical module installation and test
ESS in charge of development and procurement of
  Transport container (with vibration dampers) at ESS
  Installation tools and tunnel supports
Transportation tests performed in 2018 with a bare vessel, to validate design and procedures
Prototype cryomodule transported to ESS in February 2019
  Beam vacuum preserved
  Few loose screws on isovac flanges and tuner components
Preparation for cold testing is now taking place
  Cryomodule is installed in Bunker and interconnected to the valve box.
Transport tests and prototype receival
M-ECCTD February 15th 2019

## Slide 11: Preparation for tests
Know what to expect… Estabilished ESS Cavity Database
Live Staging Area
(typ. text files)
ESS Asset Management
ID Installation Structure
Measurement&Calibration DB
(ownCloud service)
Normalized Data
(HDF files, metadata)
Script
Tagging (in metadata)
APPLICATIONS
Browse
Compare
Assess
MEASUREMENTS @ IKC
After fabrication
Intermediate handover
Outgoing
ESS Scope
MEASUREMENTS @ ESS
Incoming
Preparation TS2/Linac
Save
Transfer
Script
https://gitlab.esss.lu.se/SRF_Section
https://meas01.esss.lu.se/owncloud/index.php/login
In QA/QC

## Slide 12: Preparation activities: We need to know our cavities!
Measurement at IK are transferred into DB, to allow reception and evaluation
  Part of handover process IK-CEA-ESS
Data at ESS then adds to DB
Historical trends and visualization, for assessments
ESS Cavity DB
Fabrication
String ASSY@CEA
Cooldown @ CEA
ESS Reception
Handover INFN/CEA

## Slide 13: Preparation activities: Cavity performance data
In the handover we also receive from the IK the summary data of the vertical tests
  Performance data (Eacc, radiation levels)
  Calibration data for TS2
First four cavities of M1 string, real time transfer
e.g. PU calibration data from DESY VT

## Slide 14: Sensitivity analysis
Data to be used during TS2/Tunnel preparation phases and incoming checks
  Account for change in environmental conditions
From demonstrator retrieved data of expected behavior of series in TS2
Parameter, all data kHz | CAV1 M001 | CAV2 MP04 | CAV3 MP01 | CAV4 MP02 | <AVE> SPREAD
From string in vacuum, RT, VV&tank PA, to 4.2 K | 1186 | 1181 | 1169 | 1150 | 1172±18
From string in vacuum, RF, VV&tank PA, to 2K | 1103 | 1107 | 1091 | 1080 | 1095±14
4.2K to 2K, cold, (Pressure sensitivity 1 bar to 30 mbar ) | -83 | -74 | -78 | -70 | -76±7
String from air to vacuum (tuner, tank & VV air, RT) | 174 | 177 | 190 | 195 | 184±11
Vessel from air to vacuum (tuner, string vacuum, tank air, RT) | 111 | 105 | 107 | 75 | 99±18

## Slide 15: Preparation activities: SRF
Established local laboratories
All the prior development phase at IK, “hands-on” capabilities at ESS
  Setup of SRF Laboratory for the preparation of all incoming reception measurements
  Permanent laboratories in B02 building when available
INFN b=0.5 5-cell elliptical
IPNO ESS Double Spoke

## Slide 16: Preparation activities: Mechanical
Development of installation tools
ESS responsibility for transport tools (IK, internal) and supports
  In close contact with ESS Engineering Division (Rigging, Design, Manuf.)
Customization of CEA assembly tools to adapt to the TS2/Tunnel
  e.g. Doorknob Installation Tool
Design at ESS discussed with IK
  Part of know-how transfer process, support from EIS
DK installation tool (ESS)
On site transport cart
Spoke cart/support

## Slide 17: Preparation activities: Incoming inspections at TS2
Setup of Module reception area with M-ECCTD
Preparation of areas for
  Storage of components/instrumentations/tools
  Workstations for mechanical, electrical and RF incoming inspections
  Workstations for activities needed for the TS2 test/tunnel
    E.g. dismount/remount of transport fixations on thermal shields and string
  Local instrumentation racks
  Training teams!
    Main mechanical reception operations on M-ECCTD
    iso-vacuum procedures
    RF incoming measurements
    Electrical measurements on inner instruments
    Assembly of Doorknobs
TS2 Bunker Supports
Doorknobs
DK Fixation
Incoming reception area

## Slide 18: Test Stand 2 Readiness
Radiation authority permit and internal Safety Readiness Review Done
Cryoline
RFDS
VB
CM cabling ongoing…
RFDS
Cooling circuits
Variable Power Dividers
Control System Racks
Klystron commissioning on loads

## Slide 19: Testing at TS2
Before Cooldown
  Warm Cable & Component Calibration
  Warm Input RF Couplers Conditioning
After cooldown no HP RF
  Cold cable Calibration
  4K/2K passband measurements, before tuning
  Cavities slow Tuners Test and Cavities Tuning
  2K passband measurements, after tuning
Stable conditions @2K starting HP RF
  Cold coupler Conditioning (off-resonance)
  Open loop operation at low forward power
  Fine tuning with Pt
  Calibration
  Eacc ramp up (cavities on resonance)
  Field emission measurements (dose & energy spectrum)
Steady state test cycle: one CM/month
Test goals
  Performance assessment (specs fulfilled?)
  Limiting mechanisms (quench, FE, Power limitations)
  Comparison/correlation wrt VT results (and cryomodule results, where possible)
  Store data for future Linac operations (degradation, perf. recovery)

## Slide 20: 2020, concurrent SPK/MB ELL Component installation
13 Spokes
9 MB ELL

## Slide 21: Spoke section gallery preparation
Waveguides
Manifolds
Cable trays for racks
support structures
Loads
Circulators

## Slide 22: Delivery of MB Klystrons
Half of production stored in gallery
a
A. Sunesson/M.Jensen, ESS

## Slide 23: Stubs, gallery side
Close to completion, for the start of the cable pulling operations
Spokes
Transition
Elliptical
Cable conduits
WR2300HH
WR1150
A. Sunesson/M.Jensen, ESS

## Slide 24: Stubs, tunnel side
Installation of tunnel components of RFDS before VB components
Cryoline
RFDS for 2 modules
A. Sunesson/M.Jensen, ESS

## Slide 25: Tunnel: Cryomodule Dummies (and Soon Warm Units)
In the accelerator “contingency” space (reserved for upgrades)
To the Dump
Same flange to flange length of CM
Linac Warm Units here
M. Juni Ferreira/ESS

## Slide 26: Cryogenics for the Linac
ACCP (ACcelerator CryoPlant)
  Main plant for the entire accelerator (96% of energy gain by SRF)
  3 kW @ 2K, 11.4 kW @ 40-50K, 9 g/s liquefaction
  Designed to cope with upgrade scenario in the contingency space
  Producing LHe: ready for CDS commissioning in Q1 2020.
  Commissioning (including 2 K operation with cold compressors) completed by 2019
Three cryoplants procured and being commissioned by ESS Cryo Team
14 High Beta Cryomodules
(Contingency, 116 m)
Endbox
Cryogenic Distribution Line
(120 m)
21 High Beta Cryomodules (174 m)
9 Medium Beta
Cryomodules
(75 m)
13 Spoke
Cryomodules
(54 m)
Linac
Cryoplant
Cryogenic Distribution Line (310 m)
Endbox
Cryogenic Transfer Line (75 m)
Splitting box
X.Wang/P. Arnold, ESS

## Slide 27: Cryogenics for the Linac
CDS (Cryogenic Distribution System)
  Delivers cryogenics to the Accelerator from ACCP, provided as IK contribution by
    WUST/PL (CDS-ELL)
    IPNO/FR (CDS-SPK)
  9 CDS-ELL Valve boxes installed and connected with Cryolines in tunnel, and other 3 positioned
  Next: CDS-SPK (VB delays)
Goal is CDS cooldown by end 2019-beginning 2020
Installation of linac Cryogenic Distribution line
J. Fredrick, ESS

## Slide 28: Cryogenics for the Test Stand and Moderator
TICP (Test and Instruments CryoPlant)
  Cooling for CM Test Stand 2: 76W @ 2K, 420W @ 40K, 6 l/h Liquefaction
  Liquefaction for Neutron Instruments / Sample Environments: 7500 l/month
  Commissioned to specs and currently providing liquid helium to Lund University and MAX IV
  Warm Pumps for subatmospheric operation
  Commissioning of transfer line to TS2 currently undergoing, then cryogenic operation of the TS2 with modules could start in summer
TMCP (Target Moderator CryoPlant)
  Non-accelerator related
  For the LH2 cooling of the Target Moderator: 30 kW @ 15-20 K
  Entering commissioning stage
Installation of linac Cryogenic Distribution line
Courtesy P. Arnold, ESS

## Slide 29: Summary
Installation/Testing goals for 2019
  Completion of CDS-EL and CDS-SPK
  He recovery line in tunnel (venting events)
  HEBT LWUs and beam lines
  Completion of Stubs and waveguides along tunnel walls
  Installation of Cryomodule support stands
  Preparation of the infrastructure: cabling, piping and support systems
  Start TS2 operation with prototypes
  Start testing of series spokes and elliptical modules
Module installation in tunnel will follow in early 2020, after the testing of the initial series components now under assembly)
Intense workload across all SRF machine section

## Slide 30
Thank you for the attention!