## Slide 1: ESS Project Update
John Haines
ESS Project Manager
IKON 16
European Spallation Source ERIC
11 Feb 2019

## Slide 2: 2018 project highlights
Established new ESS-wide baseline plan to improve coordination, communication, execution, and tracking of work
Handed-over klystron gallery and two more buildings from construction partner to ESS
Structural design of Target Building and Instrument Halls no longer on critical path
Formed new Infrastructure Subproject to be ready for Accelerator equipment deliveries and commissioning
Began commissioning Ion Source and LEBT and three helium cryo-plants
Installed Active Cell infrastructure embedded in buildings - waste pits, Active Cell liner
Held successful Bunker Critical Design Review

## Slide 3: ESS Construction Project is 57% complete
Chart: M€
Schedule Variance (SV) - 22 M€
Cost Variance (CV) - 2 M€
Schedule Perf. Index (SPI) 0.98
Cost Perf. Index (CPI) 0.99
SV
“Excellent” cost and schedule performance reflect our re-baselining in May 2018
Schedule Variance is mainly due to In-Kind work delays - more discussion of critical in-kind delays later

## Slide 4: We have managed to keep Estimate-at-Completion stable since Re-Baseline
Sub-Project | Costs in M€ |  |  | 
 | May 2018 BAC | Changes2 | Oct 2018 BAC | Oct 2018 EAC
Accelerator | 496.7 | 9.1 | 505.8 | 526.7
Target | 189.7 | 3.6 | 193.3 | 223.2
ICS | 79.3 | 3.5 | 82.8 | 89.6
NSS | 361.0 | 0.0 | 361.0 | 367.2
CF | 714.9 | 2.8 | 717.7 | 778.4
Central Support1 | 180.2 | 2.9 | 183.1 | 185.8
Total | 2022 | 22 | 2044 | 2171
1 Central Support includes Admin Directorate, Technical Management & Support, ESH&Q, and DG Office
2 Changes include extra costs for installation (11.5 M€ for Accelerator, Target, and ICS), accelerator testing (3.6 M€), unforeseen ESH&Q workforce (2.9 M€), and target monolith shielding (1.5 M€)
EAC was 2174 M€ after May-2018 re-baseline

## Slide 5: Available contingency is more than forecast increases, but little remains for unforeseen items
Forecast increases are less than available contingency, but leaves only 39 M€ for unforeseen items
Item | M€
Available Budget, i.e. Total Project Cost (TPC)* | 2210
Budget at Completion (BAC) (No contingency) | 2044
Contingency available (TPC- BAC) | 166
Estimate-at-Completion (EAC) | 2171
Forecast Increase (EAC-BAC) | 127
* Per Council resolution 13.06.a assumes full initial funding (1843 M€2013 plus additional host state contribution) plus additional 135 M€2013 based on unforeseen costs for handling seismic and antagonistic threat requirements

## Slide 6: Summary Schedule and Critical Path for Remaining Work
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float
Accel RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker and Test Beam Line RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
Instrument Hall Access for Start of Installation
Hi-Beta Install
1.3 GeV Capability Installed
BOT - Beam on Target
ES - Early Science
SOUP - Start of User Programme
EOC - End of Construction project
RXXX - Ready for XXX
CF, Target, and NSS (Bunker) teams holding zero-float Critical path to BOT
Float to Accelerator RBOT reduced from 14 months to 11 months due to IK delivery slippage
Red line indicates critical path
ES

## Slide 7: Staged Licensing process enables operation according to commissioning stages
Regulator review of license request
Licensing Approved
Ion Source & LEBT Permit
Cold Linac Permit
Normal Conducting
Linac Permit
Beam on Target Permit

## Slide 8: In-Kind Deliveries that are on or within 40 days of the Critical Path
Critical Path to Target RBOT, which has three months float to BOT
  Monolith vessel - ESS Bilbao
  Assembled Target Wheel - ESS Bilbao
  Proton Beam Window - ESS Bilbao
  Note that delivery of the Monolith Port Blocks, which is being self-performed by ESS-Lund, is near critical path
Critical Path to Accelerator RBOT, which has 14 11 months float to BOT
  RF distribution systems and DTL klystrons - ESS Bilbao
  Spoke cavities/cryomodules and cryo-distribution system + controls for all cryo-distribution - IPNO
  Spoke RF equipment - Elettra and INFN
  Med Beta cryomodules - CEA because of LASA-INFN
  High Beta cryomodules - CEA because of STFC
  Elliptical CM cryo-distribution system - Wroclaw UT
  DTL - INFN
  RFQ - CEA
Red indicates recent changes to list
This list represents only 10 of 226 In-Kind packages;
> 95% of deliveries are expected to be at ESS when needed

## Slide 9: Working to Mitigate Top Project Risks
Risk: IKC delivery delays could threaten critical path
Mitigation:
Frequent interactions at various levels with partner institute’s management and governance to raise visibility and seek solutions
    Reporting at Monthly integrated Project Review Meetings to raise ESS management awareness
    Highlighting at Technical Board and Collaboration Board Meetings with partner institutes - peer pressure
    Highlighting highest risk items at Governance Meetings (IKRC, AFC, Council) to seek help from “owners”
Risk: Installation delays due to lack of readiness to perform work
Mitigation:
    Hired ESS installation Manager to coordinate work and establish processes
    Hired installation coordinators for all sub-projects, and other key support positions
    Awarding framework contracts to access mechanical and electrical installation suppliers
    Established new sub-project to perform accelerator and ICS infrastructure design, procurement, and installation work

## Slide 10: High-level Project goals for 2019
Secure license for Warm Linac commissioning
Accelerator, ICS, and Infrastructure
  IK partners deliver RFQ, MEBT, and DTL1
  Complete Accelerator & ICS infrastructure installation for warm linac
  Start commissioning from Ion Source through DTL1
CF, Target, and Instruments
  Achieve Access to Target Building and E-Buildings
  IK partners deliver Tuning Beam Dump, Moderator and Reflector Plug, and Monolith Vessel
  Begin installation of Target Monolith and Instrument components
  Incorporate detailed plans for all early instruments, including resource-loading for installation
Manage cost and schedule to ensure project success - focus on “first science” goal
  Achieve balance between available contingency and estimated contingency needed
  Maintain BOT milestone in 2022 and Early Science & SOUP milestones in 2023

## Slide 11: Concluding Remarks
Project is 57% complete
  Critical civil construction progressing as planned - Target Building design ramping-down
  Commissioning Ion source and LEBT and three cryo-plants
Estimate at Completion projection essentially unchanged since May 2018 Re-Baseline
  However, concern that contingency is only 39 M€ more than forecast increases has led us to kick-off new cost reduction, staffing plan, and risk analysis efforts
Baseline plan implemented
  Holding zero-schedule float BOT and SOUP milestones so far
  Concerned about multiple in-kind deliveries on or near critical path - highlighting these with governance bodies to support issue resolution