## Slide 1: Common Shielding Project Status following PDR
Ken Andersen, Zvonko Lazic, Senad Kudumovic, Phil Bentley
IKON-16
Lund, 11th of February 2019

## Slide 2: Scope of proposal in April 2018
Offer: guide shielding for long and medium instruments
  from bunker to cave
  include shielding around choppers
  Include all long instruments (West sector)
  No short instruments: LOKI, FREIA, ESTIA
    strongly integrated with neighbouring beamlines
  Include medium instruments: ODIN, DREAM, VESPA, SKADI
Use engineering resources from bunker team
Use whatever neutronics resources we can get our hands on
  Mainly from instruments which have signed up
8 instruments signed up:
  Long instruments: CSPEC, BIFROST, MAGIC, T-REX, HEIMDAL
  Medium instruments: ODIN, DREAM, VESPA

## Slide 3: Scope of Phase 1 Project
December 2018:
  mechanical design completed
    Instrument-specific solutions
    analysis of compatibility with logistics
    3D model
    integration drawing(s)
  preliminary neutronics calculations completed
    validating and driving mechanical design
    reports issued
  cost offer for each instrument
  manufacturing and purchasing strategy agreed
January 2019: Preliminary Design Review

## Slide 4: Priorities for Guide Shielding
1. Shielding performance
  Reaching 3 µSv/hr
2. Activation
  Choose standard components, so they count as spare parts, not waste
  Apply ALARA for decommissioning
  Maintenance access within 24 hours
3. Instrument background
  Primarily addressed by cave design
  Long distance (60-170m) also helps: chopper pits act as expansion zones
  Boron-rich inner layer reduces albedo back-shine
Expected outcome: cost-effective solution which instruments will choose to sign up to
Modular design: inner steel layer + outer concrete layer
  Shrink to minimise cost
  High degree of standardisation
  Vary steel and concrete thickness as required

## Slide 5: Phase 1 Project Organisation
Ken Andersen
Project Sponsor
Zvonko Lazic
Project Manager
Phillip Bentley
Physics Lead
Mark Ridgley
Systems Documentation
Senad Kudumovic
Design Engineer
Tsito Randriamalala
Ext. Neutronics
Rodion Kolevatov
Ext. Neutronics
Valentina Santoro
Neutronics
Nataliia Cherkashyna
Neutronics
Damian Martin Rodriguez
Neutronics
Florian Grünauer
Ext. Neutronics
Giuseppe Scionti
Ext. Neutronics
Uwe Filges
Ext. Neutronics
Gabor Laszlo
Engineering Advisor

## Slide 6: Phase 1 Project Organisation
Ken Andersen
Project Sponsor
Zvonko Lazic
Project Manager
Phillip Bentley
Physics Lead
Mark Ridgley
Systems Documentation
Senad Kudumovic
Design Engineer
Tsito Randriamalala
Ext. Neutronics
Rodion Kolevatov
Ext. Neutronics
Valentina Santoro
Neutronics
Nataliia Cherkashyna
Neutronics
Damian Martin Rodriguez
Neutronics
Florian Grünauer
Ext. Neutronics
Giuseppe Scionti
Ext. Neutronics
Uwe Filges
Ext. Neutronics
Gabor Laszlo
Engineering Advisor
Phase 1 Project Budget: 150k€
DREAM & T-REX
BIFROST & HEIMDAL
ODIN & CSPEC
Instrument Contributions
10k€ each
VESPA
MAGIC

## Slide 7: What happened in Phase 1?
2018 | April | May | June | July | August | Sep. | Oct. | Nov. | Dec.
Proposal Development |  |  |  |  |  |  |  |  | 
ICB10 Meeting |  |  |  |  |  |  |  |  | 
Sign-up |  |  |  |  |  |  |  |  | 
Preparation |  |  |  |  |  |  |  |  | 
Project kick-off |  |  |  |  |  |  |  |  | 
Engineering design |  |  |  |  |  |  |  |  | 
Neutronics workshop |  |  |  |  |  |  |  |  | 
Neutronics start |  |  |  |  |  |  |  |  | 
Neutronics work |  |  |  |  |  |  |  |  | 
Design work complete |  |  |  |  |  |  |  |  | 
Costing & documentation |  |  |  |  |  |  |  |  | 
Project completion |  |  |  |  |  |  |  |  | 
Agreed work-flow
  Weekly minuted meetings for progress update and sharing of tasks
  Documentation written as work progressed and shared on-line
Work progressed according to schedule

## Slide 8: Neutronics Work
Guides: within/outside line-of-sight
Chopper pits: within/outside line-of-sight

## Slide 9: Neutronics Work
Guides: within/outside line-of-sight
Chopper pits: within/outside line-of-sight
Outside line-of-sight:
(Rodion Kolevatov)

## Slide 10: Neutronics Work
Guides: within/outside line-of-sight
Chopper pits: within/outside line-of-sight
Within line-of-sight:
(ODIN, Florian Grünauer)

## Slide 11: Neutronics Work
Guides: within/outside line-of-sight
Chopper pits: within/outside line-of-sight
Within line-of-sight:
(DREAM, Tsito Randriamalala)

## Slide 12: Neutronics Work
Guides: within/outside line-of-sight
Chopper pits: within/outside line-of-sight
In each case, extract required materials thicknesses

## Slide 13: Neutronics Work
 |  | 30 | 40 | 60 | 80 | 100 | 120 | 140 | 150 | 160
CSPEC | B4C cement steel concrete | 2 10 75 | 2 10 75 | 2 10 75 | 2 10 50 | 2 10 50 | 2 10 50 | 2 10 60 | 2 10 60 | 2 10 100
BIFROST | B4C cement steel concrete | 2 10 65 | 2 10 50 | 2 10 40 | 2 10 40 | 2 10 40 | 2 10 40 | 2 10 40 | 2 10 40 | 2 0 110
MAGIC | B4C cement steel concrete | 2 10 50 | 2 10 50 | 2 10 50 | 2 20 80 | 2 0 50 | 2 0 50 | 2 0 50 | 2 0 50 | 2 0 50
T-REX | B4C cement Steel B4C cement concrete | 2 10 2 60 | 2 10 2 60 | 2 10 2 60 | 2 10 0 50 | 2 10 0 50 | 2 10 0 50 | 2 10 0 50 | 2 10 0 50 | 2 10 0 80
DREAM | B4C cement Steel B4C cement concrete | 2 10 2 60 | 2 10 2 60 | 2 10 2 60 | 2 10 0 60 |  |  |  |  | 

## Slide 14: Shielding Evolution
Concept 1
Concept 3
Concept 2
Current Concept
Concept 4

## Slide 15: Structural/Construction
Designed to be installed / maintained
Shielding close to the instrument guide
Lower shielding is static (not removed for maintenance)
Minimising load removal effects on miss/re/alignment
Load effect minimisation

## Slide 16: Structural/Construction
D01/D03 vs E02
D01/D03
E02
1 m
Identical upper shielding blocks in D01/D03 and E02
Similar lower shielding blocks in D01/D03 and E02
D01/D03
E02

## Slide 17: Structural/Construction
Same formwork – different blocks

## Slide 18: Survey and Alignment E02
”pocket” block
”extrude” block
Lifting optimisation
Blocks designed so as to place ”pocket” blocks in line with the piles
only ONE lift needed to access alignment features

## Slide 19: Survey and Alignment D01/D03 – E02
”pocket” block
”extrude-pocket” block
Lifting optimisation
Blocks designed so as to place ”pocket” blocks in line with the piles
only ONE lift needed to access alignment features

## Slide 20: Preliminary Design Review 24/01/2019
Review Committee: Masa Arai (chair), Sigrid Kozielski/Ricardo Bevilacqua, Daniel Lyngh, Luca Zanini, Fabien Rey, Iain Sutton
System requirements
System verification plan
Preliminary design report
Risk Analysis
Conceptual shielding designs
  Guide shielding in D01/D03
  Guide shielding E02
  Chopper pits
Neutronics reports
  Within line-of-sight: DREAM and T-REX, T. Randriamalala
  Prompt gamma shielding, R. Kolevatov
  ODIN shielding, F. Grünauer
  BIFROST up to 35m, R. Kolevatov
  HEIMDAL, R. Kolevatov
Information given in presentations
  Answers to questions

## Slide 21: Main Issues Identified at PDR
Interfaces at CF wall and instrument cave: include installation and maintenance schemes
Ensure imposition of 4m guide sections is compatible with all instruments at the CF wall
Cost-effectiveness of steel+concrete compared to heavy concrete, steel and lead
Revisit mounting of optics D01/D03
  On support blocks or on floor
Floor loading
  We had misunderstood load limits in E02 provided by CF
Clarify scheme for recycling the shielding blocks
  Take instrument lifetime and new instruments into account
Clarify the cost estimates

## Slide 22: Project Timeline
 | 2018 H1 | 2018 H2 | 2019 H1 | 2019 H2 | 2020 H1 | 2020 H2 | 2021 H1 | 2021 H2
Proposal Development |  |  |  |  |  |  |  | 
ICB10 Meeting |  |  |  |  |  |  |  | 
Concept Development |  |  |  |  |  |  |  | 
PDR |  |  |  |  |  |  |  | 
Detailed Design |  |  |  |  |  |  |  | 
IDR & TG3 |  |  |  |  |  |  |  | 
Procurement |  |  |  |  |  |  |  | 
Contract Signature |  |  |  |  |  |  |  | 
Manufacturing |  |  |  |  |  |  |  | 
First Delivery |  |  |  |  |  |  |  | 
Installation |  |  |  |  |  |  |  | 
Register interest:
pay 10 k€ towards Phase 1
Decision point:
cost offer made
commit expenditure from instrument budget
Earliest possible start of installation
Phase 2: Instrument-specific
Phase 1

## Slide 23: Price Offers
Fixed price offers are being made
  December 2018: ODIN, DREAM, CSPEC, BIFROST, T-REX
  MAGIC (February), HEIMDAL (March), VESPA (May)
  Agreement to include MIRACLES. Discussions starting
ESS will guarantee shielding performance
  Deficiencies to biological shielding will be fixed at no added cost to instruments
  ESS takes the risk on cost overruns and performance issues
Delivery options for discussion with instruments
  1. ESS will act as provider to instrument partner delivering shielding
  2. Guide shielding removed from costbook value of IK contribution
Discussions on-going with individual instruments
  Agreements in principle to be reached quickly
  TAs will be modified accordingly, if needed

## Slide 24: What happens next
Finalise preliminary design and costing for MAGIC, HEIMDAL, VESPA
Get decisions from all instruments
  Exchange information and discuss terms and conditions
Establish prioritisation on installation timescale
  1. CSPEC, BIFROST, MAGIC
  2. DREAM, ODIN
  3. T-REX
  4. HEIMDAL
  5. VESPA
Establish detailed operational requirements
  Start with early instruments
  Modify design and costing if required
Agree on timescale for detailed design
  To be agreed individually with each instrument
  Establish dates for IDRs and sub-TG3s
Secure needed resources
  Engineering resources mostly secured
  Neutronics resourcing: use internal and external resourcing, following prioritisation

## Slide 25: Thank you!
5th June 2015
ESS site 2016

## Slide 26: Purchasing & Manufacturing plan
Cold box arrival to ESS
Stage I (tender publication):
Following publication of the tender, the supplier is selected.
The supplier and NSS enter the contract, based on open book, collaborative set-up (OBC).
The OBC ensures cost tracking, allows the latest changes to be implemented during the contractor’ manufacturing design stage.
Stage II (manufacturing design):
ESS provides design & manufacturing QA engineer.
The manufacturing takes place at contractor’ facility; the system components are produced and delivered according to ESS integrated schedule.
Stage III (installation):
NSS provides installation manager and installation resources (hardware and workforce).
The contractor provides the installation supervisor.
Following successful installation, with sign-off from both, the NSS installation manager and the contractor installation supervisor, the contract is closed.

## Slide 27: Purchasing & Manufacturing plan
The project structure could look like this:
Supplier – manages ‘production office*’ (houses common shielding production project personnel, drafting personnel; calls for any ‘open book contract’ discussions)
*This office is responsible for ordering all materials, production of detailed drawings, managing logistics and assembly of individual blocks; manages delivery of completed components to the ESS site.
NSS Common Shielding office – oversees the drafting and production effort. Enables collaboration model to work (ensures communication is maintained, key milestones are reviewed, and calls for any discussions relating to managing the open book contract).

## Slide 28: Costing
Cold box arrival to ESS
We have market prices for bulk materials, and for cutting/manufacturing cost.
  We have obtained bulk material pricing from the companies involved in current ESS projects,
  The steel bulk unit prices are obtained from a Norwegian and Danish steel suppliers.
    Median numbers are taken into calculation for the final sum.
Uncertainties include:
  Raw material utilization (especially for plate materials).
  Logistics cost.
  Installation model (NSS is responsible for securing installation resources. All available data is correct today, but changes are expected as the installation time approaches).

## Slide 29: The Common Shielding Project - Tender
Supplier’ scope:
Concept design evaluation
Detailed design
Design validation where required (internal reinforcement, lifting features,…)
Manufacture
FATs
Delivery to site
Installation oversight
SATs oversight
Tendering requirements
Delivery schedule
Interfaces definition
Design life requirements
QC requirements
Manufacturing QC oversight
Concept design
Installation
ESS scope
Open book, collaborative contract
Notes: Explain better design deliverables (what is it we have defined and what is it contractor will deliver)

## Slide 30: Storyboard The Common Shielding Project
Manufacture
Transportation
On Site Activities
Installation
Decommissioning
The Common Shielding Project tender has to be placed taking into account ESS installation schedule.
Being a large project (by volume), the plan is to stage the production and delivery in the order of the NSS need, as dictated by the ESS integrated schedule. For example, the first shielding blocks for the first instrument in line for installation will be delivered by mid-2020
Notes: NBPI is under design CDR is not done yet so this storyboard is our plan during detailed design and might be subject to change as time progress
Decommissioning is for inserts/plugs, not the facility

## Slide 31: Installation Schedules
T-REX, HEIMDAL, VESPA to be determined…

## Slide 32: Manufacturing & Installation
Transport
Manufacture
Transportation
On Site Activities
Installation
Decommissioning
Design for manufacturing (detailing)
Production
E02.1 blocks
E02.2 blocks
D01/03 blocks
Design approval
Manufacturing QC & FATs
Installation
Installation controller
Installation Manager
Acceptance tests
Contractor
ESS

## Slide 33: The Common Shielding Project Overview Outlook
Mechanical Design – Conceptual design finalized
Physics – The first round of simulations, providing input for the conceptual design, has been completed
Documentation – PDR required documentation completed.
Purchasing/schedule – Following this PDR, we will prioritize work and schedule delivery of the final design(s) in the order of instrument installation priorities. Timing for the (first) CDR will be determined following the PDR and sign up (to the project) of a number of instruments.
Budget - Current cost estimates are on budget.

## Slide 34: Structural/Construction: Chopper Pit
2 lifts for wide opening in the roof (≈1 m)
or
2 lifts for narrow opening from 3 sides (≈0,3 m)
4 lifts for full access

## Slide 35: Feedthroughs: Chopper Pit
Feedthroughs for Chopper pits are intended to go through the lower shielding. Opening is 250 x 250 mm2 which will allow installation of the feedthrough pipe Ø200 mm with bending radius 110 mm. (size to be checked and validated during detailed design for each chopper with Chopper group).

## Slide 36: Feedthroughs: Vacuum Pipes
Feedthroughs for vacuum pipes inside the E02 portion of the shielding are intended to be through the side blocks next to the piles. Current opening inside the side block is 150 x 150 mm2. (to be checked and validated during detailed design with Vacuum group)
E02
D01/D03

## Slide 37: Interfaces: Bunker Wall
Customized heavy concrete panels around guide shielding connected to the bunker wall
3 Lifts to reach Bunker Guide Insert.

## Slide 38: Interfaces CF Wall
Guide shielding through and next to the CF wall will be bricked. Driven by that, alignment guide features should be as far as possible from the CF wall to minimize lifts during realignment.
Two customized blocks outside the bricked portion of the shielding, reachable with cantilever spreader bar

## Slide 39: Interfaces Caves
Cave interface to be defined in detailing phase in collaboration with cave designers. General plan is to have simple opening for guide shielding providing necessary chicanes.
Gap between E02 floor and cave in E01 to be bridged using D01/D03 supporting blocks stacked in two levels