## Procurremnt
nBLM: procurement plan; MEBT & DTL1 nBLM installation time windows Details about procurement by CEA (parts, suppliers, lead time) in CDR3 report from CEA: L.Segui, "nBLM project, CDR 1.2- final ", https://indico.esss.lu.se/event/1173/ | [8 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com | [18 empty] | Learn about the Pro version >
[Company Name]
| Project Start Date | 2019-01-01 |  |  |  |  | Display Week | 7 | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35
| Project Lead | [7 empty] | 2019-02-11 | [6 empty] | 2019-02-18 | [6 empty] | 2019-02-25 | [6 empty] | 2019-03-04 | [6 empty] | 2019-03-11 | [6 empty] | 2019-03-18 | [6 empty] | 2019-03-25 | [6 empty] | 2019-04-01 | [6 empty] | 2019-04-08 | [6 empty] | 2019-04-15 | [6 empty] | 2019-04-22 | [6 empty] | 2019-04-29 | [6 empty] | 2019-05-06 | [6 empty] | 2019-05-13 | [6 empty] | 2019-05-20 | [6 empty] | 2019-05-27 | [6 empty] | 2019-06-03 | [6 empty] | 2019-06-10 | [6 empty] | 2019-06-17 | [6 empty] | 2019-06-24 | [6 empty] | 2019-07-01 | [6 empty] | 2019-07-08 | [6 empty] | 2019-07-15 | [6 empty] | 2019-07-22 | [6 empty] | 2019-07-29 | [6 empty] | 2019-08-05 | [6 empty] | 2019-08-12 | [6 empty] | 2019-08-19 | [6 empty] | 2019-08-26
 | time axis 2019-02-11 to 2019-09-01
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2019-02-11 to 2019-09-01
1 | Accelerator schedule - from TB28, 17.1.2019
1.1 | MEBT installation - vacuum part assembly |  |  | 2019-06-24 | 2019-08-04 | 42 | 0% | 30
1.2 | DTL1 installation - tank installation |  |  | 2019-08-19 | 2019-09-15 | 28 | 0% | 20
1.3 | MPS - final integration test (ICS) |  |  | 2019-10-30 | 2019-11-26 | 28 | 0% | 20
1.4 | RFQ/MEBT/DTL1 RF Conditioning window |  |  | 2019-10-28 | 2019-12-22 | 56 | 0% | 40
1.5 | Beam Commissioing: ISr to DTL1 |  |  | 2019-12-16 | 2020-03-22 | 98 | 0% | 70
2 | nBLM installation time slots
2.1 | Detetors (short tubes, cables, support) in tunnel
2.1.1 | MEBT detectors (4) |  |  | 2019-07-27 | 2019-08-02 | 7 | 0% | 5
2.1.2 | DTL1 detectors (8) |  |  | 2019-09-07 | 2019-09-13 | 7 | 0% | 5
2.2 | Electronics in racks - installation time window
2.2.1 | MEBT detectors (4) |  |  | 2019-07-22 | 2019-08-18 | 28 | 0% | 20
2.2.2 | DTL1 detectors (8) |  |  | 2019-07-22 | 2019-08-18 | 28 | 0% | 20
3 | nBLM reviews
3.1 | CEA IK (DEDIP) Kick-off | / |  | 2016-06-25 | 2016-06-26 | 2 | 100% | 0
3.2 | PDR1 | / |  | 2016-12-12 | 2016-12-12 | 1 | 100% | 1
3.3 | PDR2 | / |  | 2017-07-10 | 2017-07-11 | 2 | 100% | 2
3.4 | CDR1 | / |  | 2017-12-04 | 2017-12-05 | 2 | 100% | 2
3.5 | CDR2 | / |  | 2018-07-12 | 2018-07-12 | 1 | 100% | 1
3.6 | CDR3 | / |  | 2019-02-12 | 2019-02-12 | 1 | 0% | 1
4 | Detectors & FEE
4.1 | Design | CEA Dedip |  | 2016-06-25 | 2018-07-11 | 747 | 100% | 533
4.2 | Procurment - mech. Parts | CEA Dedip |  | 2018-07-12 | 2019-02-24 | 228 | 95% | 162
4.3 | Production & QA tests | CEA Dedip |  | 2019-02-25 | 2019-05-26 | 91 | 0% | 65
4.3.1 | det. 1-9 | CEA Dedip |  | 2019-02-25 | 2019-03-24 | 28 | 0% | 20
4.3.2 | det.10-18 | CEA Dedip |  | 2019-03-04 | 2019-03-31 | 28 | 0% | 20
4.3.3 | det. 19-27 | CEA Dedip |  | 2019-03-11 | 2019-04-07 | 28 | 0% | 20
4.3.4 | det. 28-36 | CEA Dedip |  | 2019-03-18 | 2019-04-14 | 28 | 0% | 20
4.3.5 | det. 37-45 | CEA Dedip |  | 2019-03-25 | 2019-04-21 | 28 | 0% | 20
4.3.6 | det. 46-54 | CEA Dedip |  | 2019-04-01 | 2019-04-28 | 28 | 0% | 20
4.3.7 | det. 55-63 | CEA Dedip |  | 2019-04-08 | 2019-05-05 | 28 | 0% | 20
4.3.8 | det. 64-72 | CEA Dedip |  | 2019-04-15 | 2019-05-12 | 28 | 0% | 20
4.3.9 | det. 73-81 | CEA Dedip |  | 2019-04-22 | 2019-05-19 | 28 | 0% | 20
4.3.10 | det. 82-84 | CEA Dedip |  | 2019-04-29 | 2019-05-26 | 28 | 0% | 20
4.4 | Delivery to ESS | CEA Dedip |  | 2019-03-25 | 2019-06-02 | 28 | 0% | 50
4.5 | tests at ESS - time window | ESS |  | 2019-04-01 | 2019-06-09 | 28 | 0% | 50
4.6 | RFI -all detetctors | / |  | 2019-06-10 | 2019-06-10 | 1 | 0% | 1
4.7 | installation at MEBT (4 det) | ESS BI |  | 2019-07-27 | 2019-08-02 | 7 | 0% | 5
4.8 | installation at DTL1 (8 det) | ESS BI |  | 2019-09-07 | 2019-09-13 | 7 | 0% | 5
5 | Electronics
5.1 | IOxOS ADC3111
5.1.1 | procur. process preparation | CEA Dedip |  | 2019-02-13 | 2019-02-26 | 14 | 0% | 10
5.1.2 | Procurement | CEA Dedip |  | 2019-02-27 | 2019-05-07 | 70 | 0% | 50
5.1.3 | QA tests | CEA Dedip |  | 2019-05-08 | 2019-05-14 | 7 | 0% | 5
5.1.4 | Delivery to ESS | CEA Dedip |  | 2019-05-15 | 2019-05-21 | 7 | 0% | 5
5.1.5 | Tests at ESS | ESS |  | 2019-05-22 | 2019-05-28 | 7 | 0% | 5
5.1.6 | RFI - all boards | / |  | 2019-05-29 | 2019-05-29 | 1 | 0% | 1
5.1.7 | Installation for MEBT det | ESS BI (WUT) |  | 2019-07-22 | 2019-08-18 | 28 | 0% | 20
5.1.8 | Installation for DTL1 det. | ESS BI (WUT) |  | 2019-07-22 | 2019-08-18 | 28 | 0% | 20
5.2 | Crates
5.2.1 | Procurement - availablity unknown (no answer from ICS) | ESS ICS
5.2.2 | Installation for MEBT det - time window | ESS BI (WUT) |  | 2019-07-22 | 2019-08-18 | 28 | 0% | 20
5.2.3 | Installation for DTL1 det. - time winodw | ESS BI (WUT) |  | 2019-07-22 | 2019-08-18 | 28 | 0% | 20
5.3 | Short signal cables, connect. & PPs - rack side
5.3.1 | pin layout | CEA Dedip |  | 2019-02-13 | 2019-02-26 | 14 | 0% | 10
5.3.2 | production/procurremnt | ESS BI (WUT) |  | 2019-02-27 | 2019-05-21 | 84 | 0% | 60
5.3.3 | Installation for MEBT det - time window | ESS BI (WUT) |  | 2019-07-22 | 2019-08-18 | 28 | 0% | 20
5.3.4 | Installation for DTL1 det. - time winodw | ESS BI (WUT) |  | 2019-07-22 | 2019-08-18 | 28 | 0% | 20
5.4 | Short signal cables, connect. & cable supports - detector side
5.4.1 | pin layout and change/confirmation of choice | CEA Dedip |  | 2019-02-13 | 2019-02-26 | 14 | 0% | 10
5.4.2 | procurment process preparation | CEA Dedip |  | 2019-02-27 | 2019-03-12 | 14 | 0% | 10
5.4.3 | procurement/production | CEA Dedip |  | 2019-03-13 | 2019-06-04 | 84 | 0% | 60
5.4.4 | Delivery to ESS | CEA Dedip |  | 2019-06-05 | 2019-06-11 | 7 | 0% | 5
5.4.5 | RFI | / |  | 2019-06-12 | 2019-06-12 | 1 | 0% | 1
5.4.6 | Installation for MEBT det - time window | ESS BI |  | 2019-07-27 | 2019-08-02 | 7 | 0% | 5
5.4.7 | Installation for DTL1 det. - time winodw | ESS BI |  | 2019-09-07 | 2019-09-13 | 7 | 0% | 5
5.5 | Long cables, connectors
5.5.1 | procurement - ongoing | ESS Infrastructure
5.5.2 | ready for connection in MEBT - time window | ESS Infrastructure |  | 2019-08-19 | 2019-09-09 | 21 | 0% | 16
5.5.3 | ready for connection in DTL1 - time window, dates unclear, this what is in P6 now, though pulling cables is the current focus, so changes likely | ESS Infrastructure |  | 2019-09-30 | 2019-10-14 | 14 | 0% | 11
5.6 | CAEN HV and LV PS system - rest
5.6.1 | procur. process preparation | CEA Dedip |  | 2019-02-13 | 2019-02-26 | 14 | 0% | 10
5.6.2 | Procurement | CEA Dedip |  | 2019-02-27 | 2019-05-21 | 84 | 0% | 60
5.6.3 | Test | CEA Dedip |  | 2019-05-22 | 2019-05-28 | 7 | 0% | 5
5.6.4 | Delivery to ESS | CEA Dedip |  | 2019-05-29 | 2019-06-04 | 7 | 0% | 5
5.6.5 | Tests at ESS | ESS |  | 2019-06-05 | 2019-06-11 | 7 | 0% | 5
5.6.6 | RFI - all boards and crates | / |  | 2019-06-12 | 2019-06-12 | 1 | 0% | 1
5.6.7 | Installation: crate 1, time window | ESS BI (WUT) |  | 2019-07-22 | 2019-08-19 | 28 | 0% | 21
5.7 | Short LV cables, connectors, PPs - rack side
5.7.1 | pin layout | CEA Dedip |  | 2019-02-13 | 2019-02-26 | 14 | 0% | 10
5.7.2 | procurment process preparation | CEA Dedip |  | 2019-02-27 | 2019-03-12 | 14 | 0% | 10
5.7.3 | procurement/production | CEA Dedip |  | 2019-03-13 | 2019-06-04 | 84 | 0% | 60
5.7.4 | delivery to ESS | CEA Dedip |  | 2019-06-05 | 2019-06-11 | 7 | 0% | 5
5.7.5 | RFI | / |  | 2019-06-12 | 2019-06-12 | 1 | 0% | 1
5.7.6 | Installation for MEBT det - time window | ESS BI (WUT) |  | 2019-07-22 | 2019-08-18 | 28 | 0% | 20
5.7.7 | Installation for DTL1 det. - time winodw | ESS BI (WUT) |  | 2019-07-22 | 2019-08-18 | 28 | 0% | 20
5.8 | Short LV cables, connectors, PPs -detector side
5.8.1 | pin layout | CEA Dedip |  | 2019-02-13 | 2019-03-12 | 28 | 0% | 20
5.8.2 | procurement - ongoing | ESS Infrastructure
5.8.3 | ready for connection at MEBT (4 det) - dates unclear | ESS Infrastructure |  | 2019-08-19 | 2019-09-09 | 21 | 0% | 16
5.8.4 | ready for connection at DTL1 (8 det) - dates unclear, this what is in P6 now, but it's the focus these days | ESS Infrastructure |  | 2019-09-30 | 2019-10-14 | 14 | 0% | 11
5.9 | Short HV cable (HV PS module - adapter module) - rack side
5.9.1 | pin layout | CEA Dedip |  | 2019-02-13 | 2019-02-26 | 14 | 0% | 10
5.9.2 | procurment process preparation | CEA Dedip |  | 2019-02-27 | 2019-03-12 | 14 | 0% | 10
5.9.3 | procurement/production | CEA Dedip |  | 2019-03-13 | 2019-06-04 | 84 | 0% | 60
5.9.4 | delivery to ESS | CEA Dedip |  | 2019-06-05 | 2019-06-11 | 7 | 0% | 5
5.9.5 | RFI | / |  | 2019-06-12 | 2019-06-12 | 0 | 0% | 1
5.9.6 | Installation for MEBT det - time window | ESS BI (WUT) |  | 2019-07-27 | 2019-08-02 | 7 | 0% | 5
5.9.7 | Installation for DTL1 det. - time winodw | ESS BI (WUT) |  | 2019-09-07 | 2019-09-13 | 7 | 0% | 5
6 | Gas system
6.1 | Long pipes
6.1.1 | Specifications | CEA Dedip |  | 2017-07-12 | 2018-05-07 | 300 | 100% | 214
6.1.2 | 3D model integration | ESS BI |  | 2017-12-06 | 2019-02-11 | 432 | 99% | 309
6.1.3 | Procurement - end date unclear | ESS Infrastructure
6.1.4 | Installation phase 1 - 200m, dates unclear | ESS Infrastructure
6.2 | Short pipes, connectors (detector sdide)
6.2.1 | Specifications | CEA Dedip |  | 2017-07-12 | 2019-02-11 | 579 | 99% | 414
6.2.2 | Procurement proc. Preparation | CEA Dedip |  | 2019-02-12 | 2019-02-25 | 14 | 0% | 10
6.2.3 | Procurement | CEA Dedip |  | 2019-02-26 | 2019-03-25 | 28 | 0% | 20
6.2.4 | delivery to ESS | CEA Dedip |  | 2019-03-26 | 2019-04-08 | 14 | 0% | 10
6.2.5 | RFI | ESS BI |  | 2019-04-09 | 2019-04-09 | 1 | 0% | 1
6.2.6 | installation at MEBT (4 det) | ESS BI |  | 2019-07-27 | 2019-08-02 | 7 | 0% | 5
6.2.7 | installation at DTL1 (8 det) | ESS BI |  | 2019-09-07 | 2019-09-13 | 7 | 0% | 5
6.3 | Control system
6.4 | PLC - delivered | CEA |  | 2018-01-09 | 2018-01-09 | 0 | 100% | 1
6.5 | Crates, valves etc | CEA
6.5.1 | Procurement proc. preparation | CEA |  | 2019-02-13 | 2019-02-26 | 14 | 0% | 10
6.5.2 | Procurement | CEA |  | 2019-02-27 | 2019-05-21 | 84 | 0% | 60
6.5.3 | tests? | CEA |  | 2019-05-22 | 2019-05-28 | 7 | 0% | 5
6.5.4 | Delivery to ESS | CEA |  | 2019-05-29 | 2019-06-04 | 7 | 0% | 5
6.5.5 | RFI | / |  | 2019-06-05 | 2019-06-05 | 1 | 0% | 1
6.5.6 | installation in rack (FEB) - prefered to be in place before long gas pipes installation | CEA or/and ESS-BI? |  | 2019-06-12 | 2019-06-18 | 7 | 0% | 5
7 | Detector mechanical support
7.1 | for MEBT detectors
7.1.1 | finalising design | CEA Dedip |  | 2019-02-13 | 2019-03-19 | 35 | 0% | 25
7.1.2 | Integration | ESS BI |  | 2019-02-13 | 2019-03-19 | 35 | 0% | 25
7.1.3 | Procurement proc. Preparation | CEA Dedip |  | 2019-03-20 | 2019-04-02 | 14 | 0% | 10
7.1.4 | Procurement | CEA Dedip |  | 2019-04-03 | 2019-06-25 | 84 | 0% | 60
7.1.5 | Delivery to ESS | CEA Dedip |  | 2019-06-26 | 2019-07-02 | 7 | 0% | 5
7.1.6 | installation at MEBT (4 det) - dates to be coordinated with Infrastructure, here assuming installation at the same time as detectors | ESS BI/Infrastructure |  | 2019-07-27 | 2019-08-02 | 7 | 0% | 5
7.2 | for DTL1 detectors
7.2.1 | Design & integration done | CEA Dedip/ESS BI |  | 2017-12-06 | 2018-08-12 | 250 | 100% | 178
7.2.2 | Procurement proc. Preparation | CEA Dedip |  | 2019-02-13 | 2019-02-26 | 14 | 0% | 10
7.2.3 | Procurement | CEA Dedip |  | 2019-02-27 | 2019-05-21 | 84 | 0% | 60
7.2.4 | Delivery to ESS | CEA Dedip |  | 2019-05-22 | 2019-05-28 | 7 | 0% | 5
7.2.5 | installation at DTL (8 det) - dates to be coordinated with infrastructue, here assuming installation at the same time as detectors | ESS BI/Infrastructure |  | 2019-09-07 | 2019-09-13 | 7 | 0% | 5
8 | System tests
8.1 | Vertical integration tests - time windows
8.1.1 | in the lab (FW, SW, HV, LV, gas?) | ESS BI/ICS/CEA/LTU |  | 2019-06-01 | 2019-08-23 | 84 | 0% | 60
8.1.2 | tests with installed MEBT detector (FW, SW, HV, LV, gas) and connecting long and short cables on detector side | ESS BI/ICS/CEA/LTU |  | 2019-09-10 | 2019-10-01 | 21 | 0% | 16
TEMPLATE ROWS
See the Help worksheet to learn how to use these template rows. You can hide these rows before printing.
1 | [ Level 1 Task, Category, or Phase ]
1.1 | . [ Level 2 Task ] |  |  |  | - |  | 0% | 0
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  | 0% | 0
1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  | 0% | 0
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.