## Slide 1: Instruments Shielding Project Installation
Antonio Bianchi
NSS Installation Coordinator
NSS Project Division
www.europeanspallationsource.se
24th January 2019

## Slide 2: General view
Skanska handover - end of June 2020 (green area)
Neutron Shielding installation starts: June 2020 (E02.1)
D03 access Q1 2021
D01 access Q2 2021
E02.2 access Q2 2021

## Slide 3: External storage area (E buildings)
NSS storage area from Q4 2019
1000 m2 (on-going discussion with Skanska)
(The area might be useful for temporary storage of shielding blocks)
E01
E02

## Slide 4
E02
E02 gate
3.6 x 3.8 m
Site route (E02 access)
Unloading zone
Site road under construction and suitable vehicles
Final road - 8% steep up to the E02 gate

## Slide 5: Logistic and storage area into E01 and E02.1
Reference time
September 2019 – April 2021
Guide Shielding length 44.000 mm
Storage areas will be allocated to minimize dependencies between different installation teams
Note: beamline piles can reduce the available area
Any of the represented areas will require a physical delimitation
E02 gate
Entrance for shielding blocks (during construction)

## Slide 6: E01- E02 logistic details
2.7 m
Free corridor 5 m
E02.2
BIFROST
44 m
E02.1
Pedestrian way
6 m
E01 - Heimdal side
E01
NMX side
Temp separ.
wall
C SPEC
E02.1/E02.2
Ladder
Office
5 m
E01
Heimdal side
Magic
Building pillars

## Slide 7: Logistic alternatives to manage heavy components
Temporary steel structure to reduce the ramp-slope up to 16.5 % (3 m extension), to be suitable with electric forklift
A) Ramp slope reduction by ramp’s extension
B) E02 slab extension
Temporary steel platform in order to extend the E02 slab under the E01 crane hook-print
A
B

## Slide 8: Transport and lift neutron shielding in the hall (E01/E02)
Mitsubishi FD 80N | 
Load capacity | 8 tonne
Overall width | 2.390 mm
Gradeability | 31%
Power source | Diesel
Steel gantry crane (E02 building) | 
Load capacity | 10 tonne
Overall width | 6.300 mm
Overall high | 6.500 mm
Linde E80 | 
Load capacity | 8 tonne
Overall width | 2.180 mm
Gradeability | 16%
Power source | Battery

## Slide 9: ESS Installation Support functions
Ladders/Temporary steel structure
Laydown Areas
Crane drivers
Logistics/Transport
Heavy lifting
Concrete drilling
ESS RESPONSIBLE
CONTACT PERSON
MANDATORY/OPTIONAL
FREE/COST
PROVIDER NAME
NSS PROJECT ORGANIZATION
(NSS INSTALLATION COORDINATOR)
Survey/Alignment
General support (washing/cleaning)
PPE and general consumables
Safety fencing
Workers cabin
Waste management
Construction site

## Slide 10: Shielding installation-sequence in E02.1 (and ESS/In Kind resources)
E02 - Step 1
E02- Step 2
Forklift
Gantry crane
Concrete shielding block (roof)
3,00 x 1,00 x 0,30 m
(2.5 tons)
Shielding wall
Installation in the beamline gallery requires specific caution, due to there are not permanent cranes available
Ramps between E01 and E02
22 %
4 (ESS)
2 (In-Kind)
3 (In-Kind)
1(ESS)

## Slide 11: E02.2 building crane (5 tonne capacity)
D03
E02.2
D03/E02 separation wall
3D View n. 1
View n. 1
Crane hook-print 5 tonne
D03/E02 separation wall
Crane hook-print
Delivered from CF in the E02.2 hall (May 2021)

## Slide 12: Installation – resource estimation (labour)
 | Installation of neutron shielding resource estimation (labour) |  | C Spec, Bifrost, Magic, Heimdal |  | Dream, Vespa |  | Odin | 
 |  | N. | Work Hours | Total W.H. | Work Hours | Total W.H. | Work Hours | Total W.H.
 | Description |  | h | h | h | h | h | h
a | Skilled Technical personnel (Mech. Tech.) | 2 | 360 | 720 | 320 | 640 | 240 | 480
b | Crane Operator, incl. tempor. cranes | 1 | 360 | 360 | 320 | 320 | 240 | 240
c | Rigger | 1 | 360 | 360 | 320 | 320 | 240 | 240
d | Surveyor | 2 | 64 | 128 | 48 | 96 | 32 | 64
e | Handling/Forklift Operator | 1 | 360 | 360 | 320 | 320 | 240 | 240
f | Support Technical staff | 1 | 64 | 64 | 48 | 48 | 32 | 32
 |  |  |  | 1992 |  | 1744 |  | 1296
 | FTE (per instrument) |  |  | 1.11 |  | 0.97 |  | 0.72
 | Total amount (labour) |  |  | 4.43 |  | 1.94 |  | 0.72
 | Assumptions |  |  |  |  |  |  | 
1 | Beamline shielding 15m /week (9 weeks in total) - C Spec, Bifrost, Magic, Heimdal |  |  |  |  |  |  | 
2 | Beamline shielding 15m /week (4 weeks in total) - Dream, Vespa |  |  |  |  |  |  | 
3 | Beamline shielding 15m /week (2 weeks in total) - Odin |  |  |  |  |  |  | 
4 | Surveying - 2 technicians plus tracker marking limit of shielding and cave footprint - marking before drilling - 64 hours in total west sector |  |  |  |  |  |  | 
5 | Experimental cave not included |  |  |  |  |  |  | 
6 | Management/supervisor |  |  |  |  |  |  | 

## Slide 13: Questions