## Slide 1: ESS Project Status
Roland Garoby
ESS Technical Director
11 February 2019

## Slide 2: ESS basic design principle
Ion Source
High Power Accelerator:
Ultimate energy: 2 GeV
Rep. Rate: 14 Hz
Current: 62.5 mA
15 Instruments in Construction budget
>30 times higher performance than at ILL
Target Station:
- He-gas cooled rotating W-target (5MW ultimate beam power)
- 42 beam ports

## Slide 3: Some numbers
1843 M€ construction cost
5 MW world’s most powerful particle accelerator
15 experimental stations
20 ⨉ more sensitive on average than today’s best
800 experiments per year
2023 first science for users
15 European member and observer nations

## Slide 4: ESS in-kind partners make ESS possible
Aarhus University
Atomki - Institute for Nuclear Research
Agder University
Bergen University
CEA Saclay, Paris
Centre for Energy Research, Budapest
Centre for Nuclear Research, Poland, (NCBJ)
CERN, Geneva
CNR, Rome
CNRS Orsay, Paris
Cockcroft Institute, Daresbury
DESY, Hamburg
Delft University of Technology
Edinburgh University
Elettra – Sincrotrone Trieste
ESS Bilbao
Forschungszentrum Jülich
Helmholtz-Zentrum Geesthacht
Huddersfield Univesrity
IFJ PAN, Krakow
INFN, Catania
INFN, Legnaro
INFN, Milan
Institute for Energy Research (IFE)
Institut Laue-Langevin (ILL)
Rutherford-Appleton Laboratory, Oxford (ISIS)
Kopenhagen University
Laboratoire Léon Brilouin (LLB)
Lodz University of Technology
Lund University
Nuclear Physics Institute of the ASCR
Oslo University
Paul Sherrer Institute
Roskilde University
Tallinn Technical Univesrsity
Technical University of Chemnitz
Technical University of Denmark
Technical University Munich
Science and Technology Facilities Council
(STFC)
University of Tartu
Uppsala University
WIGNER Research Centre for Physics
Wroclaw Univesrity of technology
Warsaw University of Technology
Zurich University of Applied Sciences
(ZHAW)
Chart: 
| End of 2014 | End of 2015 | End of 2016 | End of 2017 | End of 2018 | End of 2019
Agreed / Endorsed | 0.19 | 128.5 | 254.7 | 319 | 334.1 | 520
Planned | 272.59 | 207.15 | 258.49 | 215.34 | 215 | 28
Potential | 335.78 | 313.19 | 110.54 | 25 | 10 | 5
Collaborations | 9.4 | 16.7 | 17.09 | 22 | 19.8 | 25
Direct Contracts | 0 | 5.7 | 15.7 | 20 | 21.36 | 22

## Slide 5: Organisation and People
471
Employees
48
Citizenships
~ 100
Collaborating Institutions
Notes: Updated September 2017

## Slide 6: Baseline schedule has been revised in 2018
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float
Accel RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker and Test Beam Line RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
Instrument Hall Access for Start of Installation
Hi-Beta Install
1.3 GeV Capability Installed
BOT - Beam on Target
ES - Early Science
SOUP - Start of User Programme
EOC - End of Construction project
RXXX - Ready for XXX
ES
Start of Neutron Source

## Slide 7: Transition to Operations for Early Science is outlined
Updated description of “Early Operations of the ESS Neutron Instruments and first scientific results” (ESS-0420218) distinguishing successive stages.
(NSS requirement: 2.86 ms beam pulses on a 14 Hz time grid)
Up to Beam on Target (-July 2022)
  570 MeV Beam on Dump after “Accelerator Ready for Beam On Target” (mid-2021)
  Beam commissioning at increasing energy interlaced with installation of High Beta cryomodules
ESS initial stages (July 2022-December 2023)
  Early Days: BOT to (BOT + 3 months) (July – September 2022). Req.: 1x8 h /week with > 100 kW
  Consolidation Days: The next 3 months: (BOT + 3 months) to (BOT + 6 months) (October – December 2022). Req.: 6x8 h/week with >100 kW.
  Performance Assessment days: (BOT + 6 months) to (BOT + 9 months) (January – March 2023). Req.: 12x8 h/week with >100 kW.
  First Performance Demonstration Days: (BOT + 9 months) to (BOT + 12 months) (April – June 2023). Req.: 33x8 h/2 weeks with >300 kW.
  Ramp up and Early Science: (BOT + 12 months) to (BOT + 18 months) (July – December 2023). Req.: 33x8 h/2 weeks with up to 500 kW.
Start of the ESS User programme SOUP (2024-2027)
500 kW beam power with 80 % availability.

## Slide 8: ESS Project 57% complete
Project execution is on track with new schedule
  Based on “Early Finish” dates
  Beam on Target (BOT) in mid-2022, Start of User Programme (SOUP) at end of 2023
Ramping down building design work, ramping up installation
Ion source/LEBT and helium cryo-plants are being brought on-line
Safety readiness review SRR1 completed - permission to start trial operation of ion source granted
Staff moved to ESS site, work started on permanent laboratory and office complex
Collaboration Agreement finally signed with Germany
Full 2019 budget request approved by Council

## Slide 9: Ion source & LEBT are being commissioned
First beam: 19 Sept. 2018

## Slide 10: The temporary control room is operational
For commissioning the ion source…
…and the cryoplants.

## Slide 11: Infrastructure installation is in progress
Filling of liquid helium into mobile Dewars
Cryogenics plants installed and partly operational:
All large components of all cryoplants are on site.
Successful acceptance tests of liquefaction, refrigeration, internal purifier and Process Vacuum Pumps System. Final acceptance of plant completed.
All 19 PHS tanks ready and filled with helium
TMCP cold box
delivered
High power RF available in Test stand 2 (elliptical cavities cryomodule):
Modulator and klystron running
Bunker built
Licensing in preparation for cryomodule test
Accelerator Infrastructure project in progress:
10 496 meters of pipes, ~6000 welds, ~5000 valves
3000 m cable trays, > 700 km cables, 24 902 cables
6 central UPS-units
~800 control racks and 100-120 cooling units.

## Slide 12: Work progresses actively at in-kind partners (1/2)
  Development phase : Medium-b Cryomodules demonstrator tested, nominal gradient obtained in cavities (CEA-Saclay)
  Medium Beta cavities production (INFN- LASA)
    3 cavities welded
    2 cavities bulk BCP surface treatment done and annealing
Cryomodules and elliptical cavities
RF voltage in
cavities 1-4
(Open loop &
Trapezoid pulse
on piezo tuner)
- High Beta cavities production (STFC – Daresbury)
  Niobium Material - Contract awarded in Oct17
  Final Nb batch delivery expected in Dec18
  Cavity Manufacture - Contract awarded in Jul18
Performance of
reprocessed cavities
after coupler accident
in 2017
Mail from P. Michelato (INFN) on 21/12/2018:
“…The first INFN-LASA medium beta cavity… reached
23.7 MV/m with a Q0 of 7.9e9. At the ESS field of 16.7 MV/m,
the Q0 is 1.7e10, well over the ESS requirements of 5e9.
The frequency at cold is 704.221 MHz with a Qt of 3.6e11…”

## Slide 13: Work progresses actively at in-kind partners (2/2)
Cryomodules and spoke cavities
Prototype cryomodule delivered
at FREIA (Uppsala)
Start of test in February 2019
3 series spoke cavities have been tested and exceed requirements
Assembly of the 1st series cryomodule will begin mid –March
Delivery at FREIA mid-May

## Slide 14: Test infrastructure is operational at partners’ premises
Several Spoke prototypes tested in HNOSS
Successful validation test of high beta cavity assembly
Spoke prototype cryomodule received and being connected.
(e.g. FREIA in Uppsala)
Romea in HNOSS
cryogenics
- liquid helium
- liquid nitrogen
control room
- equipment controls
- data acquisition
radio-frequency (RF) power sources
3 bunkers
with test stands
horizontal cryostat
vertical cryostat
State-of-the-art Equipment
HB package at FREIA

## Slide 15: ESS Target and Target building
Target Building
(41% complete)
130 m
22 m
37 m
High bay
Transport hall
Beam expander hall
Target monolith
Utilities block
Active cells
Target Building
Utilities and cooling plant
Remote handling systems
proton beam
proton beam window
proton beam instrumentation plug
Moderator and reflector
target wheel
neutron beam extraction port
monolith vessel
target monitoring plug
Target Monolith
Rotating solid tungsten target (11 t, 23.3 rpm)
Moderators (LH2 – 17 K and H2O – 300 K)
Helium gas cooling of target (11 bar, 3 Kg/s)
Target Safety System
Diagnostics and instrumentation

## Slide 16: Work progresses actively at in-kind partners (1/2)
Target and its monolith vessel
Problem solved on 3rd prototype last week
1st prototype of target wheel suffered from deformation after welding
Contract for manufacturing of Target Monolith vessel awarded in June 2018

## Slide 17: Work progresses actively at in-kind partners (2/2)
Moderators and reflectors
Cold moderators are built and tested (FAT).
Beryllium reflector built and tested (Acceptance test in Moscow)
Thermal moderators are being manufactured.

## Slide 18: High bay slab will soon be cast

## Slide 19: Construction of Active Cells is advancing
Aerial view of Active Cells
Storage pits in Active Cells

## Slide 20: Construction of experimental hall E01 is well advanced

## Slide 21: Moved to site in summer 2018 - Moving to permanent office and lab buildings in 2021
Lund Tramway Depot
Permanent
Office Campus
2021
New 2018 ESS offices for all staff
Bus 20
PermanentEntrance

## Slide 22: Office and Laboratory Campus
Ground breaking for the ESS Offices and Laboratories
December 2018
Campus will consist of 3 buildings, 450 workspaces, 16 labs and workshops

## Slide 23: Campus
Labs and Workshops
Offices, auditorium canteen
Entrance Building
Plan to move in early 2021

## Slide 24: Key activities in 2019
Install and start commissioning next stage of the linac
Target Building access granted for start of technical (Target) equipment installation
Start instrument installation in long beamline Experimental Hall
Begin construction of Campus and Lab Buildings

## Slide 25: Thank you!