## Slide 1: Central Process System, CPS

## Slide 2: CPS Energy Balance 2025 and ahead
CPS
Recycling
> 95 %
CWL 35 GWh
CWM 35 GWh
CWH 60 GWh
Electricity 34 GWh
DHL 17 GWh
DH to Kraftringen
175 GWh
HVAC to air 6 GWh

## Slide 3: CPS Ramp Up
Flexible
DHL from October -19

## Slide 4: Timeplan 2019 – Stage 1
Mars
Maj
Meeting ESS
Piping PD design
Projekt meeting
Jan
Feb
April
Juni
Aug
Juli
Sep
Okt
Nov
Dec
Construction meeting
Piping Procurement
Installation
Electric design
Installations
Power up
Cirkulation
IAR ??
IAR Procurement
Installations
DIW ??
DIW Procurement
Electric Procurement
HVAC Design
HVAC Procurement
Installations
Installations
PD Review
Piping DD design
Construction meeting

## Slide 5: Timeplan 2020/2022 – Stage 2
Q1 2021
Q3 2021
Design update
Q3 2020
Q4 2020
Q2 2021
Q4 2021
Q2 2022
Q1 2022
Q3 2022
Piping Procure
Installation
Electric DD
Installation
CPS in operation
Heatpump Procure
Control System
Electric Procure
Commissioning
PD Review update
Piping DD
DD Review update
Heatpump Installation

## Slide 6: Timeplan 2023/2025 – Stage 3
Q1 2024
Q3 2024
Design update
Q3 2023
Q4 2023
Q2 2024
Q4 2024
Q1 2025
Piping Procure
Installation
Electric DD
Installation
CPS in updated operation
Heatpump
Procure
Control System update
Electric
Procure
Commissioning
PD Review update
Piping DD
DD Review update
Heatpump
Installation

## Slide 7: 3D modulation