## Slide 1: ICS work package 11 – Target Update Integrated Control Systems
Michael Beck
Work package manager
ESS/ICS
Date: 2019-04-11

## Slide 2: Background
Work Package 11’s scope is a part of the overall ICS strategy to design and integrate control systems into EPICS, in this case Target Station’s Basic Process Control (BPCS), using standard hardware, software and processes.
Notes: System Engineering Management Plan, Control System Requirements, Interface Control Document, System Design Document, System Integration Plan, Verification Plan through
PDR, CDR, TRR and SAR

## Slide 3: Target Wheel and Monitoring System
Scope of Work
Motion control of the Target Wheel (TW-PLC)
  Vibrations, Synchronization and Lubrication
  Timing Application
Target Monitoring System (TMS-PLC)
  IR Camera, Gamma Imaging of Bricks, He Acoustic Measurement
  X/Y Laser Measurement
  Z calculation
  Timing System Application
Stakeholders
Bilbao
AVS
Julich
Target Division
Motion Control Group
Status
Motion Control Testing on Rig in RATS
Control System PDR in the Summer
2018
2021
Today
2018
2019
2020
2021
PDR
2019-08
CDR
2019-12
TRR
2020-05
SAR
2021-12
2018-01 - 2019-09
Design
Notes: TMS Julich CDR – 2019-05
TW AVS Drive FAT – 2019-09
TW Bilbo FAT – Q120
TS Julich FAT – 2020-02

## Slide 4: Water Cooling Control System
Scope of Work
Primary Water Cooling Systems (MR/SP/THCS-PLC)
Intermediate Cooling Systems (MR/SP-PLC)
Drain Tanks (DR-PLC)
Water Purification System (MR/SP-PLC)
Neutron Beam Instrument Plugs Cooling
  (DR-PLC)
Proton Beam Window Cooling (MR-PLC)
Stakeholder
Target Division
Status
Preliminary Design Review held in 2019-03, follow up
Require further Functional Specification
OPI development continuing
2018
2021
Today
2018
2019
2020
2021
PDR
2019-03
CDR
2019-12
TRR
2020-07
SAR
2021-12
2018-01 - 2019-12
Design

## Slide 5: Helium Cooling Control System
Scope of Work
Purification (THCS-PLC)
Target Cooling (THCS-PLC)
Pressure Control (THCS-PLC)
Injection System (THCS-PLC)
Stakeholders
OFTTech
Target Division
Status
PDR Held in 2019-01
CDR has been delayed till the fall
  Purification and Circulator Details
Testing Tool development
2018
2021
Today
2018
2019
2020
2021
PDR
2019-01
CDR
2019-09
TRR
2020-07
SAR
2021-12
2018-01 - 2019-09
Design

## Slide 6: Cryogenic Moderator Control System
Scope of Work
Cryogenic Mod (CMS-PLC)
Associated Vacuum Pumps (CMS-PLC)
Filling Station (CMS-PLC)
Cold Box (CMS-PLC)
Stakeholders
Julich
Target Division
Elteba
Status
Control cabinet being built at Elteba
Cabinet FAT in 2019-06
Initial controls testing to start at Julich in 2019-08
Manual control of devices implemented in PLC/OPIs
2017
2021
Today
2017
2018
2019
2020
2021
PDR
2018-03
CDR
2019-10
TRR
2021-03
SAR
2021-12
2017-01 - 2019-09
Design

## Slide 7: HVAC
Scope of Work
Monitoring of Turn-key Solution (HVAC-PLC1/2)
Critical Alarms, Archiving, OPI
Stakeholder
Target Division
Status
Functional specifications starting to develop
PDR held in early 2018
2017
2021
Today
2017
2018
2019
2020
2021
PDR
2018-02
CDR
2020-03
TRR
2020-12
SAR
2021-12
2017-09 - 2020-03
Design

## Slide 8: Vacuum System
Scope of Work
Monolith Rough Vacuum System (VAC-PLC)
Proton Beam Window (VAC-PLC)
Stakeholders
Target Division
Vacuum Group
ICS work package 10
Status
Target’s Vacuum CDR scheduled in next couple months
Control Development to be coordinated with Accelerator work, current plan may change
2019
2021
Today
Jan
Apr
Jul
Oct
2020
Apr
Jul
Oct
2021
Apr
Jul
Oct
PDR
2019-09
CDR
2020-04
TRR
2021-03
SAR
2021-12
2019-01 - 2020-04
Design

## Slide 9: Special Modules: Monitoring Systems
Scope of Work
Active Cell Monitoring System (IOC on TN)
TSS Monitoring System (IOC on TN)
Tuning Beam Dump (TBD-PLC)
Light Shutter System (LSS-PLC1/2)
Utilities (UTL-PLC)
Radiolysis (SP-PLC)
NBOA (DR-PLC)
Stakeholder
Target Division
Status
Currently Radiolysis, NBOA is in water cooling control system
Requirements are still coming in
2019
2022
Jun
Oct
Feb
Jun
Oct
Feb
Jun
Oct
PDR
2019-12
CDR
2020-05
TRR
2020-12
SAR
2021-12
2019-06 - 2020-06
Design

## Slide 10: Global Target Integration
Scope of Work
Target PLC Network
Control Logic for Target Station (TS-PLC)
Global OPIs for Target Station
Target MPS/PSS integration into EPICS
Stakeholders
All Target System Owners
Target Operations and Maintenance Group
ESH
Status
Function Requirements still coming in
2019
2022
Today
Mar
Aug
2020
Jun
Nov
Apr
Sep
PDR
2019-12
CDR
2020-06
TRR
2020-12
SAR
2021-12
2019-03 - 2020-06
Design

## Slide 11: Target Station: Network/BPCS Architecture (Part 1)
D02.125.3024
Highbay
Utility
Triangular room
Utility
D02.085.3064
D02.103.3064
D02.115.3067
D02.091.4003
D02.103.3067
D02.085.3067
D02.115.3064
D02.115.4005
D02.125.3024
D02.103.4003
D02.115.400
Target PLC Network
Technical Network
TWCS
MR-PLC
TWCS:
NBIP/NBOA/DR-PLC
TWCS
SP-PLC
VAC-PLC
THCS-PLC
TS/UTL-PLC
LSS-PLC 1
LSS-PLC 2
Target Wheel
+
Proton Beam
Notes: TMS Julich CDR – 2019-05
TW AVS Drive FAT – 2019-09
TW Bilbao FAT – Q120
TS Julich FAT – 2020-02

## Slide 12: Target Station: Network/BPCS Architecture (Part 2)
D02.125.3024
Highbay
Triangular room
A2T
D02.115.3064
D02.115.4005
D02.125.4014
D02.150.4015
D02.125.3024
Outside
accelerator
D02.100.4015
Target PLC Network
Technical Network
TWCS
MR-PLC
TW-PLC
TMS-PLC
TIME-SYS
TBD-PLC
CMS-PLC
HVAC-PLC1
HVAC-PLC2
D02.085.3064
D02.103.3064
+
Proton Beam

## Slide 13: Questions?
Thank you for your attention
  Contact: Michael.Beck@esss.se