## Slide 1: Accelerator/ICS collaboration and priorities
Henrik Carling / Mats Lindroos
Date: 2019-04-11

## Slide 2: Introduction
Accelerator is the largest stakeholder of ICS during the ESS construction phase
  Control system infrastructure
  Personnel safety system
  Machine protection system
  Accelerator system integration into the ICS

## Slide 3: Background Integrated Control Systems
Accelerator division constructs the ESS accelerator
ICS division is responsible for the construction of the integrated control system
  Both projects are in-kinded in their nature implying a distributed project/activity model
Some activities of the ICS division can work relatively independent of stakeholders, while most of ICS will engage heavily with stakeholders to design and integrate systems
Most significantly, this applies to the protection systems group and hardware and integration group, who will almost exclusively work in close collaboration with stakeholders
The protection systems group can in total distribute about 12 engineers and 4 technicians to work together with stakeholders
  Protection system members attend the accelerator integration meetings and provide pro-active feedback
  Protection system work packages arranges meetings with stakeholder for planning and coordination
The hardware and integration group can in total distribute about 25 engineers and 5 technicians to work together with stakeholders
  The main stakeholders are Accelerator, Target, NSS and CF - each has an ICS integration work package in the ICS construction project
  In order for ICS resources to be able to cover stakeholder needs, a systematic allocation of resources needs to be implemented
  The hardware and integration group will implement a variant of a classical line/project matrix model in order resolve prioritization and support project planning

## Slide 4: Line/project matrix - motivation (1)
Since about one year a systematic resource allocation for ICS hardware and integration resources have been applied to stakeholder activities
The process of managing the prioritization/allocation has evolved to
  Coordinate ICS and stakeholder project planning
  Ensure correct prioritization of ICS activities
  Develop (non-technical) interfaces between ICS and stakeholders
  Strengthen administrative control of ICS budget compliance
  Optimize ICS resource competence development
There is little support in ESS processes for dealing systematically with the problem of requesting, prioritizing and allocating resources to multiple activities

## Slide 5: Line/project matrix - motivation
The line/project matrix model solves the problem of running multiple project activities with limited resources, keeping a correct prioritization that supports stakeholders project planning
It also supports the continued development of experience and competence in the line organization
Target
WP5
Acc.
WP8
ESS
Bilbao
NSS WP5
Acc. WP7
Target WP7
...
...
...
Control system architect
Industrial automation
EPICS
Embedded systems
Data networks
Analog electronics
Control System Studio
FPGA
MicroTCA
Timing system
Process control
Vacuum controls
Control system integration
Controls technicians
Information/Controls security
Motion controls
...
0.5
1
0.5
2
1
0.5
2
2
2
1
1
0.5
0.5
0.5
0.5
1
1
0.5
0.5
1
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
1
1
1
1
0.5
1
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
1
1
Step 1: Collecting requests
Project manager interacts with stakeholders and together defines what needs to be done and when
Project manager and stakeholder defines a resource estimate with a time envelope
Project manager brings the plan back to the ICS allocation board

## Slide 6: Line/project matrix - motivation (2)
The line/project matrix model solves the problem of running multiple project activities with limited resources, keeping a correct prioritization that supports stakeholders project planning
It also supports the continued development of experience and competence in the line organization
Target
WP5
Acc.
WP8
ESS
Bilbao
NSS WP5
Acc. WP7
Target WP7
...
...
...
Control system architect
Industrial automation
EPICS
Embedded systems
Data networks
Analog electronics
Control System Studio
FPGA
MicroTCA
Timing system
Process control
Vacuum controls
Control system integration
Controls technicians
Information/Controls security
Motion controls
...
0.5
1
0.5
2
1
2
2
2
1
1
0.5
1
0.5
1
0.5
0.5
0.5
0.5
0.5
0.5
1
1
1
1
0.5
1
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
1
Step 2: Prioritizing requests
ICS allocation board prioritizes requests in discussion with stakeholders
Where conflicts occur, an escalation is made to ESS project management
The prioritization is roughly adjusted to fit the joint ICS resource + stakeholder capacity

## Slide 7: Line/project matrix - motivation (2)
The line/project matrix model solves the problem of running multiple project activities with limited resources, keeping a correct prioritization that supports stakeholders project planning
It also supports the continued development of experience and competence in the line organization
Target
WP5
Acc.
WP8
ESS
Bilbao
NSS WP5
Acc. WP7
Target WP7
...
...
...
Control system architect
Industrial automation
EPICS
Embedded systems
Data networks
Analog electronics
Control System Studio
FPGA
MicroTCA
Timing system
Process control
Vacuum controls
Control system integration
Controls technicians
Information/Controls security
Motion controls
...
0.5
0.5
0.5
2
0.5
1
1
1
1
1
1
1
0.5
1
0.5
0.5
0.5
1
0.5
0.5
1
0.5
0.5
1
0.5
1
0.5
1
0.5
1
0.5
0.5
0.5
0.5
1
Step 3: Allocation
ICS line management allocates resources to activities
ICS line management function considers factors such as competence and experience of the resources
ICS line management considers vacation, and other circumstances to guarantee the allocation within the period
ICS line management is responsible for regulating the line capacity if needed

## Slide 8: Line/project matrix - motivation (2)
The line/project matrix model solves the problem of running multiple project activities with limited resources, keeping a correct prioritization that supports stakeholders project planning
It also supports the continued development of experience and competence in the line organization
Target
WP5
Acc.
WP8
ESS
Bilbao
NSS WP5
Acc. WP7
Target WP7
...
...
...
Control system architect
Industrial automation
EPICS
Embedded systems
Data networks
Analog electronics
Control System Studio
FPGA
MicroTCA
Timing system
Process control
Vacuum controls
Control system integration
Controls technicians
Information/Controls security
Motion controls
...
0.5
1
0.5
2
1
0.5
2
2
2
1
1
0.5
0.5
0.5
0.5
1
1
0.5
0.5
1
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
1
1
1
1
0.5
1
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
0.5
1
Step 1: Collecting requests
The cycle restarts
0.5
0.5

## Slide 9: Line/project matrix - roles
ICS work package managers are ”project managers” in this model
  Responsible for interacting with stakeholders to establish what needs to be done and when
  Brings requests to the ICS allocation board
  Helps prioritizing requests
  Checks requested resources are within the work package budget
  Coordinates and drives allocated resources’ activities
  Reports to ICS management and stakeholders
ICS group leaders are ”line managers” in this model
  Receives the requests from project managers, decides who and how
  Helps prioritize and, if needed, escalate conflicts
  Manages resource availability, providing an optimal resource supply to project activities
  Manages staff development and alignment to the tasks
  Responsible for process compliance and deliverable quality

## Slide 10: Line/project matrix - interaction
ICS project managers arrange coordination meetings
  Meeting with stakeholders individually to collect requests and do estimates and planning
  Meeting with stakeholders collectively to coordinate and align internal prioritization
ICS line managers arrange allocation board meetings
  Meeting with project managers to prioritize requests and to escalate
  Long-term meetings with stakeholders to understand long-term needs
Frequency/format
  Project meetings are decided per work package, typically several meetings per week
  Allocation board meetings are monthly with a 6 month hóutlook to help project managers plan
Technical discussions are arranged through project managers

## Slide 11
Managing complex interaction

## Slide 12: Program management forum
Procurements
--------------
--------------
--------------
Tasks
--------------
--------------
--------------
Issues
--------------
--------------
--------------
The program management forum creates a set of tasks, procurements and issues that taken as a whole generates a meaningful result.
The forum occurs at the beginning of each program increment and contains representatives for all members (see below).
Vacuum group
Beam diagnostics
Radio frequency
Test stand 2
Cryo group
NCL group
SCL group
Protection system group
Hardware and integration group
Program increment. Time boxed 3 months.
Notes: KRISTINA

## Slide 13: Preparations for program management forum
Each participant shall prepare the following for the program management forum:
A list of prioritized tasks proposed for completion for the next increment
An overview of available resources for the next increment
Suggestion for common goals (1-3) for the next increment
A short presentation of the three items above
Notes: KRISTINA

## Slide 14: Preparations for program management forum
Principal agenda for the program management forum:
Each participant presents prioritized tasks and resources
Open discussion and questions about the presentations
Agreement on a commonly agreed list of goals (1-3) for the next increment.
Deduction of tasks, procurements and issues that needs to be addressed.
Statement on resources from each participant.
Iteration of step 5 and 6 until everyone can commit to the plan
The results from the program management forum published on Confluence and communicated internally by each participant.
Notes: KRISTINA

## Slide 15: ICS work packages
The table lists ICS work packages
Mainly, work packages 10, 11, 12, 13 will follow the principles outlined here
  Work package 10: Philippe Rabis
  Work package 11: Michael Beck
  Work package 12: John Sparger
  Work package 13: Michael Beck
  Line manager: Karl Vestin