## Slide 1: Target collaboration Board Meeting
2019.02.08 I M. Butzek
8th Meeting / February / Copenhagen

## Slide 2: OUTLINE
Brief technical status
  Moderator & Reflector Plug -TIK3.1 status
  Cryogenic Moderator System -TIK3.2 status
  Additional small ESS projects
  Target Monitoring Plug -TIK4.1
  Neutron beam extraction system
Contractual issues

## Slide 3: MRS TIK3.1
Beryllium Reflector
Beryllium Reflector manufacturing
Beryllium acceptance test (Moscow)
Welding Reflector Feb. 19 (ZEA-1)
FAT Feb. / Mar. 18
Pre machined Beryllium disc 1
Pre machined Beryllium disc 2 and 3
Beryllium acceptance (Moscow)
Yannick / FZJ
Reflector Vessel (FZJ)

## Slide 4: MRS TIK3.1
Cold Moderators
Cold Moderator manufacturing
FAT (cold Moderator)
Final cold Moderators
Cold Moderators with
thermal Moderator (intermediate stage)

## Slide 5: MRS TIK3.4
Irradiation Module (extra project
Cooperation with Uni Roma / R. Senesi)
Irradiation Module manufacturing
FAT
Inner holder with
96 samples…
Welded inner
holder
Final Irradiation Module
Assembly of Irradiation Module

## Slide 6: MRS TIK3.1
Thermal Moderator
Thermal Moderator manufacturing
Integration irradiation Module
Integration cold Moderator Feb. 19
FAT Feb./Mar. 19
Thermal moderator intermediate stage
thM with Irradiation Module
Thermal Moderator final milling

## Slide 7: MRS TIK3.1
Rotation Unit
Rotation Unit manufacturing
FAT
Final assembly of Rotation Unit at ZEA-1
Detail view of rotation mechanism

## Slide 8: MRS
Bucket (extra project) and Crown (TIK3.1)
Crown and bucket manufacturing
FAT
Milling of crown
3D dimension check of Crown
Final Crown and Bucket

## Slide 9: MRS TIK3.1
Twister
Twister shaft manufacturing
forge of the Twister shaft
Yannick and Marc
Shaft manufacturing
Frist welding March 19
Radial bearing manufacturing April 19
Axial bearing manufacturing April 19
Frame manufacturing Mai 19
Second welding June 19
FAT August 19
More Highlight TTB……
Pre cutted twister frame parts

## Slide 10: CMS TIK3.2
Cryostat
Vacuum chamber, platform and stand of CMS
O-p- converter
Pressure control buffer
Manufacturing cryostat 80%
Pressure vessel FAT
Welding June 19
FAT Aug. 19
HX2

## Slide 11: additional “small” projects
LH2 Pump cooling
 initial budget insufficient
CMS Cabinet
 delivery will be June 2019
Retro Reflector Project
 in preparation
RAMAN view port characterization
 Master thesis completed

## Slide 12: TMP TIK4.1
Final design phase
Source: ESS
Task of Target Monitoring Plug (TMP)
Measure the x/y position of the wheel
Measure the z position of the wheel
Measure the helium coolant outlet temperature from each cassette during operation
Measure shaft vibration during operation
Measure helium borne sound in the helium coolant for acoustic diagnostics of the target cooling system and for acoustic diagnostics
Measure the internal cooling system inlet and outlet temperature
name | duration | start | complete
target monitoring plug (TMP) | 528 d | Fr 01.06.18 | Di 09.06.20
final design phase | 177 d | Mi 12.09.18 | Do 16.05.19
Milestone CDR | 2 d | Di 30.04.19 | Mi 01.05.19
making phase | 185 d | Mo 20.05.19 | Fr 31.01.20
test phase | 91 d | Di 04.02.20 | Di 09.06.20
Milestone FAT | 1 d | Mi 29.04.20 | Mi 29.04.20
Milestone Delivery | 4 d | Do 04.06.20 | Di 09.06.20
Schedule

## Slide 13: NBEX WBS 12.4.2.4
Phase 1
Source: ESS
Source: ESS
Phase 1:
Manufacturing acc.
ESS drawings
  Test Stands
  Prototype (NBPI)
Phase 2:
Neutron Beam Port Insert
Neutron Beam Port Plug
Neutron Beam Window
Light Shutter System
42 inserts / plugs are needed

## Slide 14
Outer dimensions 3480 x 722 x 270 mm
Weight 4500 kg
NBEX - NBPI prototype
Scope of phase 1
Source: ESS
Lid
NBOA, Neutron Beam Optic Assembly (NSS responsibility)
NBPI body, including welded media channel lids (yellow)
Back window, Al 6061
Media connector
Shielding plates
Front window, Al 6061
NBOA alignment lids
Rollers
Alignment features
Redesigning by FZJ designer Feb. 19
NBPI Manufacturing +14 w
Beam window manufacturing March 19

## Slide 15
NBEX – Horizontal test stand
Scope of phase 1
Source: ESS
Drawings available since January 19 (ESS)
Horizontal test stand manufacturing August 19

## Slide 16: NBEX TIK Media connector test
Scope of phase 1
Source: ESS
Media connector manufacturing April 19

## Slide 17
NBEX – light Shutter Test stand
Scope of phase 1
Source: ESS
Source: ESS
Still no final drawings ESS
Manufacturing +16 w

## Slide 18: NBEX Lid handling tool
Scope of phase 1
Source: ESS
Still no final drawings ESS
Manufacturing +14 w

## Slide 19: Summery
TIK3.1 & TIK3.2 will be complete around late summer 2019
Small projects will be complete around summer 2019
TIK4.1 will be complete around early summer 2020
NBEX phase 1 will be complete around August? 2019
NBEX phase 2 will be complete around end of 2020???

## Slide 20: Contractual issues
Contribution Agreement for the Construction Phase between
      ESS ERIC
      and
      Forschungszentrum Jülich GmbH
is finally agreed and in the process of being signed. Final signature is expected within the next month.

## Slide 21: Contractual issues
  In order to officially contract work under this Contribution Agreement TAs for all work packages have to be written, agreed and signed.
  TAs for TIK3.1 & TIK3.2 exists and are agreed (as of Nov 2018) but still have to be signed by ESS.
  TA for NBEX has to be written, agreed and signed soon.
  TIK4.1 is performed under a bilateral contract, thus no TA is needed.