## Slide 1: ESS Project Status
Roland Garoby
ESS Technical Director
14 March 2019

## Slide 2: Organisation and People
471
Employees
48
Citizenships
~ 100
Collaborating Institutions
Notes: Updated September 2017

## Slide 3: Baseline schedule has been revised in 2018
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float
Accel RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker and Test Beam Line RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
Instrument Hall Access for Start of Installation
Hi-Beta Install
1.3 GeV Capability Installed
BOT - Beam on Target
ES - Early Science
SOUP - Start of User Programme
EOC - End of Construction project
RXXX - Ready for XXX
ES
Start of Neutron Source

## Slide 4: Transition to Operations for Early Science is outlined
Updated description of “Early Operations of the ESS Neutron Instruments and first scientific results” (ESS-0420218) distinguishing successive stages.
(NSS requirement: 2.86 ms beam pulses on a 14 Hz time grid)
Up to Beam on Target (-July 2022)
  570 MeV Beam on Dump after “Accelerator Ready for Beam On Target” (mid-2021)
  Beam commissioning at increasing energy interlaced with installation of High Beta cryomodules
ESS initial stages (July 2022-December 2023)
  Early Days: BOT to (BOT + 3 months) (July – September 2022). Req.: 1x8 h /week with > 100 kW
  Consolidation Days: The next 3 months: (BOT + 3 months) to (BOT + 6 months) (October – December 2022). Req.: 6x8 h/week with >100 kW.
  Performance Assessment days: (BOT + 6 months) to (BOT + 9 months) (January – March 2023). Req.: 12x8 h/week with >100 kW.
  First Performance Demonstration Days: (BOT + 9 months) to (BOT + 12 months) (April – June 2023). Req.: 33x8 h/2 weeks with >300 kW.
  Ramp up and Early Science: (BOT + 12 months) to (BOT + 18 months) (July – December 2023). Req.: 33x8 h/2 weeks with up to 500 kW.
Start of the ESS User programme SOUP (2024-2027)
500 kW beam power with 80 % availability.

## Slide 5: ESS Project 57% complete
Project execution is on track with new schedule
  Based on “Early Finish” dates
  Beam on Target (BOT) in mid-2022, Start of User Programme (SOUP) at end of 2023
Ramping down building design work, ramping up installation
Ion source/LEBT and helium cryo-plants are being brought on-line
Safety readiness review SRR1 completed - permission to start trial operation of ion source granted
Staff moved to ESS site, work started on permanent laboratory and office complex
Collaboration Agreement finally signed with Germany
Full 2019 budget request approved by Council

## Slide 6: Ion source & LEBT are being commissioned (Accelerator subproject is 54 % complete)
First beam: 19 Sept. 2018

## Slide 7: The temporary control room is operational (ICS subproject: 54 % complete)
For commissioning the ion source…
…and the cryoplants.

## Slide 8: Infrastructure installation is in progress
Filling of liquid helium into mobile Dewars
Cryogenics plants installed and partly operational:
All large components of all cryoplants are on site.
Successful acceptance tests of liquefaction, refrigeration, internal purifier and Process Vacuum Pumps System. Final acceptance of plant completed.
All 19 PHS tanks ready and filled with helium
TMCP cold box
delivered
High power RF available in Test stand 2 (elliptical cavities cryomodule):
Modulator and klystron running
Bunker built
Licensing in preparation for cryomodule test
Accelerator Infrastructure project in progress:
10 496 meters of pipes, ~6000 welds, ~5000 valves
3000 m cable trays, > 700 km cables, 24 902 cables
6 central UPS-units
~800 control racks and 100-120 cooling units.

## Slide 9: Work progresses actively at in-kind partners (1/2)
  Development phase : Medium-b Cryomodules demonstrator tested, nominal gradient obtained in cavities (CEA-Saclay)
  Medium Beta cavities production (INFN- LASA)
    3 cavities welded
    2 cavities bulk BCP surface treatment done and annealing
Cryomodules and elliptical cavities
RF voltage in
cavities 1-4
(Open loop &
Trapezoid pulse
on piezo tuner)
- High Beta cavities production (STFC – Daresbury)
  Niobium Material - Contract awarded in Oct17
  Final Nb batch delivery expected in Dec18
  Cavity Manufacture - Contract awarded in Jul18
Prototype cryomodule
with elliptical cavities
is now at Lund
for testing…
Mail from P. Michelato (INFN) on 21/12/2018:
“…The first INFN-LASA medium beta cavity… reached
23.7 MV/m with a Q0 of 7.9e9. At the ESS field of 16.7 MV/m,
the Q0 is 1.7e10, well over the ESS requirements of 5e9.
The frequency at cold is 704.221 MHz with a Qt of 3.6e11…”

## Slide 10: Work progresses actively at in-kind partners (2/2)
Cryomodules and spoke cavities
Prototype cryomodule delivered
at FREIA (Uppsala)
Start of test in February 2019
3 series spoke cavities have been tested and exceed requirements
Assembly of the 1st series cryomodule will begin mid –March
Delivery at FREIA mid-May

## Slide 11: Test infrastructure is operational at partners’ premises
Several Spoke prototypes tested in HNOSS
Successful validation test of high beta cavity assembly
Spoke prototype cryomodule received and being connected.
(e.g. FREIA in Uppsala)
Romea in HNOSS
cryogenics
- liquid helium
- liquid nitrogen
control room
- equipment controls
- data acquisition
radio-frequency (RF) power sources
3 bunkers
with test stands
horizontal cryostat
vertical cryostat
State-of-the-art Equipment
HB package at FREIA

## Slide 12: ESS Target and Target building
Target Building
(Target subproject is 38% complete)
130 m
22 m
37 m
High bay
Transport hall
Beam expander hall
Target monolith
Utilities block
Active cells
Target Building
Utilities and cooling plant
Remote handling systems
proton beam
proton beam window
proton beam instrumentation plug
Moderator and reflector
target wheel
neutron beam extraction port
monolith vessel
target monitoring plug
Target Monolith
Rotating solid tungsten target (11 t, 23.3 rpm)
Moderators (LH2 – 17 K and H2O – 300 K)
Helium gas cooling of target (11 bar, 3 Kg/s)
Target Safety System
Diagnostics and instrumentation

## Slide 13: High bay slab will soon be cast (CF is 67 % complete)

## Slide 14: Construction of Active Cells is advancing

## Slide 15: Construction of experimental hall E01 is well advanced (NSS is 27 % complete)

## Slide 16: Moved to site in summer 2018 - Moving to permanent office and lab buildings in 2021
Lund Tramway Depot
Permanent
Office Campus
2021
New 2018 ESS offices for all staff
Bus 20
PermanentEntrance

## Slide 17: Office and Laboratory Campus
Ground breaking for the ESS Offices and Laboratories
December 2018
Campus will consist of 3 buildings, 450 workspaces, 16 labs and workshops

## Slide 18: Campus
Labs and Workshops
Offices, auditorium canteen
Entrance Building
Plan to move in early 2021

## Slide 19: Key activities in 2019
Install and start commissioning next stage of the linac
Target Building access granted for start of technical (Target) equipment installation
Start instrument installation in long beamline Experimental Hall
Begin construction of Campus and Lab Buildings

## Slide 20: Thank you!