## Slide 1: STAP Sample Environment Engineering
Zvonko Lazic
European Spallation Source ERIC
April.2019

## Slide 2: Designing for the SAD – Sample Environment
A Scientist needs ‘something’ designed/produced
Engineer conceptualises the idea
Arrive at acceptable solution
Detailed design
Manufacturing
Finished Product
ESS based design

## Slide 3: Designing for the SAD – Sample Environment
A Scientist needs ‘something’ designed/produced
Conceptualise internally (Zvonko & the scientist)
Pass the concept to external designer
Detailed design
Manufacturing
Finished Product
External design

## Slide 4: Designing for the SAD – Sample Environment
A Scientist needs ‘something’ designed/produced
Engineer conceptualises the idea
Arrive at acceptable solution
Detailed design
Manufacturing
Finished Product
Extremely long time (internal communication difficulties, engineering competences missing…)
Extremely long time (ESS CAD procedures…)
ESS based design

## Slide 5: Designing for the SAD – Sample Environment
A Scientist needs ‘something’ designed/produced
Conceptualise internally (Zvonko & the scientist)
Pass the concept to external designer
Detailed design
Manufacturing
Finished Product
Working on fixed cost (fixed time-spent) for design, no cost overruns. Still problems with timely delivery.
External design

## Slide 6: Designing for the SAD – Sample Environment
*Done ‘all in-house’.
*The design effort took ~6 months.
*The designer – scientist communication wasn’t the best.
*The engineer was a ‘generic’ skilled person. + ESS is severely limited on engineering resources (we can either search for a particular skill, but have to wait ~6 months and more until the person is fully acquainted with the ESS CAD/PLM; or hire a software/CAD specialist without appropriate experience). + This bars us from acquiring suitable skilled designers (consultants).
ESS based design – case study

## Slide 7: Designing for the SAD – Sample Environment
*Initial concept developed here.
*Concept passed to external design house.
*External design house provided a fixed price for the development and detailed design.
*Upon several rounds of iterations, the detailing was completed. *We asked the design house to proceed with the manufacturing. *The manufacturing is completed, acceptance testing and consequent adjustment(s) are outstanding.
START
FINISH
@ ESS
@ subcontractor
External design – case study

## Slide 8: Designing for the SAD – Sample Environment
ESS based design
Fosters in-house expertise.
Designer-scientist at hand for discussions.
Prolonged design cycle.
Unforeseen costs.
Large overhead costs.
External vs. External design
External design
Expertise retained by externa company.
Distance communication.
Known (fixed) cost beforehand.
Timing (schedule) management needed.
Designs done at ½ the price at (at least) 2 x the speed
External design and manufacturing timeline:
First meeting April 2018
Internal conceptual design Jul 2018-Aug2018
Kinetic engaged Sept 2018
Kinetic Conceptual design finalised Dec 2018
Detailed design Jan 2019
Manufacturing Feb 2019
Delivery March 2019
Design cost: 7 600 [EUR]
(80 [hrs] concept + 120 [hrs] det.
Manufacturing cost: 8 000 [EUR]
Apr. ’18 | May ‘18 | June ‘18 | July ‘18 | Aug. ‘18 | Sep. ’18 | Oct. ’18 | Nov. ’18 | Dec. ’18 | Jan. ’19 | Feb. ’19 | Mar. ‘19
Initiation |  |  | ESS Conceptualisation |  | Engage ext. | Concept design finalised by ext. comp. |  |  | Det. Des. | Manuf. | Delivery

## Slide 9: Q&A
Questions?