## Slide 1: SRR process Thomas Hansson ESH 2019-04-05

## Slide 2: Safety Readiness Review (SRR)
The purpose is to review readiness to safely commission/operate.
The SRR is primarily intended for activities involving the proton beam, but could in specific cases also be applied for other systems.
The SRR is an independent review of the safety aspects, performed after the Test Readiness Review (TRR) or a corresponding activity.
It is a process by which TECHNICAL SYSTEMS, PERSONNEL and PROCEDURES associated with commissioning/operation are verified.
The scope is safety, both conventional safety and ionizing radiation.
The ownership of the SRR process lies within ESH division.
Governing SRR documents;
  ”Process for SRR” ESS-0123091, rev 2
  “System Documentation prior to a SRR” ESS-0177837 rev 3
Thomas Hansson ESH, 2019-04-05

## Slide 3: General principles on TRR and SRR
Integrate A+B
(install)
Integrate C+D = Complete system
(install)
Verify D
(testing)
Verify A+B
(testing)
Installation
beam commissioning
TRR
SRR
Verify C+D = Complete system
Commissioning
TRR
B
TRR
A
TRR
C
TRR
D
TRR
SRR
System owner responsible.
Scope: Performance and safety
ESH coordinates independent review
Scope: Safety
Verify B
(testing)
Verify A
(testing)
Thomas Hansson ESH, 2019-04-05
Integrate = install
Verify = test/commissioning

## Slide 4
An example

## Slide 5: The example of Test stand 2 (TS2) based on layout 2016-05-20
Integrate
Power cabling
+ Medium temp circuit
Integrate
Shielding + PSS
Integrate
PSS + LLRF + Modulator + Medium temp circuit
TRR
TS2
Integrate
Klystron + Medium temp circuit
Verify
Klystron
Verify
LLRF
Verify
Modulator
Integrate
ICS controls + LLRF
Verify
LCW
substation
Verify
Electrical
substation
Verify
Power cabling
Verify
Medium temp circuit
Verify
Cryoplant
Verify
Transfer Line
Verify
Shielding
Verify
PSS
Verify
RF
distribution
Verify
Signal
cabling
Verify
CDS
Valve box
Verify
Bunker *
Integrate Bunker + CDS valve box + Signal cabling + LLRF + RF distribution + Medium temp circuit = Cryomodule with insulation vacuum and beam vacuum
Installation
Commissioning
SRR
Integrate = install
Verify = test/commissioning
Verify Cryomodule, including
insulation vacuum and
beam vacuum
TRR RF distribution
TRR Electrical substation
TRR Power cabling
TRR Klystron
TRR Modulator
TRR
Bunker
TRR
PSS
TRR
CDS valve
box
TRR
Transfer Line
TRR
Cryoplant
TRR
Signal cabling
TRR ICS controls
TRR LLRF
TRR LCW substation
TRR Medium temp
circuit
TRR
Shielding
Verify
ICS controls
Draft
understanding
System owner responsible.
Scope: Performance and safety
ESH coordinates independent review
Scope: Safety
“hardware, personnel and procedures associated with commissioning and operation”
SRR
TRR
Thomas Hansson ESH, December 2018
* in addition to PSS detectors/actuators, there will be;
2 mobile stand-alone neutron detectors (RP)
X mobile stand-alone x-ray (𝛄) detectors (RP)
Y OSL detectors (RP)
Beam Loss Monitoring inside Bunker (BLM team)
Mobile RF monitors (WH)
etc.

## Slide 6
Integrate
Power cabling
+ Medium temp circuit
Integrate
Shielding + PSS
Integrate
PSS + LLRF + Modulator + Medium temp circuit
TRR
TS2
Integrate
Klystron + Medium temp circuit
Verify
Klystron
Verify
LLRF
Verify
Modulator
Integrate
ICS controls + LLRF
Verify
LCW
substation
Verify
Electrical
substation
Verify
Power cabling
Verify
Medium temp circuit
Verify
Cryoplant
Verify
Transfer Line
Verify
Shielding
Verify
PSS
Verify
RF
distribution
Verify
Signal
cabling
Verify
CDS
Valve box
Verify
Bunker
Integrate Bunker + CDS valve box + Signal cabling + LLRF + RF distribution + Medium temp circuit = Cryomodule with insulation vacuum and beam vacuum
Installation
Commissioning
SRR
Verify Cryomodule, including
insulation vacuum and
beam vacuum
TRR RF distribution
TRR Electrical substation
TRR Power cabling
TRR Klystron
TRR Modulator
TRR
Bunker
TRR
PSS
TRR
CDS valve
box
TRR
Transfer Line
TRR
Cryoplant
TRR
Signal cabling
TRR ICS controls
TRR LLRF
TRR LCW substation
TRR Medium temp
circuit
TRR
Shielding
Verify
ICS controls
Draft
understanding
Thomas Hansson ESH, December 2018
Documents required | Bunker | Shielding | PSS
Design descriptions |  |  | 
Architecture description |  |  | 
Concept of Operations |  |  | 
Req. Spec, incl. Hazard identification |  |  | 
Classification doc (rad safety) |  |  | 
Interface descriptions |  |  | 
Integration Plan |  |  | 
Operation & maintenance documents |  |  | 
Verification Plan |  |  | 
Verification Report |  |  | 
Validation Report |  |  | 
CE marking / Declaration of conformity |  |  | 
Other documents |  |  | 
Example
Integrate = install
Verify = test/commissioning
The example of Test stand 2 (TS2) based on layout 2016-05-20

## Slide 7
Thank you!
Questions?