## Slide 1
  ESS status
  John Womersley, Director General

## Slide 2: Journey to deliver the world’s leading facility for research using neutrons
2014
Construction Starts on Green Field Site
2009
Decision to Site ESS in Lund
2025
ESS Construction Phase Complete
2003
European Design of ESS Completed
2012
ESS Design Update Phase Complete
2019
Start of Initial Operations Phase
2023
ESS Starts
User Program
2019
TODAY

## Slide 3: ESS is 60 % complete
2019 is peak of construction activity
Accelerator commissioning underway
First Instrument hall complete and handed over
Working hard to deliver first science in 2023

## Slide 4: ESS highlights
Progress continues
  No major new technical issues of concern have arisen
  Schedule variance stable
Interventions on key procurement and in-kind deliveries
Licensing application for commissioning of the Normal Conducting Linac submitted on schedule
Two new members of senior management team in place; reorganisation
Positive decision made at June 2019 Council meeting on completion of construction funding (240M€2013)

## Slide 5: Conventional Facilities
Civil construction remains on (or ahead of) schedule
Handover of logistics building F03 and Instrument Hall E01
Steelwork erection for target building high-bay and for D buildings now underway
ESS offices and laboratory campus making rapid progress
Key challenges
Transitioning CF into basis of future ESS facilities management function
Onsite cooling water purity is an issue

## Slide 6: Accelerator
Accelerator installation making rapid progress
  Ion source and LEBT commissioned
  MEBT installed
  DTL received and being integrated
  RFQ delayed, but final components expected this week
Cryo-test stand permit received
Key challenges
Spoke cavity fabrication delays
Accelerator is not on critical path for ESS BOT but float is being eroded

## Slide 7: Target
Target installation now underway
  High bay steelwork
  Monolith shielding
Major components in manufacturing
Monolith vessel on track for delivery by end 2019
Key challenges
Target RBOT showing 6-7 months delay due to neutron beam port blocks (steel shielding)
  High level intervention with manufacturer in June-July
  Dramatically increased production rate, but unlikely to recover the full delay

## Slide 8: Instruments
Bunker is in manufacturing
Instruments design phase complete – moving into construction in IK partners
All “First 3” instruments (and 7 of first 8) endorsed by IKRC
Common shielding, chopper and beam monitor designs developed to save time and money
Reduced delay caused by port blocks on first science to 3 months by modifying bunker installation sequence
Key Challenges
Need to move ahead with large procurements in IK partners

## Slide 9: Installation and integration
Installation underway
  Steel framing, piping, cables, cryogenics, RF
  Generally been in learning mode up to now
Key challenges
Big ramp up of work this autumn
  Accelerator cryomodules
  Target equipment – main installations start end of this year
  ICS server room
  First instrument infrastructure in E01 from September
Strengthen installation organisation to better deliver

## Slide 10: A reminder of the ESS Critical Path
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float
Accel RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker & TBL RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
Instrument Hall Access for Start of Installation
Hi -Beta Install
0.8 GeV Capability Installed
BOT - Beam on Target
RBOT - Ready for Beam on Target
FS - First Science
SOUP - Start of User Programme
EOC - End of Construction project
FS
We are focused on delivering First Science with three instruments by the end of 2023
Schedule date (no float) is March 2023

## Slide 11: What worries me?
Maintaining schedule
  Especially in-kind deliveries – only takes a couple of issues to knock us off course
Managing cost to complete
  Project contingency is a challenge. Still five years to go…
Integration and installation need to ramp up
Management agility: need to intervene when necessary
  to address issues on major procurements, on in-kind etc.
Safety!

## Slide 12
ESS is entering a new phase
Your contributions are critical to success
First Science in 2023