## Slide 1: Science Update IKON 17
Andreas Schreyer
Director for Science
European Spallation Source ERIC
09 September 2019

## Slide 2: Excellent progress with construction

## Slide 3: Lab Building B02
Weather tight in Dec 2019!

## Slide 4: Summary Schedule and Critical Path for Remaining Work
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float
Accel RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker & TBL RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
Instrument Hall Access for Start of Installation
Hi -Beta Install
0.8 GeV Capability Installed
BOT - Beam on Target July 22
FS - First Science March 23
SOUP - Start of User Prog Dec 23
EOC - End of Construction project
RXXX - Ready for XXX
Float to Accelerator RBOT reduced from 14 months to 7 months due to IK delivery slippage
Target RBOT slipped 6 months, supplier issues, but rework of CF/Bunker/Target plans can reduce impact, BOT - slips 3-4 months.
Red line indicates critical path
FS
Updated instrument
Schedule: Shane’s talk
Notes: Reminder 0 contingency schedule, no float, 35,000 activities, 264 interface milestones, 101 L1
These dates are the Rebaseline - May 2018
3 parallel paths to success
Opportunity to regain 3 months but cask commissioning, Wheel and NBPI are in the way too

## Slide 5: Progress since last IKON
Progress on TA’s: Now 6 of the first eight instruments endorsed
Mapped out the global commercial manufacturing capacity for choppers and guides: no show stopper
Common shielding, monitor and chopper projects progressing well
Draft Scientific Evaluation and Access Policy in SMT, EMT and SAC. To Council in December
New MAX IV – ESS Science colloquia working out really well
Handover of E Hall: Event today!
Key goal for 2019: Begin installation of instruments
…

## Slide 6: Copenhagen Server Room (DMSC)
Stage 1 200kW
Handover event in October/November

## Slide 7: Joint ESS ILL User Meeting 2020
Date and Venue
Wed 23rd – Fri 25th September 2020
Lund: Rooms in AF Borgen, Universitetshusest and Palaestra
7

## Slide 8: Instrument Performance Comparison
 | 2016 Performance targets (@ 2MW) | Performance targets (2019) @ 2MW
LOKI | 5 x D22 & 20 x SANS2D | 5 x D22, 20 x SANS2D
SKADI | 4 x D22 | 5 x D22
ESTIA | Conventional mode: ~ 100 x D17 High intensity mode: 1cm2 samples = seconds | 10-100 x D17, depending on collimation mode
FREIA | 30 x FIGARO, INTER | 2-30 x FIGARO, depending on Q-range and resolution
DREAM | > 10 x POWGEN or WISH | > 10 x POWGEN & WISH
HEIMDAL | ~ 50 x GEM, ~ 8 x new POLARIS | ~ 50 x GEM, ~ 8 x new POLARIS
MAGIC | Cold: > 100 x worlds best, Thermal: 1mm3 crystals = 10 min | Cold: > 100 x world’s best, Thermal: 1mm3 crystals = 10 min
NMX | > 10 x LADI & Biodiff | > 20 x LADI & Biodiff
BEER | world leading in strain scanning, unique flexibility | 1-2 x TAKUMI, 3-6 x VULCAN, 14-28 x ENGIN-X, depending on multiplexing
ODIN | world leading for high resolution, > 10 x best for TOF methods | world leading for high spatial and temporal resolution, > 10 x best for TOF methods
BIFROST | > 10 x THALES & MACS | > 10 x THALES & MACS
CSPEC | 100 x IN5 (with RRM) | 6-150 x IN5 (3meV), depending on focusing and RRM
T-REX | 3 x 4-SEASONS, 3 x IN5 (without RRM) | 6-60 x IN5 (3meV), 10-100 x 4Seasons (100meV), depending on RRM
VESPA | 10 x VISION (ΔE = 130 meV) | 1-3 x VISION (ΔE < 160 meV) trading intensity for resolution
MIRACLES | 2 x BASIS and DNA | 4 x BASIS, 5 x DNA, for QENS at same resolution
2016 vs 2019

## Slide 9: Instrument Performance
All Instruments are funded to be world-leading at 2MW power
Instrument Class | Instrument | Performance targets (2019) @ 2MW
Large Scale Structures | LoKI (Broad band SANS) | 5 x D22, 20 x SANS2D
 | SKADI (General Purpose SANS) (+SONDE funds) | 5 x D22
 | ESTIA (Focusing Reflectometer) | 10-100 x D17, depending on collimation mode
 | FREIA (Liquids Reflectometer) | 2-30 x FIGARO & INTER, depending on Q-range and resolution
Diffraction | DREAM (Bispectral powder diffractometer) | > 10 x POWGEN & WISH
 | HEIMDAL (Hybrid diffractometer) | ~ 8 x POLARIS, ~ 50 x GEM
 | MAGiC (magnetism single crystal diffractometer) | Cold: > 100 x world’s best, Thermal: 1mm3 crystals = 10 min
 | NMX (Macromolecular crystallography) | > 20 x LADI & Biodiff
Engineering & Imaging | BEER (Engineering diffractometer) | 1-2 x TAKUMI, 14-28 x ENGIN-X, depending on multiplexing
 | ODIN (multi-purpose imaging) | world leading for high spatial and temporal resolution, > 10 x best for TOF methods
Spectroscopy | BIFROST (extreme environment spectrometer) | > 10 x THALES & MACS
 | CSPEC (cold chopper spectrometer) | 6-150 x IN5 (3meV), depending on focusing and RRM
 | T-REX (bispectral chopper spectrometer) | 6-60 x IN5 (3meV), 10-100 x 4Seasons (100meV), depending on RRM
 | VESPA (vibrational spectroscopy) | 1-3 x VISION (ΔE < 160 meV) trading intensity for resolution
 | MIRACLES (backscattering spectrometer) | 4 x BASIS, 5 x DNA, for QENS at same resolution
Version 27/8/2019

## Slide 10: Instrument Papers
Status in September 2019
Single long paper for all instruments
  agreement to submit to Nucl. Instr. Meth. A
  full draft exists
  all instruments have written their part
  introduction and conclusion sections written by Ken with input from Andreas and Dimitri
  introductory sections for each instrument class written by instrument class coordinators
  most sections have been through more than one iteration
  instrument “quick facts” tables completed
  instrument layout figures making good progress with graphic designer
  harmonisation of instrument and instrument class sections ongoing (Ken, Andrew, Andreas, …)
  ready for circulation to all instrument teams by early October
  plan to submit in November
Individual instrument papers
  to be timed roughly with TG3 of each instrument
  format remains to be agreed
  no decision yet on journal, but needs to be covered by citation index

## Slide 11: Installation in E-Hall has started!
CSPEC: First components of Guide support structure
More to come in 2019:
First components for guide support structure for more instruments
Shielding support blocks for CSPEC, BIFROST, MAGIC
NBOA integration (temporary tent)
Temporary storage of Lab furniture for E03/04

## Slide 12: E03-E04 buildings fit-out (Q1-2020)
Installation starts: Q1/2020
Buildings: E04 (handover December 2019)
Main tasks: Installation of piping above the suspended ceiling (lab gases, power cables, fume hoods…..)
Installation of lab furniture, fume hoods,…
IRR: Q4/2019
Responsible: NSS

## Slide 13: Bifrost: experimental cave structure
Installation starts: April 2020
Structure: pre-cast concrete blocks;
Resources: Bifrost civil contractor, ESS support for handling, surveying, lifting;

## Slide 14: E01/E02.1 electrical power distribution
Substation
Instruments power panel
Instruments control racks
CF
NSS
Instruments teams
Installation starts: Q4/2020
Buildings: E01, E02.1
Resources: NSS (electrical framework agreement for installation in place)
Responsible: NSS;
E05

## Slide 15: Bunker project:
installation of R6 bracket Q1-2020
R6 brackets installation : Q1/2020 (28.02.2020)
Halls: D02 (both D01 and D03 side, two teams involved at the same time)
Resources: NSS (framework agreement)
IRR: Q4 2019
Responsible: NSS
Parallel work with SKANSKA: before building handover
R6 brackets
Coordination with Skanska and ESS target ongoing
Installation plan resource loaded already submitted at Bunker CDR on December 2018

## Slide 16: Bunker Manufacuring is progressing well

## Slide 17: Programme Overview
9th September 2019
IKON17, Hotel Lundia
E01 Hall Ceremony Handover, ESS Site
12.00-13.00 | Regsitration | 
13.00-13.10 | Welcome from the DG | John Womersley
13.10-13.40 | Welcome and Science Update | Andreas Schreyer
13.40-14.10 | NSS Project Update | Shane Kennedy
14.10-14.30 | Target Update | Rikard Linander
14.30-14.45 | NBOA/NBEX Update | Hansdieter Schweiger
14.45-15.15 | Coffee break | 
15.15-16.00 | Update: DREAM & BIFROST | Mikhail Feygenson, Rasmus Toft-Petersen
17.00-17.15 | Arrival at the E-Hall | 
17.20-17.45 | Welcome and speeches | 
17.45-18.00 | Photo call: ”Key” hand-over and Instrument Suite | 
18:00-18.50 | Mingle | 
18.50/19.00 | Departure back to Lund C | 

## Slide 18: Stage Programme
17.20-17.26 Welcome John
17.26-17.32 Greetings from Council Kurt
17.32-17.40 The long instrument hall
incl. movie Andreas
17.40-17.45 Hand-over from Skanska Per
17.45-17.50 Photo call: ”Key” hand-over Per, John, Kurt, Andreas
17.50-18.00 Photo call: Instrument suite
Call-up instrument by instrument John + Andreas

## Slide 19: Floor Plan of the E-Hall Area

## Slide 20: Photo Call Instrument Suite

## Slide 21: Photo Call Instrument Suite