## Slide 1: NSS Project status update
Shane Kennedy
NSS Project Leader
www.europeanspallationsource.se
IKON 17, Lund, 9th September 2019

## Slide 2: NSS Project scope: 15 neutron instruments + test beamline + support labs
ESS Instrument Layout (September 2017)
ESS In-Kind Partners also collaborate on sample environment, data management, lab fitout (D04, D08, E03 & E04) etc.
ESS Lead Partners for instrument construction
ODIN
DREAM
NMX
MIRACLES
T-REX
MAGIC
BIFROST
HEIMDAL
FREIA
LOKI
VESPA
ESTIA
SKADI
+
+
C-SPEC
+
Nuclear Physics Institute
BEER
Test Beam Line
D07
D08
D04
E03
E04

## Slide 3: NSS Schedule Overview

## Slide 4: Baseline schedule for Neutron Beam Instruments (NSS MS V4.2)
2016 2017 2018 2019 2020 2021 2022 2023 2024 2025 2026
* NBI = Neutron Beam Instrument
West sector
North sector
East and South sectors
Current date
SOUP
(3NBI*)
BOT
& HC
8NBI* in User Program
FS
First 3 NBI selected for SOUP: DREAM, LOKI & ODIN (best chance for early impact, as agreed by NSS, SAC and ESS Council)
Back-up instruments: (for risk of late access to D01 & D03) BEER, CSPEC, MAGIC or BIFROST, ESTIA
Preliminary Design
Detailed Design
Manufacturing & Procurement
Installation & Integration
Hot Commission/Early science
Operation
March 2023:
First Science (FS) with expert teams on some of instruments above
Review progress of first 3 NBI for SOUP, implement backup plan if needed.
FS

## Slide 5: NSS Schedule detail (Bunker, & first instruments)
Preliminary Design
Detailed Design
Manufacturing & Procurement
Installation & Integration
Hot Commission/Early science
Operation
Bunker Installation:
CP for BOT
Test Beamline Installation:
116 days float for BOT
Instrument 1-3 Commissioning:
CP for First Science & SOUP
Current date
SOUP
(3NBI*)
BOT
& HC
FS
Schedules updated for LOKI, ODIN, DREAM, CSPEC, MAGIC & ESTIA all updated with new TA agreements and/or monthly reports
Detailed Schedules for BEER & BIFROST currently under review

## Slide 6: Budget Overview

## Slide 7: The NSS Project Neutron Instruments
Instrument Class | Neutron Instrument | Budget (M€) | Partners
Large Scale Structures | LOKI (Broad band SANS) | 12.85 | ISIS (81 %) + ESS (19 %)
 | SKADI (General Purpose SANS) (+SONDE funds) | 11.50 | FZJ (50 %) & LLB (50 %)
 | ESTIA (Focusing Reflectometer) | 11.80 | PSI (100 %)
 | FREIA (Liquids Reflectometer) | 13.20 | ISIS (100 %)
Diffraction | DREAM (Bispectral powder diffractometer) | 13.66 | FZJ (76 %), LLB (20 %) + ESS (4 %)
 | HEIMDAL (Hybrid diffractometer) | 13.55 | Åarhus U. (30%), PSI (35%), IFE (35%)
 | MAGIC (magnetism single crystal diffractometer) | 13.10 | LLB (52 %), FZJ (24 %), PSI (16 %) + ESS (8 %)
 | NMX (Macromolecular crystallography) | 11.67 | ESS (33%), WI/IER(38%), Bergen (22%), LLB (7%)
Engineering & Industrial | BEER (Engineering diffractometer) | 14.99 | NPI (50%) & HZG (50%)
 | ODIN (multi-purpose imaging) | 11.77 | TUM (60 %), PSI (36 %) + ESS (4 %)
Spectroscopy | BIFROST (extreme environment spectrometer) | 13.45 | DTU/KU (26%), PSI (32%), IFE(22%), LLB (20%)
 | C-SPEC (cold chopper spectrometer) | 16.50 | TUM (50%), LLB (40%) + ESS (10 %)
 | T-REX (bispectral chopper spectrometer) | 16.85 | FZJ ( 75%) & Perugia U. (25%)
 | VESPA (vibrational spectroscopy) | 12.00 | CNR (100%)
 | MIRACLES (backscattering spectrometer) | 13.40 | ESS-Bilbao (98%), KU (1%), ESS (1%)
Total cost book value (M€) |  | 200.28 | 

## Slide 8: NSS major non instrument IK work packages: (total value 20.3 M€)
Sept 2019
Current total value (including planned work) = 20.3 M €

## Slide 9: NSS In-Kind Contributions: Summary by Country
August 2019
* Proposed split of IT (90%) & UK (10%) contributions to VESPA under review - could shift further to UK & ESS
Total IK contributions (approved, planned & potential): 210.4 M€ (92.5 % of the NSS IK target)
IKC constitutes > 61 % of NSS scope
There is still some potential for IK contributions
Notes: Pie-chart to the right needs to be updated

## Slide 10: Construction project: NSS performance progress (July 2019)
Schedule Variance (SV): -2,1 M€ & SPI = 0,98
Cost Variance (CV): 2,78 M€ & CPI = 1,03
NSS budget = 361 M€ (Ringfenced)
NSS Project is 30 % complete
Preliminary design complete, detailed design ongoing, bunker under construction
Instrument IK: 7/15 instruments (incl all of first three) have all TAs in place, procurements and manufacturing starting
Cash Spent = 86.14 M€
In Kind Spent = 15.04 M€
210.4 M€ by IK partners
- In part treated as cash IK
Manufacturing & Procurement
Planned | Earned | Actual | SV | CV | SPI | CPI*
106 048 845 | 103 960 161 | 101 180 131 | -2 088 683 | 2 780 031 | 0,98 | 1,03
NSS central contingency
Estimated need* = 27.08 M€
Available funds = 17.66 M€
Shortfall (EAC – BAC) = 9.42 M€
* Contingency Need = Uncertainty risk
+ forecast changes + event risks
Notes: 91,7
338,04
---
Variance analysis thresholds at subproject level (Level 2):
Cumulative Cost Variance threshold: CPI < 0.95 and CV < - 0.5 M€
Cum Schedule Variance threshold: SPI < 0.95 and SV < - 0.5 M€
Note: These values are fairly tight since we have re-baselined each year

## Slide 11: NSS major procurements

## Slide 12: Neutron Bunker:
Neutron Bunker (Total Budget = 18 M€)
Now in manufacturing,
first deliveries in November
Start installation Feb 2020 (R6).
Inspection of pilot block manufacturing (Hungary, 28 August):
“most block dimensions are either correct, or within +/- 2 mm”

## Slide 13: Other NSS major work for Neutron Instrument Construction: (~ 25 - 30 M€)
Common guide shielding (value ~ 10 - 12 M€)
  9 instruments: BIFROST, C-SPEC, DREAM, HEIMDAL, MAGIC, MIRACLES, ODIN, T-REX & VESPA - tenders for first 3-6 close 15th September
  NMX &/or BEER may join
Neutron detectors (value ~ 10 M€)
  Five Instruments: C-SPEC, ESTIA, FREIA, NMX & T-REX,
Beam monitors (value ~ 1.5 M€)
  Potentially most instruments will join
Installation & cold commissioning (value ~ 2 - 3 M€)
  2 instruments: LOKI, FREIA
  VESPA may join
Common slow choppers (value ~ 3 - 5 M€) - Preliminary offers made
  Potentially 9 instruments: BEER, BIFROST, C-SPEC, HEIMDAL, LOKI, MAGIC, MIRACLES, NMX, & SKADI

## Slide 14: Project IK Status & planned Activities -next 6 months

## Slide 15: Status of In Kind documentation for neutron instruments
Neutron Instrument | Budget M€ | IK Partners | MoU | Phase I | Phases II-IV | 
 |  |  |  |  | No. of TAs | Status of TA
LOKI (Broad band SANS) | 12.85 | UKRI/STFC | SIGNED | Passed | 1 | 1 SIGNED
ESTIA (Focusing Reflectometer) | 11.80 | PSI | DRAFT | Passed | 1 | 1 SIGNED
DREAM (Bispectral powder diffractometer) | 13.66 | FZJ and LLB | DRAFT | Passed | 2 | 2 SIGNED
MAGIC (magnetism single xtal diffractometer) | 13.10 | FZJ, LLB and PSI | SIGNED | Passed | 3 | 3 SIGNED
BEER (Engineering diffractometer) | 14.99 | NPI and HZG | NO DRAFT | Passed | 2 | 2 UNDER REVIEW
ODIN (multi-purpose imaging) | 11.77 | TUM and PSI | SIGNED | Passed | 2 | 2 SIGNED
C-SPEC (cold chopper spectrometer) | 16.50 | TUM and LLB | NO DRAFT | Passed | 2 | 2 SIGNED
BIFROST (extreme environment spectrometer) | 13.45 | DTU, KU, IFE, LLB and PSI | SIGNED | Passed | 5 | 1 SIGNED
 |  |  |  |  |  | 4 UNDER REVIEW
HEIMDAL (Hybrid diffractometer) | 13.55 | ÅU, IFE and PSI | SIGNED | Passed | 3 | 3 UNDER REVIEW
NMX (Macromolecular crystallography) | 11.67 | Wigner, EK, LLB, Bergen U. | SIGNED | Passed | 11 | 8 SIGNED
SKADI (General Purpose SANS) (+SONDE funds) | 11.50 | FZJ and LLB | NO DRAFT | Passed | 2 | 2 UNDER REVIEW
FREIA (Liquids Reflectometer) | 13.2 | UKRI/STFC | SIGNED | Passed | 1 | DRAFT
T-REX (bispectral chopper spectrometer) | 16.85 | FZJ and CNR | NO DRAFT | Passed | 2 | DRAFT
VESPA (vibrational spectroscopy) | 12.0 | CNR and UKRI/STFC | SIGNED | Passed | 2 | NO DRAFT
MIRACLES (backscattering spectrometer) | 13.40 | ESS Bilbao and KU | DRAFT | Passed | 1 | 1 UNDER REVIEW
IK-total CBV = 190.10 M€, ESS+total value =10.2 M€ | 200.28 |  | 7/15 | DONE | 40 | 20/40
First eight instruments shown at top of table

## Slide 16: Next Six Months: • Manufacturing progressing for First 8 instruments* • First Installations in E01 & E02
2018-2019 | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
LOKI |  |  |  |  |  |  |  |  |  |  |  | 
SKADI |  |  |  |  |  |  |  |  |  |  |  | 
ESTIA |  |  |  |  |  |  |  |  |  |  |  | 
FREIA |  |  |  |  |  |  |  |  |  |  |  | 
NMX |  |  |  |  |  |  |  |  |  |  |  | 
MAGIC |  |  |  |  |  |  |  |  |  |  |  | 
HEIMDAL |  |  |  |  |  |  |  |  |  |  |  | 
DREAM |  |  |  |  |  |  |  |  |  |  |  | 
BEER |  |  |  |  |  |  |  |  |  |  |  | 
ODIN |  |  |  |  |  |  |  |  |  |  |  | 
CSPEC |  |  |  |  |  |  |  |  |  |  |  | 
BIFROST |  |  |  |  |  |  |  |  |  |  |  | 
MIRACLES |  |  |  |  |  |  |  |  |  |  |  | 
T-REX |  |  |  |  |  |  |  |  |  |  |  | 
VESPA |  |  |  |  |  |  |  |  |  |  |  | 
Final TG3
SAC22
ICB12
IKRC16
29
IKON17
STAP
DMSC STAP
s
Subsystem TG3 (intermediate)
s
s
s
s
s
12
8
2-3
30
24-25
25-26
SAC 23
s
s
s
s
s
s
s
s
s
Intermediate Design Review
s
s
s
s
s
s
s
s
s
s
s
7-8
IKRC19
10-11
ICB13
15-16
TG4 (to be confirmed)
IKON18
* 13/14 NBOA are in manufacturing:
9 with SNAG and 4 with SDH

## Slide 17: Questions ?