## Slide 1: Target Sub-project Update IKON17
Rikard Linander
Acting Head of Target Division
European Spallation Source ERIC
9th September 2019

## Slide 2: Target sub-project is 45% complete
Current budget at completion for the ESS Target Sub-project is 222M€
Earned value end of July 2019 is 100M€
Since the re-baseline mid 2018 CF has held the site early access dates
Target Ready for Beam milestone is March 2022
  Currently the sub-project is carrying a negative float of about 6 months.
  Most Target WP installations are with < 40 days float to Critical Path.
Several heavy steel structures (~700 tonnes) have been installed, including monolith vessel supports, baseplate, ground shielding, and D2T shielding
Raw material for monolith vessel delivered to manufacturer. On track for delivery of this in-kind element by end of this year.

## Slide 3: The Target Sub-Project Context

## Slide 4: ESS Target Station Collaborators
- In-kind partners

## Slide 5: Key features of the ESS Target Station
Helium cooling of target material
Mass flow 3 kg/s
Pressure 11 bar
Temperature inlet/outlet 40 °C/240 °C
proton beam
proton beam window
proton beam instrumentation plug
Moderator and reflector
target wheel
neutron beam extraction port
monolith vessel
target monitoring plug
Rotating solid tungsten target
36 sectors
Mass, total 11 tonnes, whereof 3 tonnes of W
Rotates 23.3 rpm, synchronized with pulsed proton beam 14 Hz
Moderators
Provisional locations of moderators above and beneath the target wheel, i.e. monolith centre
1st MR plug exploits the upper space, offering:
  Cold, 30 mm high, liquid H2 moderators, 17 K
  Thermal, 30 mm high, H2O moderator, 300 K
Diagnostics and instrumentation
Controlled and integrated commissioning and operation of the accelerator and target
Fluorescent coating of PBW and target front face
Optical paths, grid profile monitor, aperture monitor
Wheel monitoring including position, temperature, vibration, as well as internal structure
Target Safety System
Monitors target coolant flow, pressure and temperature, monolith pressure, & target wheel rotation
Prohibit beam on target if parameters are outside specified limits
Neutron beam extraction
Offers 42 neutron beam ports
Allows neutron science instruments to view either upper or lower moderator position

## Slide 6: Key features of the ESS Target Station
Utilities and cooling plant
Helium cooling of target wheel
Water cooling of moderators, plugs and shielding
Intermediate water loops between primary circuits and conventional facility utilities
Helium cryoplant for refrigeration of cold moderator system
Nuclear grade HVAC system
130 m
22 m
37 m
High bay
Transport hall
Remote handling systems
Large active cells for safe storage and processing of spent radioactive target components
Shielded casks for transfer of spent components from monolith to active cells
Beam expander hall
Target monolith
Utilities block
Active cells

## Slide 7: Monolith foundation

## Slide 8: Monolith space

## Slide 9: Monolith vessel, outer shielding, and inner shielding
Monolith Puck
Monolith vessel
Monolith Port Block Package (360°)
Outer Shielding (360°)
Neutron Beam Port Inserts (42x)
Outer Shielding (360°)
Outer Shielding (360°)

## Slide 10: Monolith vessel

## Slide 11: Monolith vessel

## Slide 12: Monolith Port Block Package
East Block
South Block
West Block
North Block
NN-Bar Frame
Shielding beam level
Shielding beam level Proton Beam Section
PBW Port Block – Shielding

## Slide 13: Site Installation Progress

## Slide 14: Site installations
- Ground Shielding

## Slide 15: Site installations
- Monolith Vessel Supports, Monolith Baseplate, Ground Shielding, and Wall Embedments

## Slide 16: Site installations
- Bulk Shielding above D2T

## Slide 17: Site installations
- Embedments for Neutron Shield wall

## Slide 18: So, Target has entered installation phase!
ACF liner plates will start being installed September
Tuning Beam Dump is scheduled for installation in October/November
Monolith Vessel installation activities begin in December/January.
Cooling systems and HVAC installation starts 2019 Q1
- What’s next?

## Slide 19: Target Deliveries Progress

## Slide 20: Target Systems
Target wheel and drive unit
Progress on Target Helium Cooling System
Target monitoring plug
Tungsten Bricks in Cassette

## Slide 21: Target Wheel
- Tungsten bricks received, awaiting assembly

## Slide 22: Target Wheel
- Tungsten bricks mounted in cassette

## Slide 23: Target Wheel
  One Tungsten Cassette finally fitted into the Target Wheel Prototype.
- Prototype #1 & #2 Problems
Key accomplishment
Very narrow tolerance between the cassette and the wheel
Challenged by the wheel manufacturing welding.
The heat transferred during welding tends to deform the wheel structure.
Mitigations needs to be applied for the final wheel manufacturing

## Slide 24: Target Wheel
- Prototype #3 success

## Slide 25: Moderator / Reflector Systems, Irradiation Module
Helium Cryoplant
Cryogenic Hydrogen System
Irradiation module
MR Plug
Moderator and reflector plug
  Detailed design completed for all parts of MR plug, fabrication imminent
  Order for beryllium placed
  Extensive prototyping and testing on-going
Cryostat internals
Cryogenic moderator prototype
Hydrogen System
Cryogenic

## Slide 34: Moderator / Reflector
- Shaft ready for assembly
Courtesy of FZJ

## Slide 35: Steel supply challenges
- Ingot surface cracking

## Slide 36: Steel supply challenges
- Ingot surface cracking

## Slide 37: Steel supply challenges
Neutron Beam Port Blocks
  Start of installation currently carrying a negative float of 132 days to Target RBOT
  The lessons learned are that complicated, non-standard production requires more schedule contingency, and large industries are less agile and adaptive.
  Material quality issues, with severe edge cracking, were encountered and caused delays.
  The measures taken to mitigate further delays are weekly video meetings focusing on schedule, site visits, top management intervention, and enforcing agile decision making.
  The manufacturer’s remedy for schedule recovery is to redistribute some production between different facilities. We see more stability in their plan and recovery of two weeks. Without actions, the delay could easily have become doubled from the original 13 weeks instead.
  Further measures will be to secure flexible planning and coordination of the the subsequent workshop machining phase with the manufacturing company.
- Current main Target sub-project schedule concern

## Slide 38: Neutron Beam Port Tubes
- In manufacturing
Bottom part of port tube, with insert alignment features
Port flange raw material
Top parts of port tubes

## Slide 39: Neutron Beam Port Insert
- Manufacturing Prototype

## Slide 40: Neutron Beam Port Insert
- Manufacturing Prototype
Void for Neutron Beam Optics Assembly
Neutrons here!
Cut-out for rollers

## Slide 41: Insert Installation Tool
- In manufacturing

## Slide 42: Neutron Beam Extraction System
- Test Stand Frames
Horizontal test stand frame
Vertical test stand frame

## Slide 43: Concluding remarks
Several heavy steel structures (~700 tonnes) have been installed, including monolith vessel supports, baseplate, ground shielding, and D2T shielding.
Hardware deliveries are arriving continuously and are kept in storage, awaiting installation.
Main installations will ramp up to full speed by end of 2019.
Target Ready for Beam milestone is March 2022.