## Slide 1: Update on NBOA progress NBOA = Neutron Beam Optics Assembly (in-Monolith optics)
Hansdieter SCHWEIGER
on behalf of NSS Technical Coordination
European Spallation Source ERIC
IKON17, September 2019

## Slide 2: Content – Update on NBOA progress
Status quo
  Stakeholders and Responsibilities
  Review and approval procedure
  Schedule and Milestones
Integration and Installation
  Location and Infrastructure
  Process and Responsibilities
Summary and Outlook
  Lessons Learned
  Questions
Why is everybody
pointing at me??
Sketch of NBOAs and the scared moderator

## Slide 3: Status quo
What we all do for earning our money
Stakeholders and Responsibilities
In-kind partner - YOU:
Conceptual NBOA design
Procurement of NBOA
Approvals of Deliverables
NBOA manufacturer – SDH, SNAG:
Detailed NBOA design
Fabrication of NBOA
Integration of NBOA into NBPI
ESS NSS – Hans, Beniamino:
Responsibility over reference drawings/models
Technical coordination and interface control
Quality control standardization/harmonization
NBOA procurements (if applicable)
ESS Target Division – Naja, Bengt:
System responsibility of NBEX2 and all related interface documents
NBPI1 manufacturer - FZJ:
Detailed NBPI design
Fabrication of NBPI
1NBPI = Neutron Beam Port Insert
(Steel plug that will contain NBOA)
2NBEX = Neutron Beam Extraction System
(NBPI + NBOA + other stuff)
*** = sneaky communication path
(can be very efficient)
***
***
***

## Slide 4: Status quo
And yet another diagram
Review and Approval procedure
In-kind partner
NBOA manufacturer
ESS NSS
ESS Target Division
NBPI manufacturer
Symbol for the “sea of desperation”
in order to get there
Color coding showing major involvement of:
NBOA conceptual design:
Technical specifications
NBOA conceptual design:
Conceptual drawings
(“released for procurement”)
NBOA procurement:
Release, offers, bidder selection
Contract signature/kick-off:
Updated conceptual drawings
(“released for detailed design”)
Preliminary NBOA design (PDR)
Manufacturability Check of NBPI:
“Model hand-over” to ESS Target Division
Final NBOA design (FDR)
~ Toll Gate 3 (TG3)
NBOA manufacturing
(what a surprise!)
Factory acceptance Test (FAT)
Site acceptance check
Integration readiness review
Integration and adjustment
Sealing of NBPI, Project Termination
Handover to ESS Target Division
(NBPI installation into monolith)

## Slide 5: Status quo
And yet another diagram
Review and Approval procedure
Red arrows = Points of interest
NBOA conceptual design:
Technical specifications
NBOA conceptual design:
Conceptual drawings
(“released for procurement”)
NBOA procurement:
Release, offers, bidder selection
Contract signature/kick-off:
Updated conceptual drawings
(“released for detailed design”)
Preliminary NBOA design (PDR)
Manufacturability Check of NBPI:
“Model hand-over” to ESS Target Division
Final NBOA design (FDR)
~ Toll Gate 3 (TG3)
NBOA manufacturing
(what a surprise!)
Factory acceptance Test (FAT)
Site acceptance check
Integration readiness review
Integration and adjustment
Sealing of NBPI, Project Termination
Handover to ESS Target Division
(NBPI installation into monolith)

## Slide 6: Status quo
Where the instruments currently are
Review and Approval procedure
BEER
HEIMDAL
LOKI
VESPA
DREAM
NMX
T-REX
C-SPEC
ODIN
FREIA
Pascale just loves the dash
ESTIA
BIFROST
MAGIC
(No NBOA)
SKADI
MIRACLES
NBOA conceptual design:
Technical specifications
NBOA conceptual design:
Conceptual drawings
(“released for procurement”)
NBOA procurement:
Release, offers, bidder selection
Contract signature/kick-off:
Updated conceptual drawings
(“released for detailed design”)
Preliminary NBOA design (PDR)
Manufacturability Check of NBPI:
“Model hand-over” to ESS Target Division
Final NBOA design (FDR)
~ Toll Gate 3 (TG3)
NBOA manufacturing
(what a surprise!)
Factory acceptance Test (FAT)
Site acceptance check
Integration readiness review
Integration and adjustment
Sealing of NBPI, Project Termination
Handover to ESS Target Division
(NBPI installation into monolith)

## Slide 7: Status quo
Where we currently are, shown in a more complicated way
Blue = Delays
Red = Design Phase
Yellow = Manufacturing
Note:
The integration/installation schedule (Green) will be revised end of September. Also SAT milestone dates will be updated then.
Schedule and Milestones
Friday last week

## Slide 8: Integration and Installation
NBOA comes to ESS
NBPI comes to ESS
NBOA goes into NBPI
NBPI goes into experiment
Location and Infrastructure
This is where you party tonight.
(E01 instrument hall)
This is where we integrate
the NBOA into the NBPI.
(“HEIMDAL corner”)
This is where the NBPI goes into the monolith.
(Monolith area)

## Slide 9: Integration and Installation
Temporary “clean” tent
Location and Infrastructure
~15m x 15m
Entrance
Exit
8
5
Temporary NBPI
Storage, Cleaning, Test
Integration
Survey
Sealing
Leak Test
Unwrapping
Rough cleaning
Preparation for
Logistics
STORAGE
WASTE DISPOSAL
CHEMICALS
WASTE DISPOSAL
STORAGE
STORAGE
Storage
Temporary tent (Image credits: O.B.Wiik)
Small crane (WLL ~1000kg)
Support structures for testing,
adjustment and integration
10
15
15
10
5

## Slide 10: Integration and Installation
NSS: Overall Coordination
ESS Target: NBPI testing, sealing and logistics
NBOA manufacturer: Adjustment & integration
ESS Survey team: Technical support
Workflow (simplified):
Process and Responsibilities
(1) Arrival of NBPI and NBOA in crates
(2) Unpacking, transport into clean area
(3) Cleaning, unwrapping
(4) Transport/lifting on Survey station
(5) Integration, survey and NBOA alignment
(6) Sealing and leak test
(7) Wrapping and logistics preparation
(8) Transport to storage/monolith

## Slide 11: Summary and Outlook (not the one by Microsoft)
All NBOAs* have been procured. This is a major achievement. Thank you for your collaboration!
The most time-critical NBOAs for final design delivery (end of 2019) are HEIMDAL (complexity) and BEER (delay).
The first NBOA is planned to be integrated in early/mid 2020, the rest is going to follow in the few months after this.
The temporary integration tent will be set up and filled with tools after the E01 building hand-over this evening.
Summary
*except BEER, but it has been published in the ESS system last week

## Slide 12: Summary and Outlook
Technical Coordination within the current ESS in-kind collaboration model is tricky.
  No formal authority to impose ESS standards, envelopes and NBEX interface agreements.
Big delays due to incomplete interface definitions and unclear agreements.
  Some procurements were launched before framework (NBPI constraints) was fully understood.
  As a result, an appropriate structure had to be created on-the-fly, which did not make suppliers happy.
  Responsibility for NBPI design changed beginning of this year, which did not help either.
There are not many specialized guide suppliers that were qualified to manufacture NBOAs.
  Small companies have small design teams  Extra-time needed for development of alignment features.
  Market dictates the price of high-tech products that comes from limited resources.
  Coordination approach needs to be inclusive, by creating trust and investing time.
Lessons learned

## Slide 13: Summary and Outlook
Technical Coordination within the current ESS in-kind collaboration model is tricky.
  No formal authority to impose ESS standards, envelopes and NBEX interface agreements.
Big delays due to incomplete interface definitions and unclear agreements.
  Some procurements were launched before framework (NBPI constraints) was fully understood.
  As a result, an appropriate structure had to be created on-the-fly, which did not make suppliers happy.
  Responsibility for NBPI design changed beginning of this year, which did not help either.
There are not many specialized guide suppliers that were qualified to manufacture NBOAs.
  Small companies have small design teams  Extra-time needed for development of alignment features.
  Market dictates the price of high-tech products that comes from limited resources.
  Coordination approach needs to be inclusive, by creating trust and investing time.
Lessons learned
Good luck with your guide procurements!
A few meters done, a few km to go!
#@%§!!
Image credits: SEMI_RAD

## Slide 14: Summary and Outlook
Thank you for your attention!
Thanks also to Beniamino, Iain, Naja, Bengt, Chris and all stakeholders for the good collaboration in the last 1.5 years!
Any questions?
Questions
Feel also free to contact me
 Hansdieter.Schweiger@esss.se

## Slide 15: Backup slides

## Slide 16: Backup slides
Quality checks
Check of completeness of Technical Specifications/Offers for Tender (TG3A)

## Slide 17: Backup slides
Quality checks
Technical check of reference models and drawings (Model Hand-over check)

## Slide 18: Backup slides
Quality checks
TG3 review

## Slide 19: Backup slides
Model hand-over to Target Division
NBOA/NBEX interface document

## Slide 20: Backup slides
Model hand-over to Target Division
Confirmed 3D model
Interface drawing