## Slide 1: BIFROST: Update
Rasmus Toft-Petersen (DTU/ESS) Liam Whitelegg (ESS)
Technical University of Denmark

## Slide 2
Bifrost phase 2
Status of reviews
Progress: Vacuum tank
Progress: Cave
Progress: Instrument cabin
Progress: Detectors
Problems: TA’s
Potential problems: Cave validation

## Slide 3
Overview

## Slide 4
Overview

## Slide 5
Review status
 | CTV | Tender | PDR | IDR | Sub TG-3 | Installation Starts
Spectrometer Tank | Cleared | Cleared | Cleared | On-going | Planned Dec 19 | Planned Aug 20
Cave | Cleared | Goes Live 20/09 | Planned Jan 20 | Planned Feb 20 | Planned April 20 | Planned June 20
Analysers | Cleared | Planned Oct 19 | N/A | N/A | N/A | Planned July 21
NBOA | Cleared | Cleared | Cleared | N/A | N/A | Planned Dec 20
Guide | Cleared | Planned Oct 19 | Planned April 20 | Planned June 20 | Planned Sept 20 | Planned Nov 21
Choppers | October 2019 | Planned Nov 19 | Planned March 20 | Planned Apr 20 | Planned June 20 | Planned Jan 22
Detector Tubes | October 2019 | Planned Nov 19 | N/A | N/A | Planned June 20 | Planned Dec 21
Slits | Cleared | Cleared | Planned Oct 19 | N/A | Planned Dec 19 | Planned Dec 21
Sample Stack | Now | Planned Oct 19 | N/A | N/A | Planned Feb 20 | Planned May 21
Instrument Cabin | Cleared | Cleared | N/A | N/A | Planned Oct 19 | Planned Jan 20

## Slide 6
The spectrometer tank
- Small but complicated
Vacuum tank should house 45 analysers, scattering neutrons onto the 3-stagger arrangement of detectors on the tank floor. Came in below budget

## Slide 7
The spectrometer tank
- Small but complicated
Tank assembly includes
cross talk shielding
hatches for maintaining analysers
detectors mounted on the outside
Cadmium lining internally
Poly lining externally

## Slide 8
The spectrometer tank
- Small but complicated
PDR done, deformation FEM’s look good. Motion system looks fine

## Slide 9
Details, details…
PDR done, deformation FEM’s look good. Motion system looks fine

## Slide 10
Cave evolution

## Slide 11
Cave evolution

## Slide 12
Cave evolution

## Slide 13
1.2m concrete walls required to reduce peak radiation to 1.5uSv/hr
Need ground access for installation, maintenance and access to sample position
Need elevated access for sample changes
Roof access for auxiliary sample environment equipment
Moving hatch required to allow the removal of equipment
Use of ferrite materials must be minimised
Elevated Access
Ground Access
Moving Hatch
PSS Fence
Sample Environment Equipment
Cave got complicated

## Slide 14
Elevated labyrith

## Slide 15
Details

## Slide 16
Details
Due to the close collaboration with Rodion Kolevatov (IFE), we feel procurement ready, even though the design goals for caves changed in May.
We need our H1/H2 document approved to start validating our designs IFE very kindly accepted having the cave project being a cash contribution procured by ESS, due to VAT-issues. Allows us to move forward and hopefully have the cave installed April next year.

## Slide 17
Hutch
36 square meters, room for a small conference table and 3 large work stations, well insulated for noise reduction We hope for a nice working environment for once!

## Slide 18
Hutch
36 square meters, room for a small conference table and 3 large work stations, well insulated for noise reduction We hope for a nice working environment for once!
Having a hutch before everything else provides a HQ for installation
Nice to get out of way
Plenty of space in the E02 hall
Limited access in the E02 hall – no cranes
Needs construction on site

## Slide 19
Hutch installation
For installing the hutch we need:
General safety course for all workers
Danish company needs to be registered in Sweden for electrical work
Company needs to show compliance with EU directive EN-50110
Company electrician need 3 hour course in how ESS applies EN-50110
Risk Assessment and Methods Statement
Certificate of compliance for fuse box
We need sprinklers in the hutch (not part of our current scope)
Access and documentation requirements are overwhelming for many small and local companies, without compliance departments.

## Slide 20
Our triplet He-3 tubes is standard technology.
We got a quote from the ILL for the frontend electronics, slightly below budget
The ESS detector group requested us to use another ADC than provided by the ILL We accepted, but this involves moving the firmware, involving labor costs and risks.
We agree with the need for standardisation and easy maintenance. However, the detector electronics sub-project ad budget is not too well defined.
We still need to test the durability of He-3 tubes under intense bursts
Detectors

## Slide 21
TA’s are problematic
BIFROST have 5 partners, and we have to deal with 5 legal departments, interpreted by 5 scientists
VAT issues above our paygrade
TA’s on the critical path: Milestones now change every time signatures are delayed
DTU signed the contract for the tank before having signed TA’s and S&S IFE agreed to have the cave become a cash contribution, procured by ESS Thanks, DTU and IFE!
We are heavily affected by the PSI VAT problem, currently on critical path – guide and HOPG needs to be ordered ASAP.
Illustrative example – from TA: ”The required technical data package to be provided at TG5, SAR, is described in [TG5D]”

## Slide 22
TA’s are problematic
BIFROST have 5 partners, and we have to deal with 5 legal departments, interpreted by 5 scientists
VAT issues above our paygrades.
TA’s on the critical path: Milestones that change every time signatures are delayed
DTU signed the contract for the tank before having signed TA’s and S&S IFE agreed to have the cave become a cash contribution, procured by ESS Thanks, DTU and IFE!
We are heavily affected by the PSI VAT problem, currently on critical path – guide and HOPG needs to be ordered ASAP.
Illustrative example – from TA: ”The required technical data package to be provided at TG5, SAR, is described in [TG5D]”

## Slide 23
Safety and cave licensing
Argon activation might pose a problem
Sprinklers still an open question.
Cave is complicated, we can’t model every brick in MCNP. Assumptions have to be made
PSS, magnet activation, hazard analysis couples with cave design

## Slide 24
Summary
We are progressing on some fronts, on budget so far, but major procurements are yet to be made. Exciting times.
Major procurements will be done simulataneously, and installation will be hectic.
We need the TA’s done soon, to avoid delays, and to focus on delivering the instrument.
It is satisfying to get into the details, and it will be great to see equipment installed in less than a year!

## Slide 25
Thank you for your attention
Thanks to the large Bifrost team:
Finn Saxild (DTU)
Sylvain Rodrigues (LLB)
Rodion Kolevatov (IFE)
Jonas Okkels Birk (KU)
Philippe Bourges (LLB)
Niels Bech Christensen (DTU)
Kim Lefmann (KU)
Henrik Rønnow (EPFL)
Christof Niedermayer (PSI)
Felix Groitl (PSI)
Isabel Llamas (IFE)
Bjørn Hauback (IFE)
Christof Frommen (IFE)
Marko Marton (Wigner)
Keld Theodor (KU)
Liam Whitelegg (DTU)