## Slide 1: Common Shielding Project Update and Interfaces
Ken Andersen, Zvonko Lazic, Senad Kudumovic, Valentina Santoro
IKON-17
Lund, 10th September 2019

## Slide 2: Instrument Overview
Instrument | Beamport | SS cost | Quote | Partner | Payment | Neutronics work | Engineering design | Procurement
NMX | W1 |  | 1300 | Wigner | cash | Preliminary design ongoing | Preliminary design completed | Group 3
BEER | W2 | 1885 | 1310 | NPI | cash | Preliminary design completed | Preliminary design completed | Group 2
CSPEC | W3 | 1344 | 1340 | TUM | in-kind | Detailed design ongoing | Detailed design ongoing | Group 1
BIFROST | W4 | 1667 | 1165 | IFE | cash | Detailed design ongoing | Detailed design ongoing | Group 1
MIRACLES | W5 | 1109 | 1400 | ESS-Bilbao | cash | Preliminary design ongoing | Preliminary design completed | Group 3
MAGIC | W6 | 952 | 1130 | LLB | cash | Detailed design ongoing | Detailed design ongoing | Group 1
T-REX | W7 | 1686 | 1400 | CNR | ? | Preliminary design completed | Preliminary design completed | Group 3
HEIMDAL | W8 | 2070 | 1290 | IFE | cash | Preliminary design completed | Preliminary design completed | Group 3
ODIN | S2 | 1887 | 490 | TUM | in-kind | Preliminary design completed | Detailed design ongoing | Group 2
DREAM | S3 | 996 | 590 | LLB | cash | Preliminary design completed | Detailed design ongoing | Group 2
VESPA | E7 | 2221 | 900 | CNR | cash | Preliminary design ongoing | Preliminary design completed | Group 3
Quote in italics: working number, no price offer yet

## Slide 3: Neutronics Status
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA

## Slide 4: Neutronics Status
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA
Preliminary neutronics design complete for all except NMX, MIRACLES, VESPA
  has allowed price offers to be made for all others
Last price offers to be made by end-October

## Slide 5: Neutronics Status
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA
Preliminary neutronics design complete for all except NMX, MIRACLES, VESPA
  has allowed price offers to be made for all others
Last price offers to be made by end-October
Neutronics validation of detailed engineering design ongoing for Group 1

## Slide 6: Neutronics Status
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA
Preliminary neutronics design complete for all except NMX, MIRACLES, VESPA
  has allowed price offers to be made for all others
Last price offers to be made by end-October
Neutronics validation of detailed engineering design ongoing for Group 1
Group 2 next in line for neutronics validation of detailed engineering design

## Slide 7: Neutronics Status
Organisation of the work
Group 1 | Neutronics
CSPEC | Florian Grünauer
BIFROST | Rodion Kolevatov
MAGIC | Florian Grünauer
Group 2 | Neutronics
BEER | Jaroslav Šoltés
ODIN | Florian Grünauer
DREAM | Tsito Randriamalala
Group 3 | Neutronics
NMX | Szabina Török
MIRACLES | Miguel Magán
T-REX | Tsito Randriamalala
HEIMDAL | Rodion Kolevatov
VESPA | Jimmy Scionti
Weekly meetings organized and chaired by Valentina Santoro
  status updates
  allocation of tasks
  exchange of information

## Slide 8: Neutronics Status
Current hot topic: gamma emission from supermirrors
For guides out of line of sight, the shielding need is dominated by gamma emission from supermirrors
For typical Ni-Ti supermirror: ~0.9 photons/capture with MeV
Difficult to evaluate within neutronics Monte Carlo, e.g. MCNP, PHITS
  deficiencies in implementation of supermirror physics
Algorithm developed by Rodion Kolevatov provides good description
  use as benchmark for approved Monte Carlo packages
  needs experimental verification for formal approval (TG5)
Implementation in MCNP and PHITS by reflection card
Recent implementation in MCNP6 by Miguel Magán
  agrees well with Rodion’s calculations
  used for design of MIRACLES shielding
Need to benchmark various methods and make them available to all
Need to perform experimental verification
  planned at Budapest research reactor
R. Kolevatov et al., NIM A 922 (2019) 98—107.

## Slide 9: Neutronics Status
Recent Achievements
Chunk lengths [cm] | 1500 - 2500 | 2500 - 3500 | 3500 - 4500 | 4500 - ~5600
Concrete thickness [cm] | 90 | 80 | 70 | 60
Florian Grünauer: CSPEC
  computed the impact of shifting the upper blocks up due to gamma dose rates
Jimmy Scionti: VESPA
  neutron dose maps from the bunker wall to the cave
Miguel Magán: MIRACLES
  neutron dose map outside bunker wall

## Slide 10: Engineering Status
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA

## Slide 11: Engineering Status
Group 1
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA
Initial detailed design complete
Drawings sent out to all three instruments for neutronic validation

## Slide 12: Engineering Status
CSPEC
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA
Upper shielding blocks now lifted 50mm to accommodate adjustment features
Lower blocks made 100mm wider to compensate, following neutronics calculations
Chopper pit design: awaiting chopper design
Instrument interface: awaiting cave design

## Slide 13: Engineering Status
BIFROST
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA
Neutronic validation complete up to shutter pit, resulting in some changes to design.
Awaiting neutronic validation for rest, including chopper pit
Cave interface agreed: stainless steel insert in cave
Position of vacuum feed-throughs TBD

## Slide 14: Engineering Status
MAGIC
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA
Drawings sent out for neutronic validation
Cave interface and to be defined and agreed
Position of vacuum feed-throughs to be defined

## Slide 15: Engineering Status
Group 2
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA
BEER:
  Conceptual design ready but missing drawings for neutronic validation
ODIN:
  Conceptual design ready and communicated
  Drawings for neutronic design submitted
DREAM:
  Conceptual design ready and communicated
  Drawings for neutronic design submitted
ODIN
DREAM

## Slide 16: Procurement plan
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA

## Slide 17: Procurement plan
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA
Request For Quotation out for bottom shielding blocks in E02.1
RFQ

## Slide 18: Procurement Plan
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA
Tender
Call for tender out for all shielding: fixed price for Group 1 (detailed design sufficiently complete)
unit prices for Group 2
Fixed
price
Unit
price

## Slide 19: Procurement Plan
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Group 3
NMX
MIRACLES
T-REX
HEIMDAL
VESPA
Tender
Call for tender out for all shielding: fixed price for Group 1 (detailed design sufficiently complete)
unit prices for Group 2
Fixed
price
Unit
price
Unit
price
Can be added to first order, at same unit price – one at a time OK
Can be subject to new tender – should be grouped

## Slide 20: Procurement plan
Group 1
CSPEC
BIFROST
MAGIC
Group 2
BEER
ODIN
DREAM
Delivery
Release RFQ for E02.1 lower blocks for Group 1
Release tender for Groups 1 and 2
Contract signed
Design 4 man.
Production lot 1
Select contractor & order
Design 4 man.
Production
Delivery and inst.
Delivery
Production lot 2
Production lot...
Delivery
02.Sep.
20-30.Sep.
Oct.-Nov.
Nov.-Dec.
Dec. ‘19-Jan.’20
15.Aug.’19
15.-30.Sep.
Oct.-Dec. ‘19
Oct.-Dec. ‘19
Feb.-June ‘20

## Slide 21: Tollgate Process and Documentation
Needed from instruments:
  Up-to-date Concepts of Operations
  Up-to-date H1-H2 scenario analysis
  Instrument-specific requirements relating to guide shielding
Common Shielding Project will provide (in time for TG3):
  shielding analysis
  activation analysis (not including waste analysis)
  radiation hazard analysis
  conventional hazard analysis
  Sub-system design description, detailing PBS, including technical risk analysis
  Sub-system interface description – mainly an integration drawing showing interfaces: floor, bunker, cave, neighbours
  System integration and verification plan (installation and cold commissioning) – preliminary level (finalise for TG4)
  System validation plan (hot commissioning) – preliminary level (finalise for TG5)
  Systems operations and maintenance plan – preliminary level (finalise for TG5)
We provide the content, the instrument team then inserts it into the appropriate instrument-level document
We need to agree with each instrument on the timing of the various inputs
  a full-time document editor/coordinator is being arranged for the project

## Slide 22: Thank You!

## Slide 23: Supplementary slides

## Slide 24: Timeline
Installations
 |  | E02.1 | E02.2 | D03 | D01
Building handover |  | Aug-19 | May-21 | Jan-21 | Jun-21
CSPEC | Inst. start | Jun-20 | Jun-21 | Mar-21 | N.A.
 | Duration (weeks) | 3 | 3 | 3 | 
BIFROST | Inst. start | Jul-20 | Jul-21 | Apr-21 | N.A.
 | Duration (weeks) | 3 | 3 | 3 | 
MAGIC | Inst. start | Aug-20 | Aug-21 | May-21 | N.A.
 | Duration (weeks) | 3 | 3 | 3 | 
ODIN | Inst. start | N.A. | N.A. | N.A. | Jul-21
 | Duration (weeks) |  |  |  | 3
DREAM | Inst. start | N.A. | N.A. | N.A. | Aug-21
 | Duration (weeks) |  |  |  | 5

## Slide 25: Timeline
Design

## Slide 26: Timeline
Procurement and Manufacturing