## Slide 1
Status of TS2 Infrastructure preparation
Wolfgang Hees WP Leader TS2
TAC 2019-04-02

## Slide 2
bunker
lights & power
PSS
modulator
cryomodule
building
HVAC
valve
box
LTS2
cryo distribution
TICP
cryoplant
controls cabling
LLRF
controls
vacuum pumps &
clean room
CWM
cooling water
water
substation
electrical substation
power cabling
klystron
access cage
concrete door
klystron
RF distribution
RF distribution
SRF measurement
coupler cooling circuit
prep station
comp. air
racks
timing system
motion control
W. Hees
E. Asensi
WP11
WP11
WP11
WP16
ICS
WP10
ICS
ICS
WP15
WP15
SRF
WP8
WP8
WP8
WP8
WP17
WP15
CF
WP5
WP8
WP10
WP10
WP15
CF
CF
WP12
WP16
WP16
CF
2019-03-20
RAD monitoring
ES&H
Test Stand 2 system overview

## Slide 3
bunker
lights & power
PSS
modulator
cryomodule
building
HVAC
valve
box
LTS2
cryo distribution
TICP
cryoplant
controls cabling
LLRF
controls
vacuum pumps &
clean room
CWM
cooling water
water
substation
electrical substation
power cabling
klystron
access cage
concrete door
klystron
RF distribution
RF distribution
SRF measurement
coupler cooling circuit
prep station
comp. air
racks
timing system
motion control
W. Hees
E. Asensi
WP11
WP11
WP11
WP16
ICS
WP10
ICS
ICS
WP15
WP15
SRF
WP8
WP8
WP8
WP8
WP17
WP15
CF
WP5
WP8
WP10
WP10
WP15
CF
CF
WP12
WP16
WP16
CF
2019-03-20
RAD monitoring
ES&H
completed
Test Stand 2 system overview

## Slide 4: TS2 progress
Progress has been made in the main sub-projects of TS2:
Cryogenics:
  commissioning and acceptance of TICP
  completion of installation of CDS, commissioning in progress
Controls: integration of instrumentation, panels
Utilities:
  powering of HV
  start of cooling water operation
Bunker: completion of main structure
SRF: prep station installed and equipped
Licencing: TS2a licence application sent
Vacuum: delivery of all major pieces of equipment
PSS: CDR, start of installation
RF: 

## Slide 5: TS2 schedule

## Slide 6: TS2 RF Activities
SAT of CPI prototype klystron
  repetition of all FAT tests
  new E-bend at the klystron output to solve the phase non-monotinicity issue
  integration of MicroStep type arc detector at the klystron output
Test of new SS driver amplifier (for MB series klystrons)
Test of new interface boards for the interlock system
Stepper motor controller for the RF variable power dividers (VPD) provided by ICS
RF signal level test of VPD
One VPD installed

## Slide 7: RF distribution components high power tests
CPI klystron with max. output power (~1.5 MW) used for testing of components and imperfections:
  WR1150 RF window
  WR1150 bellow
  Different types of anomalies inside of the waveguides
    deep scratches in the walls, including long burrs
    welding residual bumps in the corners
    foreign object (steel nut) moved around
    flange misalignment
The tests confirmed that all of these imperfections are RF tolerant.