## Slide 1: THE STATE OF BEAM DIAGNOSTICS
Tom Shea
for the ESS Beam Diagnostics Team

## Slide 2: Organization
>20 Partners and Collaborators
System Leads
Rafael Baron
Clement Derrez
Elena Donegani
Hooman Hassanzedagen
Irena Dolenc Kittelmann
Roxana Tarkeshian
Cyrille Thomas
Aarhus University
CEA Saclay, Paris
CERN, Geneva
Cockcroft Institute, Daresbury
DESY, Hamburg
Elettra – Sincrotrone Trieste
ESS Bilbao
INFN, Catania
INFN, Legnaro
Lund University
University of Oslo
DTU, Denmark
STFC, Daresbury
WUT, Warsaw
Lodz U. of Technology, Lodz
Chinese ADS
J-PARC, Japan
ORNL, USA
LANL, USA
IHEP, Russia
INR, Moscow
Högskola Väst, Trollhättan
Stony Brook U., New York
BNL, New York
Technical Team
All system leads contribute technical expertise
In addition:
Edvard Bergman
Thomas Grandsaert
Slava Grishin
Maria Hoflund
Hinko Kocevar
Mehdi Mohammednezhad
Johan Norin
Kaj Rosengren
At ESS Lund, the team consists of staff, consultants, students, and matrixed staff
Lead system design and deployment
Cover all technical disciplines
Tom Shea

## Slide 3: System Leads Updated
System | System Lead
Aperture Monitor(fixed and moveable) | Cyrille Thomas
BCM (BCM, fast BCM, IS supply current) | Hooman Hassanzadegan
BLM (nBLM, ICBLM, X-Ray spectroscopy) | Irena Dolenc Kittelmann
BPM (BPM, fast BPM) | Rafael Baron
Doppler | Cyrille Thomas
EMU (Alison, slit-grid) | Roxana Tarkeshian
FC | Elena Donegani
Imaging | Cyrille Thomas
Insertable Beam Stops | Elena Donegani
LBM (BSM) | Irena Dolenc Kittelmann
NPM (IPM, BIF) | Roxana Tarkeshian
Scraper(MEBT) | Cyrille Thomas
Target Grid | Cyrille Thomas
WS(scanning, fast) | Clement Derrez
https://confluence.esss.lu.se/display/BIG/Organization+of+Beam+Diagnostics

## Slide 4: Technical Leads (same as 2018, but updates are in progress)
Technical Area | Responsible
Cabling | Edvard Bergman
Commissioning (LEBT) | Cyrille Thomas
Data Management | Johan Norin
Electronics | Clement Derrez, Hooman Hassanzadegan
FPGA, digital architecture | Kaj Rosengren
Installation Manager | Viatcheslav Grishin
Laboratory Manager | Edvard Bergman
Mechanical | Thomas Grandsaert
Motion Control | Clement Derrez
Project Planning | Johan Norin
Protection | Irena Dolenc Kittelmann, Thomas Grandsaert
Radiation effects | Irena Dolenc Kittelmann ,Elena Donegani
Software, EPICS integration | Hinko Kocevar
Verification | Clement Derrez
https://confluence.esss.lu.se/display/BIG/Organization+of+Beam+Diagnostics

## Slide 5: Personnel news in Lund
Maria Hoflund
  Returned and completed Master thesis
  Off to Lund University for PhD
Roxana Tarkeshian
  Arrived in Diagnostics Scientist position
  EMU, NPM System lead
Rafael Baron
  Returned from academic leave
  BPM system lead
  Electronics, EMC
Henrique
  accepted Technician position

## Slide 6: Accelerator Controls Program Forum
BI resources in place, partners delivering, but…
Still impacted by limited ICS resources, both labor and non-labor
Too late to fully recover
We needed a way to support deployment for commissioning with limited resources
Focus on “first proton functionality”, prioritized by stakeholders across the organization

## Slide 7: Proposal developed with ICS
Manage objectives across teams
  We have a plan in P6. We manage execution with team boards containing detailed tasks.
  Focus on first proton functionality: Features, not systems - Avoid a priori rejection of entire measurement systems
    Take advantage of remaining flexibility to prioritize features for first protons
Tighten communications
  The most successful diagnostics projects have been executed by multidisciplinary teams that integrate early: (Examples: J-PARC experiment, BPM, …)
  Take a more lean approach to documentation and procedures. Rely on data, intra-team communications.
On same project team
Probability of effective communication
~2 weeks
Many Team Boards
One Program Board
P6 Plan (Milestones, Earned Value)
Physical separation
Add a program board that contains the objectives
Add a program forum that periodically prioritizes and agrees on objectives. Includes ICS, Diagnostics, Ops, Linac group, and other key stakeholders.*
~2 months

## Slide 8: Accelerator Controls Program Board
The program objectives are Jira issues in the CAP project
Anybody can suggest
99 Suggested
Experts analyze
Managers decide what to do
Every 2 months, program forum agrees what to do next
Managers accept results
In Diagnostics: system leads choose objectives to analyze

## Slide 9: Example objective

## Slide 10: FBS – Functional Breakdown Structure
The FBS is a database that contains a functional breakdown of ESS. Nodes can be both systems and components.
FBS-nodes are referred to as “positions” in EAM.
FBS node Description
ESS ESS
ESS.ACC Accelerator
ESS.ACC.B01 Proton Beam Instrumentation Systems
ESS.ACC.B01.B03 Wire Scanners
ESS.ACC.B01.B03.B02 Control Group ’PBI WS-02’ (Spoke wire scanners)
ESS.ACC.B01.B03.B02.B01 SPK WS1 diagnostic system (Spk-020LWU:PBI-WS-001)
ESS.ACC.B01.B03.B02.B01.B02 SPK WS1 horizontal beamline device

## Slide 11: FBS – Functional Breakdown Structure
A position (FBS node) can be identified with an ESS name or a cable name, but the FBS is a much larger structure. Most of the system level FBS nodes (the ‘skeleton’ of the structure) does not have ESS names.
Assets can be assigned to FBS nodes in EAM.
Present count:
 | ESS | PBI | Comment
ESS names | 41722 | 2841 | 
Cables | 28649 | 2672 | Only the NCL cables are added to FBS so far.
FBS nodes | 75673 | 4497 | 
Assets in EAM | 4220 | 858 | 

## Slide 12: Schedule
This table contains some key accelerator milestones that affect beam instrumentation (2019-10-22)
Beam Section | Beam line installation completed | SRR | Start of comissioning | End of commisioning
Up to DTL1 | 2020-03-13 | 2020-04-29 (SRR2) | 2020-05-15 | 2020-08-07
Up to DTL4 | 2020-11-05 | 2020-11-19 (SRR3) | 2021-01-13 | 2021-04-19
Beam on dump | 2021-06-10 | 2021-09-16 (SRR4) | 2021-09-24 | 2021-11-30
Beam on target | 2021-06-10 | 2021-11-30 (SRR5) | 2021-12-01 (RBOT) | 

## Slide 13: Naming tool and FBS History – Development
Original
Level 1: Instrument types
Level 2: Individual instruments
Now
Level 1: Instrument type (e.g. Beam current monitors)
Level 2: Control group (All equipment that is controlled and powered together)
Level 3: Individual diagnostic systems (e.g. LEBT BCM), Control systems in rack
Level 4: Beam line elements, Rack mounted crates, Cables
Level 5: Sub-components (e.g. uTCA-mounted cards)
Can have assets

## Slide 14: WP7 Status – October 2019
WP 7 construction and installation project is around 70 % done.
Much of the remaining material cost for construction is tied to end-of construction milestones and a few large deliveries.
There will be a substantial decrease in burn rate in 2020 due to transfers to the initial operation budget.
Chart: WP7 - October 2019
| IK | Construction | Installation
Present | 6170174 | 12241896 | 351020
Remaining | 2359340 | 3136164 | 2509880

## Slide 15: Putting the systems together
Acquisition
Analysis
Low latency processing
Single input functions Continuous buffering
Trigger annunciation
Updates to analysis layer managed by trigger system
Gigabit/s
Acquisition
Acquisition
Multi input Control and
Protection functions Low latency data link
Data analysis Machine learning
Adaptation
Machine
Actuators
Terabit/s
trig
trig

## Slide 16
2002
2003
2004
2005
2006
2
1
4
3
5
7
8
9
6
2019
2018
2017
Source/
LEBT
RFQ/MEBT/DTL1
DTL 2-4
DTL5
+ Spokes
+ Medium Beta
SNS
ESS
Source/LEBT at Catania
Elliptical
Deployment at scale: superconducting linac devices
DTL 1
MEBT
improve
improve
2020
2021
2022
In years past, the ESS plan appeared too aggressive.
In 2018, it looked achievable and similar to RHIC and SNS.
Now, the pace appears slow
To target
Comparison

## Slide 17: 2019 Goals
Explicitly linked goals of diagnostics to overall goals of ESS

## Slide 18: Focus Areas for 2019 (copied from 2018 presentation)
Deploy normal-conducting linac diagnostic systems [ongoing, slow start]
Wrap up most prototype testing and remaining design reviews [ongoing]
Project management
  Biggest issue: Projected budget gap of 2 to 5% [projected gap remains]
  Soliciting ideas for cost savings/deferral
Technical
  V 1.0 firmware and software architecture [see FPGA and system presentations]
  Data on demand [firmware implemented]
  Timing integration [soon]
  MPS integration [firmware implemented]
  Low latency link [firmware implemented]

## Slide 19: Focus Areas for 2020 (builds on 2019)
Normal-conducting linac deployment (still)
Enter fabrication and installation phase for remaining systems
Evolve the organization to support commissioning and operations
  System lead team to collectively own diagnostics suite.
  Technical team(s) to consolidate and improve underlying components
Data (full stack)
  Integrate components like DoD, timing, links, etc into data acquisition solution
  Common data exchange format (Clement) for verification. Also beam tests, machine studies
  Data analysis, visualization, machine learning (Irena)
  Requires collaboration: within diagnostics, beam physics, ops, controls, DMSC, ... SNS, …

## Slide 20
thanks