## Instrument Project Summary
| 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
west sector
BEER | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2 | 2.5 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
CSPEC | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
TREX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
HIEMDAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
NMX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
BIFROST | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
MAGIC | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 2.5 | 2.5 | 2.5 | 3 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Miracles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5
North Sector
LOKI | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 2 | 2 | 2.5 | 2.5 | 2 | 2.5 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
FREIA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5
SOUTH & East Sector
ODIN | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
DREAM | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
ESTIA | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 2 | 2.5 | 2.5 | 2 | 2.5 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
SKADI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Total FTE allocated to instruments projects | 0 | 0 | 0 | 4 | 4 | 4 | 6.5 | 8 | 8 | 11.5 | 15 | 20 | 20 | 18.5 | 20.5 | 16 | 16 | 15 | 11.5 | 9.5 | 11 | 15 | 15.5 | 17 | 18 | 17 | 17 | 15 | 15 | 9.5 | 9.5 | 9 | 9 | 7 | 7 | 7 | 7
Total dmsc staff profile | 30 | 38 | 40 | 42 | 42 | 46 | 46 | 46 | 46 | 50 | 50 | 50 | 50 | 50 | 52 | 52 | 52 | 53 | 54 | 54 | 54 | 55 | 55 | 55 | 55 | 56 | 56 | 56 | 56 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
Staff in data reduction and DAQ and controls | 17 | 23 | 24 | 24 | 24 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 31 | 31 | 31 | 31 | 34 | 34 | 34 | 34 | 35 | 35 | 35 | 35
Data analysis suport | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
Staff woking on core scope deferen from construction | 2019 Q4: 17; 2020 Q1: 23; 2020 Q2: 24; 2020 Q3: 20; 2020 Q4: 20; 2021 Q1: 22; 2021 Q2: 19.5; 2021 Q3: 18; 2021 Q4: 18
Staff for core development during installation and commsioing phase | 2022 Q1: 14.5; 2022 Q2: 11; 2022 Q3: 6; 2022 Q4: 6; 2023 Q1: 7.5; 2023 Q2: 5.5; 2023 Q3: 10; 2023 Q4: 10; 2024 Q1: 12; 2024 Q2: 15.5; 2024 Q3: 17.5; 2024 Q4: 16; 2025 Q1: 13; 2025 Q2: 12.5; 2025 Q3: 11; 2025 Q4: 10; 2026 Q1: 14; 2026 Q2: 14
Staff for reduction and analysis support and sceince programe support & delivary | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 7.5 | 9.5 | 8 | 6 | 5.5 | 4 | 3 | 5 | 5 | 7 | 7 | 15.5 | 15.5 | 16 | 16 | 20 | 20 | 20 | 20
Project Staff in Lund at 70% | 0 | 0 | 0 | 2.8 | 2.8 | 2.8 | 4.55 | 5.6 | 5.6 | 8.05 | 10.5 | 14 | 14 | 12.95 | 14.35 | 11.2 | 11.2 | 10.5 | 8.05 | 6.65 | 7.7 | 10.5 | 10.85 | 11.9 | 12.6 | 11.9 | 11.9 | 10.5 | 10.5 | 6.65 | 6.65 | 6.3 | 6.3 | 4.9 | 4.9 | 4.9 | 4.9

## DMSC STAFF Summary
DMSC staff profile summary roles, location and instrument projects
|  | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
|  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
DMSC P6 Staff plan | Data Redudction and Data Analysis | 10 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 18 | 18 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | These numbers are taken from the current p6 initial operations staff plan for DMSC. In steady state ops the FTE count is 59. Here I only consider the first tranche of instruments so tructate at 2024
| Modeling and Simulation | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| Management and Administration | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| User Office system development | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3
| Experimemnt Control and Data curation | 7 | 11 | 11 | 11 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15
| Data Systems and Technology | 7 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Total planed P6 | 30 | 38 | 40 | 42 | 42 | 46 | 46 | 46 | 46 | 50 | 50 | 50 | 50 | 50 | 52 | 52 | 52 | 53 | 54 | 54 | 54 | 55 | 55 | 55 | 55 | 56 | 56 | 56 | 56 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
| Technical groups | 17 | 23 | 24 | 24 | 24 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 31 | 31 | 31 | 31 | 34 | 34 | 34 | 34 | 35 | 35 | 35 | 35
| Simulation & analysis | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| User office | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3
DMSC support in Lund for User programme operations | User office develkopment Lund Support | 2019 Q4: 0; 2020 Q1: 0; 2020 Q2: 0; 2020 Q3: 0; 2020 Q4: 0; 2021 Q1: 0; 2021 Q2: 0; 2021 Q3: 0; 2021 Q4: 0; 2022 Q1: 1; 2022 Q2: 1; 2022 Q3: 1; 2022 Q4: 1; 2023 Q1: 1; 2023 Q2: 1; 2023 Q3: 1; 2023 Q4: 1; 2024 Q1: 1; 2024 Q2: 1; 2024 Q3: 1; 2024 Q4: 1 | These staff cover DMSC support activities that are not sepcific to any particular instrument. Noteably the user office software system and modeling and simulation support for the instruments in the user programme
| Management | 2019 Q4: 0.5; 2020 Q1: 0.5; 2020 Q2: 0.5; 2020 Q3: 0.5; 2020 Q4: 0.5; 2021 Q1: 0.5; 2021 Q2: 0.5; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.5
| Modelling and simulation Lund Support | 2019 Q4: 0; 2020 Q1: 0; 2020 Q2: 0; 2020 Q3: 0; 2020 Q4: 0; 2021 Q1: 0; 2021 Q2: 0; 2021 Q3: 0; 2021 Q4: 0; 2022 Q1: 0; 2022 Q2: 0; 2022 Q3: 0; 2022 Q4: 0; 2023 Q1: 0; 2023 Q2: 0; 2023 Q3: 1; 2023 Q4: 1; 2024 Q1: 1; 2024 Q2: 1; 2024 Q3: 1; 2024 Q4: 1
| Total for UP support in Lund | 2019 Q4: 0.5; 2020 Q1: 0.5; 2020 Q2: 0.5; 2020 Q3: 0.5; 2020 Q4: 0.5; 2021 Q1: 0.5; 2021 Q2: 0.5; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 1.5; 2022 Q2: 1.5; 2022 Q3: 1.5; 2022 Q4: 1.5; 2023 Q1: 1.5; 2023 Q2: 1.5; 2023 Q3: 2.5; 2023 Q4: 2.5; 2024 Q1: 2.5; 2024 Q2: 2.5; 2024 Q3: 2.5; 2024 Q4: 2.5
DMSC staff NSS project meetings | Data Redudction and Data Analysis | 2019 Q4: 0.8; 2020 Q1: 0.8; 2020 Q2: 0.8; 2020 Q3: 0.8; 2020 Q4: 0.8; 2021 Q1: 0.8; 2021 Q2: 0.8; 2021 Q3: 0.8; 2021 Q4: 0.8; 2022 Q1: 0.8; 2022 Q2: 0.8; 2022 Q3: 0.8; 2022 Q4: 0.8; 2023 Q1: 0.8; 2023 Q2: 0.8; 2023 Q3: 0.8; 2023 Q4: 0.8; 2024 Q1: 0.8; 2024 Q2: 0.8; 2024 Q3: 0.8; 2024 Q4: 0.8 | These staff numbers are indicative of the current level of DMSC staff presenece in Lund to cover project meetings and planning. They are an indiaction of how the group leaders and some staff currently work
| User Office system development | 2019 Q4: 0.2; 2020 Q1: 0.2; 2020 Q2: 0.2; 2020 Q3: 0.2; 2020 Q4: 0.2; 2021 Q1: 0.2; 2021 Q2: 0.2; 2021 Q3: 0.2; 2021 Q4: 0.2; 2022 Q1: 0.2; 2022 Q2: 0.2; 2022 Q3: 0.2; 2022 Q4: 0.2; 2023 Q1: 0.2; 2023 Q2: 0.2; 2023 Q3: 0.2; 2023 Q4: 0.2; 2024 Q1: 0.2; 2024 Q2: 0.2; 2024 Q3: 0.2; 2024 Q4: 0.2
| Experimemnt Control and Data curation | 2019 Q4: 0.5; 2020 Q1: 0.5; 2020 Q2: 0.5; 2020 Q3: 0.5; 2020 Q4: 0.5; 2021 Q1: 0.5; 2021 Q2: 0.5; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.5
| Data Systems and Technology | 2019 Q4: 0.2; 2020 Q1: 0.2; 2020 Q2: 0.2; 2020 Q3: 0.2; 2020 Q4: 0.2; 2021 Q1: 0.2; 2021 Q2: 0.2; 2021 Q3: 0.2; 2021 Q4: 0.2; 2022 Q1: 0.2; 2022 Q2: 0.2; 2022 Q3: 0.2; 2022 Q4: 0.2; 2023 Q1: 0.2; 2023 Q2: 0.2; 2023 Q3: 0.2; 2023 Q4: 0.2; 2024 Q1: 0.2; 2024 Q2: 0.2; 2024 Q3: 0.2; 2024 Q4: 0.2
| Total | 2019 Q4: 1.7; 2020 Q1: 1.7; 2020 Q2: 1.7; 2020 Q3: 1.7; 2020 Q4: 1.7; 2021 Q1: 1.7; 2021 Q2: 1.7; 2021 Q3: 1.7; 2021 Q4: 1.7; 2022 Q1: 1.7; 2022 Q2: 1.7; 2022 Q3: 1.7; 2022 Q4: 1.7; 2023 Q1: 1.7; 2023 Q2: 1.7; 2023 Q3: 1.7; 2023 Q4: 1.7; 2024 Q1: 1.7; 2024 Q2: 1.7; 2024 Q3: 1.7; 2024 Q4: 1.7
DMSC staff allocated to instrument projects installation and commsioning | Experimemnt Control and Data curation | 2019 Q4: 0; 2020 Q1: 0; 2020 Q2: 0; 2020 Q3: 0; 2020 Q4: 0; 2021 Q1: 0; 2021 Q2: 2.5; 2021 Q3: 4; 2021 Q4: 4; 2022 Q1: 4; 2022 Q2: 4; 2022 Q3: 8; 2022 Q4: 8; 2023 Q1: 8; 2023 Q2: 8; 2023 Q3: 4; 2023 Q4: 4; 2024 Q1: 1.5; 2024 Q2: 1.5; 2024 Q3: 2; 2024 Q4: 2 | These staff numbers indicate the level of staff cover required for delivary of the instruments according to the latest rebaselined NSS schedule. The level of effort is commensurate with that at other facilities and absoulutely required if ESS is going to deliver 3 instruments into a credible user programme
| Redudction Analysis & Modelling | 2019 Q4: 0; 2020 Q1: 0; 2020 Q2: 0; 2020 Q3: 4; 2020 Q4: 4; 2021 Q1: 4; 2021 Q2: 4; 2021 Q3: 4; 2021 Q4: 4; 2022 Q1: 5; 2022 Q2: 7.5; 2022 Q3: 8; 2022 Q4: 8; 2023 Q1: 8.5; 2023 Q2: 12; 2023 Q3: 12; 2023 Q4: 12; 2024 Q1: 13.5; 2024 Q2: 10; 2024 Q3: 6; 2024 Q4: 7.5
| Data Systems and Technology | 2019 Q4: 0; 2020 Q1: 0; 2020 Q2: 0; 2020 Q3: 0; 2020 Q4: 0; 2021 Q1: 0; 2021 Q2: 0; 2021 Q3: 0; 2021 Q4: 0; 2022 Q1: 2.5; 2022 Q2: 3.5; 2022 Q3: 4; 2022 Q4: 4; 2023 Q1: 2; 2023 Q2: 0.5; 2023 Q3: 0; 2023 Q4: 0; 2024 Q1: 0; 2024 Q2: 0; 2024 Q3: 1.5; 2024 Q4: 1.5
| total allocated instrument projects | 2019 Q4: 0; 2020 Q1: 0; 2020 Q2: 0; 2020 Q3: 4; 2020 Q4: 4; 2021 Q1: 4; 2021 Q2: 6.5; 2021 Q3: 8; 2021 Q4: 8; 2022 Q1: 11.5; 2022 Q2: 15; 2022 Q3: 20; 2022 Q4: 20; 2023 Q1: 18.5; 2023 Q2: 20.5; 2023 Q3: 16; 2023 Q4: 16; 2024 Q1: 15; 2024 Q2: 11.5; 2024 Q3: 9.5; 2024 Q4: 11
| Total LOE in Lund assuming 70% occupancy | 2019 Q4: 1.54; 2020 Q1: 1.54; 2020 Q2: 1.54; 2020 Q3: 4.34; 2020 Q4: 4.34; 2021 Q1: 4.34; 2021 Q2: 6.09; 2021 Q3: 7.14; 2021 Q4: 7.14; 2022 Q1: 10.29; 2022 Q2: 12.74; 2022 Q3: 16.24; 2022 Q4: 16.24; 2023 Q1: 15.19; 2023 Q2: 16.59; 2023 Q3: 14.14; 2023 Q4: 14.14; 2024 Q1: 13.44; 2024 Q2: 10.99; 2024 Q3: 9.59; 2024 Q4: 10.64
| Available for Core development projects | 2019 Q4: 28.46; 2020 Q1: 36.46; 2020 Q2: 38.46; 2020 Q3: 37.66; 2020 Q4: 37.66; 2021 Q1: 41.66; 2021 Q2: 39.91; 2021 Q3: 38.86; 2021 Q4: 38.86; 2022 Q1: 39.71; 2022 Q2: 37.26; 2022 Q3: 33.76; 2022 Q4: 33.76; 2023 Q1: 34.81; 2023 Q2: 35.41; 2023 Q3: 37.86; 2023 Q4: 37.86; 2024 Q1: 39.56; 2024 Q2: 43.01; 2024 Q3: 44.41; 2024 Q4: 43.36
| Precent of DMSC staff in Lund | 2019 Q4: 5.1333; 2020 Q1: 4.0526; 2020 Q2: 3.85; 2020 Q3: 10.3333; 2020 Q4: 10.3333; 2021 Q1: 9.4348; 2021 Q2: 13.2391; 2021 Q3: 15.5217; 2021 Q4: 15.5217; 2022 Q1: 20.58; 2022 Q2: 25.48; 2022 Q3: 32.48; 2022 Q4: 32.48; 2023 Q1: 30.38; 2023 Q2: 31.9038; 2023 Q3: 27.1923; 2023 Q4: 27.1923; 2024 Q1: 25.3585; 2024 Q2: 20.3519; 2024 Q3: 17.7593; 2024 Q4: 19.7037

## DREAM
Dream
| Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
|  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
DREAM installation | ECDC control | 2019 Q4: C; 2020 Q1: C; 2020 Q2: C; 2020 Q3: C; 2020 Q4: C; 2021 Q2: 0; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5
| ECDC DAQ | 2019 Q4: C; 2020 Q1: C; 2020 Q2: C; 2020 Q3: C; 2020 Q4: C; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5
| RAG ID Sci |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Dream Hot comm | RAG reduction | 2019 Q4: C; 2020 Q1: C; 2020 Q2: C; 2020 Q3: C; 2020 Q4: C; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5
| RAG Analysis | 2019 Q4: C; 2020 Q1: C; 2020 Q2: C; 2020 Q3: C; 2020 Q4: C; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5
| DST | 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0
| Total |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| RAG Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## ODIN
| Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
|  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Odin installation | ECDC control | 2021 Q2: 0; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5
| ECDC DAQ | 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5
| RAG ID Sci |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
odin Hot comm | RAG reduction | 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5
| RAG Analysis | 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5
| DST | 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5
| ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| RAG Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## LOKI
Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECDC control | 2021 Q2: 0.5; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5
ECDC DAQ | 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5
RAG ID Sci |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
RAG reduction | 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5
RAG Analysis | 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5
DST | 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5
ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAG Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 2 | 2 | 2.5 | 2.5 | 2 | 2.5 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## CSPEC
Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECDC control | 2021 Q2: 0.5; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5
ECDC DAQ | 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5
RAG ID Sci |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
RAG reduction | 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5
RAG Analysis | 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5
DST | 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5
ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAG Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## BEER
Beer instrument
| Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
|  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| ECDC control | 2021 Q2: 0.5; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5
| ECDC DAQ | 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5
| RAG ID Sci |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| RAG reduction | 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5
| RAG Analysis | 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5
| DST | 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5
| ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| RAG Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2 | 2.5 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## BIFROST
Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECDC control | 2021 Q2: 0.5; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5
ECDC DAQ | 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5
RAG ID Sci |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
RAG reduction | 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5
RAG Analysis | 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5
DST | 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5
ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAG Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## MAGIC
Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECDC control | 2021 Q2: 0.5; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5
ECDC DAQ | 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5
RAG ID Sci |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
RAG reduction | 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5
RAG Analysis | 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5
DST | 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5
ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAG Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 2.5 | 2.5 | 2.5 | 3 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## ESTIA
Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECDC control | 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5
ECDC DAQ | 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5
RAG ID Sci |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
RAG reduction | 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5
RAG Analysis | 2023 Q2: 0.5; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q1: 0.5
DST | 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5
ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAG Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 2 | 2.5 | 2.5 | 2 | 2.5 | 2 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## NMX
Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECDC control | 2024 Q1: 0.5; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5
ECDC DAQ | 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5
RAG ID Sci | 2024 Q1: 0.5; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5; 2027 Q1: 0.5; 2027 Q2: 0.5; 2027 Q3: 0.5; 2027 Q4: 0.5; 2028 Q1: 0.5; 2028 Q2: 0.5; 2028 Q3: 0.5; 2028 Q4: 0.5
RAG reduction | 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5
RAG Analysis | 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5
DST | 2024 Q3: 0.5; 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0
ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAG Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Hiemdal
Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECDC control | 2024 Q1: 0.5; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5
ECDC DAQ | 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5
RAG ID Sci | 2024 Q1: 0.5; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5; 2027 Q1: 0.5; 2027 Q2: 0.5; 2027 Q3: 0.5; 2027 Q4: 0.5; 2028 Q1: 0.5; 2028 Q2: 0.5; 2028 Q3: 0.5; 2028 Q4: 0.5
RAG reduction | 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5
RAG Analysis | 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5
DST | 2024 Q3: 0.5; 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0
ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAG Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## TREX
Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECDC control | 2024 Q1: 0.5; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5
ECDC DAQ | 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5
RAG ID Sci | 2024 Q1: 0.5; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5; 2027 Q1: 0.5; 2027 Q2: 0.5; 2027 Q3: 0.5; 2027 Q4: 0.5; 2028 Q1: 0.5; 2028 Q2: 0.5; 2028 Q3: 0.5; 2028 Q4: 0.5
RAG reduction | 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5
RAG Analysis | 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5
DST | 2024 Q3: 0.5; 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0
ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAG Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## FREIA
Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECDC control | 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5
ECDC DAQ | 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5
RAG ID Sci | 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5; 2027 Q1: 0.5; 2027 Q2: 0.5; 2027 Q3: 0.5; 2027 Q4: 0.5; 2028 Q1: 0.5; 2028 Q2: 0.5; 2028 Q3: 0.5; 2028 Q4: 0.5 | 0.5 | 0.5 | 0.5 | 0.5
RAG reduction | 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5; 2027 Q1: 0.5; 2027 Q2: 0.5; 2027 Q3: 0.5; 2027 Q4: 0.5
RAG Analysis | 2026 Q4: 0.5; 2027 Q1: 0.5; 2027 Q2: 0.5; 2027 Q3: 0.5; 2027 Q4: 0.5
DST | 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0
ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAG Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## SKADI
Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECDC control | 2024 Q3: 0.5; 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5
ECDC DAQ | 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5
RAG ID Sci | 2024 Q3: 0.5; 2024 Q4: 0.5; 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5; 2027 Q1: 0.5; 2027 Q2: 0.5; 2027 Q3: 0.5; 2027 Q4: 0.5; 2028 Q1: 0.5; 2028 Q2: 0.5; 2028 Q3: 0.5; 2028 Q4: 0.5
RAG reduction | 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5
RAG Analysis | 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5
DST | 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0
ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAG Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## Miracles
Role | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECDC control | 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5
ECDC DAQ | 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5; 2027 Q1: 0.5; 2027 Q2: 0.5
RAG ID Sci | 2025 Q1: 0.5; 2025 Q2: 0.5; 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5; 2027 Q1: 0.5; 2027 Q2: 0.5; 2027 Q3: 0.5; 2027 Q4: 0.5; 2028 Q1: 0.5; 2028 Q2: 0.5; 2028 Q3: 0.5; 2028 Q4: 0.5 | 0.5 | 0.5 | 0.5 | 0.5
RAG reduction | 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0.5; 2027 Q1: 0.5; 2027 Q2: 0.5; 2027 Q3: 0.5; 2027 Q4: 0.5
RAG Analysis | 2026 Q4: 0.5; 2027 Q1: 0.5; 2027 Q2: 0.5; 2027 Q3: 0.5; 2027 Q4: 0.5
DST | 2025 Q3: 0.5; 2025 Q4: 0.5; 2026 Q1: 0.5; 2026 Q2: 0.5; 2026 Q3: 0.5; 2026 Q4: 0
ECDC Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
RAG Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5
DST Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5