## Slide 1: JÜLICH contribution (TIK3.1, TIK3.2, TIK4.1 and NBEX)
2019.09.12 I M. Butzek (Y. Beßler)
TCB / Copenhagen

## Slide 2: OUTLINE
Technical status
  Moderator & Reflector Plug -TIK3.1
  Cryogenic Moderator System -TIK3.2
  Target Monitoring Plug -TIK4.1
  Neutron beam extraction system
    Project 1 (Prototype phase)
    Project 2 (Test phase)
    Project 3 (NBPI series)
Contractual issues

## Slide 3: MRP TIK3.1
Twister overview
Moderator &
Reflector Unit
FAT setup 1
FAT setup 2
Twister ready
for delivery
Crown
Axial bearing
Shaft
Frame
Bucket
Rotation Unit
Manufacturing complete
Manufacturing in progress

## Slide 4: MRS TIK3.1
Twister components (Shaft)
forge the of Twister shaft
Twister shaft at FZJ
Twister shaft forged
Welded cooling channels

## Slide 5: MRS Components
Twister components (bearing / crown / bucket / frames)
Twister bucket and crown
Frame sheets water cuted
Axial bearing
Upper radial
bearing

## Slide 6: MRP TIK3.1
Moderator & Reflector Unit overview
Moderator &
Reflector Unit
FAT setup 1
Thermal Moderator
Beryllium Reflector
Vacuum jacket
Cold Moderators
Manufacturing complete
Manufacturing in progress
Irradiation Module

## Slide 7
Thermal Moderator
+ cold Moderators
+ Irradiation module
Thermal Moderator welding
and leak test
Cold
Moderator
Thermal Moderator
Position of irradiation module inside Thermal Moderator

## Slide 8: MRS TIK3.1
Reflector (Beryllium reflector)
Acceptance test (Moscow)
Beryllium assembly
TIC welding
Electron beam welding

## Slide 9: MRS TIK3.1
Schedule status and outlook
Sub unit | Final design | CDR | Manufacturing | FAT | delivery | SAT
Cold Moderator | . | . | . | . | 07-20 | n.a.
Thermal Moderator | . | . | . | 10-19 | 07-20 | n.a.
Beryllium Reflector | . | . | . | 10-19 | 07-20 | n.a.
Vacuum Jacket | . | . | 12-19 | 01-20 | 07-20 | n.a.
Crown | . | . | . | . | 07-20 | n.a.
Bucket | . | . | . | . | 07-20 | n.a.
Rotation Unit | . | . | . | . | 07-20 | n.a.
Shaft assembly (welded) | . | . | 11-19 | 12-19 | 07-20 | n.a.
Radial bearing | . | . | . | 10-19 | 07-20 | n.a.
Axial bearing | . | . | . | 10-19 | 07-20 | n.a.
Frames assembly | . | . | 02-20 | 03-20 | 07-20 | n.a.
M&R Plug | . | . | 03-20 | 04-20 | 07-20 | n.a.

## Slide 10: CMS TIK3.2
Cryostat
overview
Platform
Stand
Vacuum chamber
Top plate
Pressure vessels
GMP
Pump unit
Manufacturing complete
Manufacturing in progress
Pipework

## Slide 11: CMS TIK3.2
Pressure vessels
HX2
Ortho-para converter
Pressure control buffer

## Slide 12: CMS TIK3.2
Top plate
+ stand
+ platform
+ vacuum chamber
Stand, platform
and top plate
Vacuum chamber

## Slide 13: CMS TIK3.2
CMS control cabinet delivered
CMS control cabinet
3000 x 2000 0.5 t

## Slide 14: CMS TIK3.2
Status CMS assembly
vacuum chamber
1.2 t / d=2m
Stand, top plate and platform

## Slide 15: MRS TIK3.2
Schedule status and outlook
Sub unit | Final design | CDR | Manufacturing | FAT | delivery | SAT
Vacuum chamber | . | . | . | n.a. | 09-20 | n.a.
Stand | . | . | . | n.a. | 09-20 | n.a.
Platform | . | . | . | n.a. | 09-20 | n.a.
Top plate | . | . | . | n.a. | 09-20 | n.a.
Pressure control buffer | . | . | . | . | 09-20 | n.a.
Ortho para converter | . | . | . | . | 09-20 | n.a.
Heat exchanger | . | . | . | . | 09-20 | n.a.
LH2 pumps | . | . | . | . | 09-20 | n.a.
Cold pipework | . | . | 12-19 | n.a. | 09-20 | n.a.
Gas management panel | . | . | 12-19 | n.a. | 09-20 | n.a.
Control cabinet | . | . | . | . | 09-20 | X
CMS Cryostat | . | . | 03-20 | 04-20 | 2020 | ???

## Slide 16: MRS TIK3.2 / CMS SAT issue
CMS SAT issue
SAT of CMS is part of contract with Jülich
SAT of transfer lines, coyoplant and twister by ESS
Schedule unclear because all other systems have to be ready for CMS SAT
SAT of CMS cannot be performed without other systems working -> combined SAT?
Still unclear how much resources from Jülich have to be at ESS for how long. We can not afford to have people at ESS for several month if combined SAT takes longer
ESS needs to come up with concept and schedule for a “combined SAT“ soon to start planning

## Slide 17: TMP TIK4.1
Overview and status
Task of Target Monitoring Plug (TMP)
Measure the x/y position of the wheel
Measure the z position of the wheel
Measure the helium coolant outlet
temperature from each cassette during operation
Measure shaft vibration during operation
Measure helium borne sound in the helium coolant for acoustic diagnostics of the target cooling system and for acoustic diagnostics
Measure the internal cooling system
inlet and outlet temperature
Status / issues
CDR
Procurement and manufacturing in progress
FAT will be in April 2020
Delivery will be in June 2020
Funding will not cover the full and extended SoW (≈ + 20%)
Main plug
Two half's
Collimator Insert
X,Y,IR Insert
X,Y,Z Insert
Collimator
package

## Slide 18: MRS TIK4.1
Schedule status and outlook
Sub unit | Final design | CDR | Manufacturing/Procurement | FAT | delivery | SAT
T measurement | . | . | . | X | 06-20 | X
z measurement | . | . | . | X | 06-20 | X
IR measurement | . | . | . | X | 06-20 | X
x,y measurement | . | . | . | X | 06-20 | X
Main body | . | . | 02-20 | 03-20 | 06-20 | X
Inserts | . | . | 12-19 | 01-20 | 06-20 | X
Control cabinet | . | . | 12-19 | 01-20 | 06-20 | X
TMP | . | . | 03-20 | 04-20 | 06-20 | X

## Slide 19: Neutron Beam Extraction System project 1 (Prototyp manufacturing)
  Neutron Beam Port Insert (NBPI) prototype for LoKI instrument
  Vertical Handling Teststand (VTS) & Light Shutter System (LSS)
  Horizontal Test Stand (HTS)
  Insert Installation Tool (IIT)
  Media Connector prototype
NBEX Assemblies

## Slide 20: Neutron Beam Port Insert (NBPI) prototype for LOKI (project 1)
Design Update of NBPI prototype by FZJ has been finished in April 2019
Manufacturing at Kinkele has started in July 2019

## Slide 21: Light Shutter test stand (LSS) (project 1)
LSS Frame
LSS
LSS Blocks
GBS
BBG
FFB
Actuator Assy
Ball Screw
Media Branch
Manufacturing has started in June 2019
Manufacturing progress at Kinkele

## Slide 22: Horizontal Test Stand (HTS) (project 1)
Manufacturing has started
in June 2019
Manufacturing progress:
sub-frame
Manufacturing progress:
upper component

## Slide 23: Insert Installation Tool (IIT) (project 1)
Manufacturing has started
in June 2019
Manufacturing progress:
Beam, feet and side parts

## Slide 24: Media Connector (project 1)
Delayed delivery of the metal bellows shifts back the completion date to October 2019
Media Connector Test Bed is currently manufactured in FZJ’s workshop
Manufacturing of single components is finished

## Slide 25: Neutron Beam Extraction System Schedule status and outlook (phase 1)
Name | Design Feedback from FZJ to ESS | Design Update | Status | Delivery Date to FZJ
NBPI LOKI Prototype |  |  (FZJ) | Manufacturing at Kinkele | week 46
LSS Prototype |  |  (ESS) | Manufacturing at Kinkele | week 43
VTS |  |  (ESS) | Manufacturing at Kinkele | week 43
HTS |  |  (ESS) | Manufacturing at Kinkele | week 39
IIT |  | n.a. | Manufacturing at Kinkele | week 39
Media Connector |  | n.a. | Manufacturing at FZJ | Week 39

## Slide 26: Test Phase (project 2)
Test phase is scheduled from October 2019 until April 2020
Planned Budget: 200.000 €
Test Programm:
  Assembly test
  Handling
  Accuracy
  Installation sequence
  Tightness tests

## Slide 27: NBPI Series (project 3)
Scheduled from October 2019* until April 2021
Planned Budget: 4 Mio. €
Scope of Work for 16 NBPIs:
  NBOA integration into NBPI Design
  Manufacturability check
  Heat calculations
  Commissioning of manufacturing
  Supervision of manufacturing
  Quality Management
  Functional tests at Jülich
  Cleaning
  Delivery
  *project has started already (phase 1 budget)
Notes: Use week numbers
NBOA Design del = 3d model delivered to NBPI team as released chess file
NBOA Approval = ICD released for review TD+NSS
NBPI CDR = individual cdr of the NBPI performed by TD
FAT = Factory acceptance testing of the NBPI only (no NBOA)
Delivery to Site = Lund
NBOA Integration = tent integration
NBPI installation = installing NBPI in portblock in final position

## Slide 28: NBPI Series Schedule status and outlook (project 3)
NBPI | NBOA design delivery to FZJ | NBOA integration and approval | Manufacturing Drawing | CDR
Test Beamline |  (no NBOA) |  | 90 % | 
MAGIC |  (no NBOA) |  | 90 % | 
LOKI |  |  | 75 % | 
VESPA |  |  | 0 % | 
DREAM |  |  | 0 % | 
ESTIA |  | in progress | 0 % | 
BIFROST |  |  | 0 % | 
ODIN |  |  | 0 % | 
HEIMDAL |  |  | 0 % | 
FREIA |  |  | 0 % | 
CSPEC |  |  | 0 % | 
NMX |  | in progress | 0 % | 
SKADI |  |  | 0 % | 
T-REX |  |  | 0 % | 
MIRACLES |  |  | 0 % | 
BEER |  |  | 0 % | 
Notes: Use week numbers
NBOA Design del = 3d model delivered to NBPI team as released chess file
NBOA Approval = ICD released for review TD+NSS
NBPI CDR = individual cdr of the NBPI performed by TD
FAT = Factory acceptance testing of the NBPI only (no NBOA)
Delivery to Site = Lund
NBOA Integration = tent integration
NBPI installation = installing NBPI in portblock in final position

## Slide 29: summery
TIK3.1 & TIK3.2 will be almost complete in 2019.
  Full FAT will be in spring 2020
  Delivery will be, as scheduled, in summer 2020
BF1 study is complete!
TIK4.1 will be complete around summer 2020
NBEX series will be complete (include tests) around
spring 2021

## Slide 30: Contractual issues
Contribution Agreement for the Construction Phase between
      ESS ERIC
      and
      Forschungszentrum Jülich GmbH
is finally agreed and signed!
(after just 5 years)