## Slide 1: Target Sub-project Update TCB.09
Rikard Linander
Acting Head of Target Division
European Spallation Source ERIC
12th September 2019

## Slide 2: Target sub-project is 47% complete
Current budget at completion for the ESS Target Sub-project is 222M€
Earned value end of August 2019 is 104M€
Since the re-baseline mid 2018 CF has held the site early access dates
Target Ready for Beam milestone is March 2022
  Currently the sub-project is carrying a negative float of about 6 months.
  Most Target WP installations are with < 40 days float to Critical Path.
Several heavy steel structures (~700 tonnes) have been installed, including monolith vessel supports, baseplate, ground shielding, and D2T shielding
Raw material for monolith vessel delivered to manufacturer. On track for delivery of this in-kind element by end of this year.
Commissioning of the Target Moderator CryoPlant has been completed.

## Slide 3: High Level Schedule (CP items)
Delivery to site
CDR
PDR
System test completed
Start of Installation
Target Wheel Drive & Shaft
2017
2018
Q1 Q2 Q3 Q4
Target Monitoring System
Target Helium Cooling System
2019
Q1 Q2 Q3 Q4
2021
Q1 Q2 Q3 Q4
Tuning Beam Dump
Monolith Inner Shielding
2020
Q1 Q2 Q3 Q4
inst. MUTS
10/9
31/12
#1
#2 14-15/3
Ready for
delivery 12/3
Test inst. MUTS
1/5
1/10 Heat Ex.
12/8
7/10
17/4
28/3
15/12
#1
2022
Q1 Q2 Q3 Q4
1/5
9/6
15/5
#2
15/10
#3
15/2
#4
test inst.
19/4
final inst.
11/6
Target RBOT Mar -22
Monolith Vessel
18/12
Neutron Beam Port Blocks
16/7
NBPB Part #1: 11/5 …
NBPB Part #5: 15/7
Moderator & Reflector
Complete unit
on site 31/7
test inst.
6/7
final inst.
22/12
inst. MUTS
12/8
11/12
Monolith Connection Ring
22/6
Inst piping in
connection cell10/1
22/2
Integrated System Tests Complete
Sep/Oct
-132 d
Notes: CP for WP2 is He system,

## Slide 4: Target organisation

## Slide 5: Target organisation
Mark Anthony left Target Division to be ESS Project Director
Consolidation of the ESS Spallation Physics and Analysis resources
Build-up of the Target installation coordination and support group
Streangthening of the Target Operations and Maintenance group being planned
- Recent evolution

## Slide 6: Site Installation Progress

## Slide 7: Site installations
- Ground Shielding

## Slide 8: Site installations
- Monolith Vessel Supports, Monolith Baseplate, Ground Shielding, and Wall Embedments

## Slide 9: Site installations
- Bulk Shielding above D2T

## Slide 10: Site installations
- Embedments for Neutron Shield wall

## Slide 11: So, Target has entered installation phase!
ACF liner plates will start being installed September
Tuning Beam Dump is scheduled for installation in October/November
Monolith Vessel installation activities begin in December/January.
Cooling systems and HVAC installation starts 2019 Q1
- What’s next?

## Slide 12: Target Deliveries Progress

## Slide 13: Monolith Outer Shielding
- Blocks ready for shipment

## Slide 14: Steel supply challenges
- Ingot surface cracking

## Slide 15: Steel supply challenges
- Ingot surface cracking

## Slide 16: Steel supply challenges
Neutron Beam Port Blocks
  Start of installation currently carrying a negative float of 132 days to Target RBOT
  The lessons learned are that complicated, non-standard production requires more schedule contingency, and large industries are less agile and adaptive.
  Material quality issues, with severe edge cracking, were encountered and caused delays.
  The measures taken to mitigate further delays are weekly video meetings focusing on schedule, site visits, top management intervention, and enforcing agile decision making.
  The manufacturer’s remedy for schedule recovery is to redistribute some production between different facilities. We see more stability in their plan and recovery of two weeks. Without actions, the delay could easily have become doubled from the original 13 weeks instead.
  Further measures will be to secure flexible planning and coordination of the the subsequent workshop machining phase with the manufacturing company.
- Current main Target sub-project schedule concern

## Slide 17: Neutron Beam Port Tubes
- In manufacturing
Bottom part of port tube, with insert alignment features
Port flange raw material
Top parts of port tubes

## Slide 18: Neutron Beam Port Insert
- Manufacturing Prototype

## Slide 19: Neutron Beam Port Insert
- Manufacturing Prototype
Void for Neutron Beam Optics Assembly
Neutrons here!
Cut-out for rollers

## Slide 20: Insert Installation Tool
- In manufacturing

## Slide 21: Neutron Beam Extraction System
- Test Stand Frames
Horizontal test stand frame
Vertical test stand frame

## Slide 22: Target Safety System
- TSS mock-up operational!

## Slide 23: Target Safety System
- Mock-up tests of Target Wheel rotation sensors for the TSS

## Slide 24: Concluding remarks
Several heavy steel structures (~700 tonnes) have been installed, including monolith vessel supports, baseplate, ground shielding, and D2T shielding.
Hardware deliveries are arriving continuously and are kept in storage, awaiting installation.
Main installations will ramp up to full speed by end of 2019.
Target Ready for Beam milestone is March 2022.

## Slide 25: In-kind related schedule variances

## Slide 26: Target In-Kind Packages
Target Sub-Project has 22 in-kind work elements
  TA or CA signed for 10 work elements
  Partner selected for another 4 work elements
  Completed 2
  Self Performing 6 work elements
78.2M€ total Inkind achieved, this represents 37% of Target Budget