## Slide 1: STAP Update - September 2019
On behalf of Loki team

## Slide 2: Loki

## Slide 3: Sub-Contracted
Guide
  Order placed with SNAG - May 2019
  Kick-off with SNAG - Sep 2019
  Final Design Review at TG3.2 - Jan 2020
Jaws
  Out for tender (bids under review)
  Final Design Review at TG3.2 - Jan 2020
Collimation selector vessel
  Order placed with AVS - Aug 2019
  Kick-off with AVS - Aug 2019
  Final Design Review at TG3.2 - January 2020
Detector vessel
  Order placed with AVS - Jul 2019
  Kick-off with AVS - Aug 2019
  Final Design Review at TG3.2 - January 2020
Sample Stack
  In CTV

## Slide 4: TG3.1
Heavy Shutter
  Excludes: motion control system, guide & guide vessel
Chopper 1 & Chopper 2
  Excludes control system, remote handling & support structures
Collimation Selector
  Excludes vessel, jaws, guide, motion control system
Detector Systems
  Excludes vessel & monitors, motion control system

## Slide 5: TG3.1 In-Bunker Elements
Chopper 1
Heavy Shutter

## Slide 6: TG3.1 – Heavy Shutter

## Slide 7: TG3.1 – Heavy Shutter

## Slide 8: TG3.1 – Heavy Shutter
Sliding components
Guide
Shutter shielding
Rails
Shock absorbers
Air cylinder rod
Rail attachment bar
Remote handling

## Slide 9: TG3.1 – Chopper 1
“Conventional” design, based on choppers in service at ISIS –low technical risk.
Similar to ESS “Horizontal Split” concept, but simplified due to remote handling capabilities being provided by separate mounting pallet.

## Slide 10: TG3.1 – Chopper 2
Serviceable parts are housed within extractable cassettes.
Centre housing & rocker etc,, designed to remain in situ following installation, as removal would require disassembly of adjacent vacuum tank / collimator.

## Slide 11: TG3.1 – Chopper 2

## Slide 12: TG3.1 – Collimation Selector

## Slide 13: TG3.1 – Collimation Selector
Vacuum Vessel
Selector assemblies
Slits sets
Poly shine blocks
Concrete base blocks

## Slide 14: Guide Collimation configurations
Selectors can provide Guide –Guide, or Guide –Collimation, etc

## Slide 15: TG3.1 - Detector System

## Slide 16: TG3.1 - Detector System
Seven boron coated straws inside a 1” aluminium tube
Pre-building
Mount the detector modules on the frames
Mount the frames on the rails
Move the rear detectors

## Slide 17: TG3.1 - Detector System
Preamplifier Boards

## Slide 18: TG3.1 Beam Stop

## Slide 19: TG3.1
Positive experience
ESS focused on the right detail and gave valuable feedback
ESS seem keen to work with us to push on to manufacture
The content requested was appropriate, but it was a lot of work (we under estimated how much work would be required)

## Slide 20: In-Bunker Vacuum Seal
Aluminium Wire Seal
  tested – good confidence in sealing reliability, concern regarding cold welding
Copper Wire Seal
  Initial tests – high torque required, more work planned to optimize anneal & compression %
Aluminium edge seal
  procured, tests planned later this month
Copper edge seal
  procured, tests planned later this month

## Slide 21: Rack Location

## Slide 22: TG3’s

## Slide 23: Documentation for TG3.1
+30 documents
736 Standard (Commercial items)
925 Prepared Drawings
1661 Total drawings

## Slide 24
STAP Advice

## Slide 25: Verification process
Verification of the system requirements during installation.
Requires:
Clear procedures
Person responsible
When during the installation or integration
Definition of responsibilities during the verification
Resources to use: hardware and software
Fill the records needed
Clear procedures how to handle non-conformities or verification failures

## Slide 26: STAP Advice
A brief description of verification activities for key components:
Choppers Detector systems Beam monitors
Guides SE equipment Collimations
Shutters More ….
Inputs:
Component:
Title:
Statement (Brief description):
Rationale:
Verification method: