## Slide 1: TG4 and Installation plan LoKI Instruments
Clara Lopez
Integration Engineer
on behalf of LoKI team
www.europeanspallationsource.se
25 September, 2019

## Slide 2: Topics
TG4
Schedule for LoKI- integrated with NSS Master Schedule
Installation binders – information for IRR

## Slide 3: TG4 Installation readiness review
Phase 4 (Installation and Integration)
Readiness of 1st set of components
Phase 3
(Manufacturing & Procuring)
Readiness of 2nd set of components
Readiness of nth set of components
Phase 4
(Installation & Integration)
Phase 4
(Installation & Integration)
Phase 5
(Hot Commissioning)
Sub-TG4. 1
Sub-TG4. 2
Sub-TG4.n
and
Final TG4
Goal: Facilitate early installation, establish sequence and respect dependencies
Challenge: Complex review process and schedule
Phase 4
(Inst&Integ)
Phase 4
(Inst&Integ)
Phase 4
(Inst&Integ)

## Slide 4: TG4 - LoKI

## Slide 5: NSS Master schedule v4.2- North sector
Current date
SOUP
(3NBI*)
BOT
& HC
FS
March 2023:
First Science (FS) with expert teams on some of instruments above
Review progress of first 3 NBI for SOUP, implement backup plan if needed.
8NBI* in User Program
SOUP: Start Of User Program
BOT: Beam On Target
HC: Hot Commissioning
NBI: Neutron Beam Instruments

## Slide 6: Building Access

## Slide 7: Preliminary dates: September 2019 LoKI Pre-build and Installation
Pre-build at ISIS
Shipping UK to Sweden
Installation at ESS
  In Bunker:
  16/07/20 – 17/12/20
  Bunker to Cave
  16/10/20 - 17/12/20
  Cave shielding:
  18/05/21 - 18/08/21
  Sample area:
  12/03/21 - 18/08/21
  Pre- build completed
  18/11/21
  Delivery package 1
  (In Bunker components):
  13/05/21-15/06/21
  Delivery package 2:
  (Detector Vessel)
  18/11/21-27/01/22
  Delivery package 3:
  (Out of bunker component)
  27/01/22-29/03/22
  In Bunker:
  09/07/21 – 28/10/21
  Hutch
  16/08/21-09/02/22
  Services Installation
  06/10/21 – 01/8/22
  Bunker to Cave
  29/10/21 - 23/12/21
  Cave shielding:
  24/02/22 - 25/04/22
  Detector Installation:
  25/04/22 – 21/07/22
  Sample area:
  25/04/22 - 04/08/22

## Slide 8: Pre-build Progress

## Slide 9: Pre-build progress

## Slide 10: Installation binders LoKI Instrument

## Slide 11: Installation binders – Scope divided in Field installation packages
ESS Work package
Field Installation packages

## Slide 12: Field installation package document P1, P2,, Pn
Package ID. (logistic operations)
Work description: Scope of work
Schedule: time and man power estimation
Site preparation needed for field installation package (grouting, mounting supports, alignment plates, etc.)
Pre assembly activities for field installation packages
List of Drawings /Mounting instructions/Figures/ Electrical schemes/reference documents P&ID’s/specifications, 3d scans, photo archives, etc.
Particular considerations: access permits, regulatory requirements, risks, safety, temporary provisions, special limitations or recommendations for lifting equipment, subcontractors, vendors support, etc.
List of equipment, tools, consumables and materials
Location identification at site (bunker-hall-sectors)
Boundaries: dimensions LxWxH and mass
Utilities distribution preassembly needs: fluids, power, data, signals, etc. Check lists
Scaffolding, cranes and construction equipment requirements
Critical interface verification
Test validation to perform at site: ref document
P1
P2
Pn

## Slide 13: Loki Instrument Build Sequence Depends of the schedule and access to building
concrete base
Cave walls & roof
Monolith Insert
Vacuum pumps
Detector vessel
Detectors
Beamline shielding
PSS
Safety systems
Loki cabin
Racks and services
First Neutrons
Jib Crane
Gamma Shutter
Bunker wall insert
Services from Gallery
Sample area access floor
Sample area Components
End wall and beam-stop
Bunker wall
Loki within bunker
Bunker wall
Services through wall
Bunker roof
DAE Racks
Alignment base
Post bunker components
Generic Cables/pipes

## Slide 14: Field installation Packages
To facilitate management of installation an instrument will be divided into a set of field installation packages. These will be chosen to be of manageable size and defined by the sequence of engineering work and the assembly process. The FIPs will be prepared in an organized way to deliver the scope of work needed for the process of installation required at ESS by the partner and ESS installation teams.
This process is aligned with the detailed design phase, manufacturing process, installation, QA & safety requirements, and specific constraints and requirements specific to the relevant installation areas.

## Slide 15: Information from instruments
Swedish certification for instrument personnel for installation
Updated Planning information
Documentation related to safety requirements, logistics, contractors, access, induction etc.
Contract agreements
Electrical coordination
Remote handling: details about lifting for components design, tools to be included in pre-build at ISIS

## Slide 16: Questions
Thanks to LoKI team