## Slide 1: ESS Update
Ken Andersen
Joint Reflectometry and SANS STAP Meeting
Lund, 25th September 2019

## Slide 2: Journey to deliver the world’s leading facility for research using neutrons
2014
Construction Starts on Green Field Site
2009
Decision to Site ESS in Lund
2025
ESS Construction Phase Complete
2003
European Design of ESS Completed
2012
ESS Design Update Phase Complete
2019
Start of Initial Operations Phase
2023
ESS Starts
User Program
2019
TODAY

## Slide 3: ESS is 60 % complete
2019 is peak of construction activity
Accelerator commissioning underway
Target installation in progress
First Instrument hall complete and handed over
Working hard to deliver first science in 2023

## Slide 4: ESS Highlights
Progress continues
  No major new technical issues of concern have arisen
Two new members of senior management team in place; reorganisation
Positive decision at June 2019 Council meeting on completion of construction funding (240M€2013)
Civil construction remains on schedule
Accelerator installation making rapid progress
Target installation underway
  delay anticipated due to neutron beam port blocks
Bunker is in manufacturing
6 of the First 8 instruments endorsed by In-Kind Review Committee

## Slide 5: A reminder of the ESS Critical Path
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float
Accel RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker & TBL RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
Instrument Hall Access for Start of Installation
Hi -Beta Install
0.8 GeV Capability Installed
BOT - Beam on Target
RBOT - Ready for Beam on Target
FS - First Science
SOUP - Start of User Programme
EOC - End of Construction project
FS
We are focused on delivering First Science with three instruments by the end of 2023
Schedule date (no float) is March 2023

## Slide 6: Highlights from Science Directorate
Mapped out global manufacturing capacity for guides and choppers – no show stoppers
Draft Scientific Evaluation and Access Policy presented to SAC – to Council in December
New series of Science Colloquia between ESS and MAX-IV
Common instrument projects: guide shielding, choppers, monitors
2019 marks start of instrument installation
Handover ceremony for E halls
and NSS

## Slide 7: E-Hall Handover Ceremony
September 9th, during IKON17

## Slide 8: Instrument Papers
Status in September 2019
Single long paper for all instruments
  agreement to submit to Nucl. Instr. Meth. A
  full draft exists
  all instruments have written their part
  introduction and conclusion sections written by Ken with input from Andreas and Dimitri
  introductory sections for each instrument class written by instrument class coordinators
  most sections have been through more than one iteration
  instrument “quick facts” tables completed
  instrument layout figures making good progress with graphic designer
  harmonisation of instrument and instrument class sections ongoing (Ken, Andrew, Andreas, …)
  ready for circulation to all instrument teams by early October
  plan to submit in November
Individual instrument papers
  to be timed roughly with TG3 of each instrument
  format remains to be agreed
  no decision yet on journal, but needs to be covered by citation index

## Slide 9: Installation in E-Hall has started!
CSPEC: First components of Guide support structure
More to come in 2019:
First components for guide support structure for more instruments
Shielding support blocks for CSPEC, BIFROST, MAGIC
NBOA integration (temporary tent)
Temporary storage of Lab furniture for E03/04

## Slide 10: E03-E04 buildings fit-out (Q1-2020)
Installation starts: Q1/2020
Buildings: E04 (handover December 2019)
Main tasks: Installation of piping above the suspended ceiling (lab gases, power cables, fume hoods…..)
Installation of lab furniture, fume hoods,…
IRR: Q4/2019
Responsible: NSS

## Slide 11: Neutron Bunker in Progress
First deliveries in November 2019
Start of installation in February 2020
Now in Manufacturing
Inspection of pilot block manufacturing (Hungary, 28 August):
“most block dimensions are either correct, or within +/- 2 mm”

## Slide 12: Instrument Performance Comparison
 | 2016 Performance targets (@ 2MW) | Performance targets (2019) @ 2MW
LOKI | 5 x D22 & 20 x SANS2D | 5 x D22, 20 x SANS2D
SKADI | 4 x D22 | 5 x D22
ESTIA | Conventional mode: ~ 100 x D17 High intensity mode: 1cm2 samples = seconds | 10-100 x D17, depending on collimation mode
FREIA | 30 x FIGARO, INTER | 2-30 x FIGARO, depending on Q-range and resolution
DREAM | > 10 x POWGEN or WISH | > 10 x POWGEN & WISH
HEIMDAL | ~ 50 x GEM, ~ 8 x new POLARIS | ~ 50 x GEM, ~ 8 x new POLARIS
MAGIC | Cold: > 100 x worlds best, Thermal: 1mm3 crystals = 10 min | Cold: > 100 x world’s best, Thermal: 1mm3 crystals = 10 min
NMX | > 10 x LADI & Biodiff | > 20 x LADI & Biodiff
BEER | world leading in strain scanning, unique flexibility | 1-2 x TAKUMI, 3-6 x VULCAN, 14-28 x ENGIN-X, depending on multiplexing
ODIN | world leading for high resolution, > 10 x best for TOF methods | world leading for high spatial and temporal resolution, > 10 x best for TOF methods
BIFROST | > 10 x THALES & MACS | > 10 x THALES & MACS
CSPEC | 100 x IN5 (with RRM) | 6-150 x IN5 (3meV), depending on focusing and RRM
T-REX | 3 x 4-SEASONS, 3 x IN5 (without RRM) | 6-60 x IN5 (3meV), 10-100 x 4Seasons (100meV), depending on RRM
VESPA | 10 x VISION (ΔE = 130 meV) | 1-3 x VISION (ΔE < 160 meV) trading intensity for resolution
MIRACLES | 2 x BASIS and DNA | 4 x BASIS, 5 x DNA, for QENS at same resolution
2016 vs 2019

## Slide 13: Monolith foundation
and space above…

## Slide 14: Site installations
- Ground Shielding

## Slide 15: Site installations
- Monolith Vessel Supports, Monolith Baseplate, Ground Shielding, and Wall Embedments

## Slide 16: Site installations
- Bulk Shielding above D2T

## Slide 17: Target Wheel
- Tungsten bricks received, awaiting assembly

## Slide 18: Target Wheel
- Tungsten bricks mounted in cassette

## Slide 19: Target Wheel
- Prototype #3 success

## Slide 20: Beryllium Reflector
Acceptance tests

## Slide 21: Beryllium Reflector
Full assembly

## Slide 22: Cold Moderators
Final Cold Moderators
Cold Moderators with Thermal Moderator
(intermediate stage)

## Slide 23: Thermal Moderator
Final Cold Moderators
Cold Moderators with Thermal Moderator
(intermediate stage)

## Slide 24: Thermal Moderator
Final Cold Moderators
Cold Moderators with Thermal Moderator
(intermediate stage)

## Slide 25: Moderator / Reflector
Shaft ready for assembly
Final Cold Moderators
Cold Moderators with Thermal Moderator
(intermediate stage)

## Slide 26: Steel supply challenges
- Ingot surface cracking

## Slide 27: Steel supply challenges
- Ingot surface cracking

## Slide 28: Monolith Port Block
it’s not very monolithic
Monolith Port Block Package (360°)
East Block
South Block
West Block
North Block
NN-Bar Frame
Shielding beam level
Shielding beam level Proton Beam Section
PBW Port Block – Shielding

## Slide 29: Steel supply challenges
Neutron Beam Port Blocks
  Start of installation currently carrying a negative float of 132 days to Target RBOT
  The lessons learned are that complicated, non-standard production requires more schedule contingency, and large industries are less agile and adaptive.
  Material quality issues, with severe edge cracking, were encountered and caused delays.
  The measures taken to mitigate further delays are weekly video meetings focusing on schedule, site visits, top management intervention, and enforcing agile decision making.
  The manufacturer’s remedy for schedule recovery is to redistribute some production between different facilities. We see more stability in their plan and recovery of two weeks. Without actions, the delay could easily have become doubled from the original 13 weeks instead.
  Further measures will be to secure flexible planning and coordination of the the subsequent workshop machining phase with the manufacturing company.
- Current main Target sub-project schedule concern

## Slide 30: Neutron Beam Port Tubes
- In manufacturing
Bottom part of port tube, with insert alignment features
Port flange raw material
Top parts of port tubes

## Slide 31: Neutron Beam Port Insert
- Manufacturing Prototype

## Slide 32: Neutron Beam Port Insert
- Manufacturing Prototype
Void for Neutron Beam Optics Assembly
Neutrons here!
Cut-out for rollers

## Slide 33: Insert Installation Tool
- In manufacturing

## Slide 34: ESS Reorganisation
Focus on organisational priorities
  build the facility as well as the operational capacity
Agile decision-making process
Better integration and coordination using common processes
Achieve first science in 2023
Desired outcomes

## Slide 35: Proposed Future Organization
ESS Technical Directorate (from October 1st)
Director General
Technical
Director
KEVIN JONES
Pre-Operations
and Operations
CARLO BOCCHETTA
Accelerator
MATS LINDROOS
Office of the Technical Director
    Technical Coordinators MASATOSHI ARAI, FERENC MEZEI
    Engineering Manager
    PETER RÂDAHL (acting)
Target
RIKARD LINANDER
(acting)
NSS
SHANE KENNEDY
ICS
HENRIK CARLING
EIS
MAGNUS TÄCKLIND
(acting)
    Operations Planning
    DIMITRI ARGYRIOU

## Slide 36: Proposed Future Organization
Neutron Scattering Systems (NSS) Division (from October 1st)
Technical
Director
KEVIN JONES
NSS
SHANE KENNEDY
Instrument Scientists
KEN ANDERSEN
Experiment Control & Data curation
TOBIAS RICHTER
Technical Projects
VACANT
Choppers
NIKOLAOS TSAPATSARIS
Detectors
RICHARD
HALL-WILTON
Coordination & Planning
SOFIE OSSOWSKI
Personal Assistant
NSS Technical Coordination

## Slide 37: Proposed Future Organization
Science Directorate (from October 1st)
Director General
JOHN WOMERSLEY
Data Management and Software Center
JONATHAN TAYLOR
Science Directorate
ANDREAS SCHREYER
Instrument Technologies
OLIVER KIRSTEIN
Scientific
Activities
ARNO HIESS
Neutron Instruments
KEN ANDERSEN
Personal Assistant
Senior Advisor on Policy, Communication and Strategy SINDRA PETERSON ÅRSKÖLD
Deputy Science Director TBD
Scope remaining in SD until start of Hot Commissioning
  scientific advocacy and programme development
  preparation for first science and start of user programme
  scientific activities
  DMSC activities not related to data acquisition
  sample environment equipment
  motion control
  laboratory facilities
Activities and staff moving into SD at start of HC
  bunker, test beamline
  all instruments
  common projects (guide shielding, chopper)
  detectors
  DAQ and beamline controls
  safety and licensingf

## Slide 38: Highlights from May SAC Meeting
Pleased with common shielding and chopper projects
Very concerned about lack of progress with Technical Annexes
Schedule under pressure
  delay with port blocks will likely result in delay to BOT, First Science and SOUP
  danger of insufficient time for hot commissioning
Continue to support DREAM, ODIN, LOKI as first three instruments
Draft Scientific Evaluation and Access Policy is excellent start
Good plans for sample environment for high pressure and magnetic fields
Support for DMSC plans to focus on essential developments for First Science
  Artificial Intelligence and Deep Learning should be aspirations for the future
STAP reports very highly appreciated
  generally good progress reported, though sometimes too detailed
  concerns noted about multigrid detector developments: request focused detector session next time
  recommends joint STAP and SAC meetings once a year

## Slide 39: Joint STAP and SAC Meetings
Proposal for meeting structure starting in spring 2020
STAP | Members | Instruments | Spring | Autumn
Diffraction | 6 | 3 | Virtual | Real
Spectroscopy | 8 | 5 | Virtual | Real
SANS | 6 | 2 | Virtual | Real
Reflectometry | 6 | 2 | Virtual | Real
NMX | 6 | 1 | Virtual | Real
Imaging/Engineering | 6 | 2 | Virtual | Real
Samples & Users | 7 | 0 | Real | Virtual
Sample Environment | 8 | 0 | Real | Virtual
DMSC | 6 | 0 | Real (SE) | Real (DK)
Day | Morning | Afternoon | Evening
Mon | Arrival | Plenary | Dinner (all STAP together, no teams)
Tue | STAP | STAP | Dinner (individual STAPs + teams)
Wed | STAP | Individual closeout + STAP chair joint session + joint chairs feedback to SMT. SAC chairs pre-meeting + SMT STAP member departure (not chairs) | Dinner (STAP chairs) – could include SAC chairs/newcomers etc or nothing at all.
Thu | SAC Parallel with SAC newcomers intro (optional) | SAC | Dinner
Fri | SAC | SAC | Departure
Hold instrument STAPs with autumn SAC
Hold SAD and DMSC STAPs with spring SAC
Maximises exchange between instrument STAPs
Makes SAD & DMSC staff available for instrument STAPs
Makes instrument staff available for SAD & DMSC STAPs
Needs good coordination and planning between ICCs for STAP agendas
  manage availability of SAD & DMSC staff and coordinate common topics
  instrument STAP meetings need to run to schedule

## Slide 40: Thank You!