## Slide 1: ESS Visit @ Elettra Sincrotrone Trieste October 14th – 15th, 2019

## Slide 2: Status of ESS Project and IK Contributions
ESS @ Elettra Sincrotrone Trieste S.C.p.A.
Mauro Zambelli
European Spallation Source ERIC
Trieste, 14th / 15th October 2019

## Slide 3: Status of the ESS Project Construction, towards Operations & First Science

## Slide 4: Journey to deliver the world’s leading facility for research using neutrons
2014
Construction Starts on Green Field Site
2009
Decision to Site ESS in Lund
2025
ESS Construction Phase Complete
2003
European Design of ESS Completed
2012
ESS Design Update Phase Complete
2019
Start of Initial Operations Phase
2023
ESS Starts
User Program
2019
TODAY
Construction project is 61% complete

## Slide 5: ESS highlights
Progress continues
  No major new technical issues of concern have arisen
Rapid growing of installation and commissioning activities
Licensing application for commissioning of the Normal Conducting Linac submitted on schedule
Two new members of senior management team in place; reorganisation underway
Positive decision made at June 2019 Council meeting on completion of construction funding (240 M€2013)

## Slide 6: Flight scannings 2019/2018
April 2019
March 2018
JUNE 2019

## Slide 7: ESS Highlights
Civil construction and delivery of conventional facilities according to schedule
Notes: CF and Skanska have kept all critical access dates since the Rebaseline
CP is temporary Target High bay crane operational for vessel installation Dec 16th
Subprojects will give more, the tour is best

## Slide 8: A reminder of the ESS Critical Path
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float
Accel RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker & TBL RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
Instrument Hall Access for Start of Installation
Hi -Beta Install
0.8 GeV Capability Installed
BOT - Beam on Target
RBOT - Ready for Beam on Target
FS - First Science
SOUP - Start of User Programme
EOC - End of Construction project
FS
Main focus on delivering First Science with three instruments by the end of 2023
Schedule date (no float) is March 2023

## Slide 9: ESS Highlights
Conventional facilities
Civil construction remains on or ahead of schedule
Steelwork erection for target building high-bay and for D buildings now underway

## Slide 10: ESS highlights
Accelerator installation proceeding
  Ion source and LEBT commissioned
  MEBT installed
  DTL received and being integrated
  RFQ on site
Cryo-test stand permit received
Accelerator

## Slide 11: ESS highlights
Target installation proceeding
  High bay steelwork
  Monolith shielding
Major components in manufacturing
Monolith vessel on track for delivery by end 2019
Target

## Slide 12: ESS highlights
Bunker is in manufacturing
Instruments design phase complete – moving into construction
“First 3” instruments endorsed by IKRC
Common shielding, chopper and beam monitor designs developed to save time and money
Schedule mitigations implemented to reduce impact of port blocks on first science by modifying bunker installation sequence
Instruments

## Slide 13: Inauguration of the E01 Experimetal Hall
September 9th, 2019

## Slide 14: ESS Highlights
ESS offices and laboratory campus

## Slide 15: First eight instruments planned to be ready for commissioning by end of 2022
ESTIA
LOKI
DREAM
ODIN
BEER
C-SPEC
BIFROST
MAGIC
Aug 2019 Access
Jan 2021 Access
Jun 2021 Access
Preferred first
three instruments
May 2021 Access
Diffractometers | Spectrometers | Reflectometers | SANS | Engineering & Imaging
DREAM | BIFROST | ESTIA | LOKI | BEER
MAGIC | C-SPEC |  |  | ODIN
Notes: There is risk with this plan and we need to revisit it
2 of the 3 choices for first science has the last area access

## Slide 16: New Organization @ ESS Focus on delivery First Science in 2023

## Slide 17: ESS New Organization - 1

## Slide 18: ESS New Organization - 2

## Slide 19: ESS New Organization - 3

## Slide 20: ESS New Organization - 4

## Slide 21: In-Kind Contributions @ ESS Contracts, Construction, Operation

## Slide 22: New challenges for IK management
  IK Management @ ESS is rapidly moving from the Contractual phase to the Implementation phase, starting to look forward to the Operation phase
    This requires a progressively different approach to the relationship both with the IK Partners and with the relevant Functions inside ESS
    Complex issues are now coming into play: logistics, VAT on delivery and installation, quality documentation, CE marking

## Slide 23: ESS – IK Provider relationship
  The operative relationship between ESS and the IK Provider is essentially (and usefully) focused on the scientific/technical channel (WP Leader)
    However, IK is a far more complex process, which requires a “multi-channel” communication and comprehensive interaction between ESS and the IK Partners / IK Provider

## Slide 24: Multi-channel communication
  IK Contribution Agreements
  Technical Annexes and TA amendments
  Relationship with Ministries and Funding Agencies
  Administrative issues (i.e. Call-Offs payments)
  VAT issues (particularly on delivery and installation)
  Technical specifications
  Project schedule
  Logistics (transport, delivery)
  Quality Control and quality documentation
  CE marking / DOI
  Installation and commissioning

## Slide 25: ESS – IK Provider relationship
  The IK Partners and the specific IK Providers must be supported by ESS in order to accomplish their contracts on spec, on time and on budget
  ESS must be assured by the IK Provider about its capability to deliver equipment and services according to the specifications and to the schedule agreed

## Slide 26: ESS – Organizational issues
  In order to increase the effectiveness of the co-operation between ESS and the IK Partners, improvement in the internal organization for IK management are currently under way
  In particular the two following concepts have been introduced:
    IN-KIND FRAMEWORK MANAGEMENT
    IN-KIND SUPPLY CHAIN MANAGEMENT

## Slide 27: IK Framework vs. IK Supply Chain
ESS Project
IK
Partner
European Spallation
Source ERIC
ESS Requirements
Partner’s Issues
IKFR (Support)
IKSC (Control)

## Slide 28: ESS – Organizational issues
  IN-KIND FRAMEWORK MANAGEMENT
    General and organizational issues: contracts, amendments, legal issues, liabilities, warranties, VAT, quality, contacts with Funding Agencies, Ministries, National Bodies
    Responsibility: Strategy Directorate
  IN-KIND SUPPLY CHAIN MANAGEMENT
    Schedule and budget control
    Responsibility: Project Directorate

## Slide 29: ESS In-Kind System
In-Kind
SUPPLY CHAIN
Management
In-Kind FRAMEWORK
Management
ESS Work Package Leader
In-Kind
Provider
IK
ACCSYS
IK
TARGET
IK
NSS
IK
ICS
BrightnESS2 WP3
FC
FC
FC
FC
FC

## Slide 30: ESS In-Kind System – The Stakeholders
Partner States
Research Infrastructures Universities
Funding Agencies
In-Kind Partner
Institutions
Industry
National and European Research Centres and Institutes
ESS Council
IKRC
EMT
AFC
In-Kind
SUPPLY CHAIN
Management
In-Kind FRAMEWORK
Management
ESS Work Package Leader
In-Kind
Provider
IK
ACCSYS
IK
TARGET
IK
NSS
IK
ICS
BrightnESS2 WP3
FC
FC
FC
FC
FC
PAC

## Slide 31: In-Kind in Operations
Principles presented to and approved by Council#15 – 19/02/2019

## Slide 32: In-Kind in Operations
Principles presented to and approved by Council#15 – 19/02/2019

## Slide 33: In-Kind Contributions @ ESS Facts & Figures

## Slide 34: IK Status
Key Points
2015
2017
242 M€ (85 TAs) approved by Council (including 19 accredited).
178 M € (53 TAs) endorsed by IKRC.
Almost all IK for Accelerator, ICS and Target is approved by Council or endorsed by IKRC.
To date
126 M€ to be agreed for NSS – mostly Instruments (Sample Environment + Neutron Technologies)
Agree 3 remaining IKCAs; STFC (UK), ESS Bilbao (ES) and CNR (IT).
Following 15th Council approval of IK Principles, next step is to establish Procedures for IK Contributions during Operations
Ongoing
550 M€ estimated IK.
Additional c.28 M€ in collaborations (SE/DK) and c.13 M€ in direct contracts placed with German Institutes.
End of ESS Construction

## Slide 35: IK Status
Status of Agreements

## Slide 36
Yearly progress of In-Kind
Chart: 
| End of 2014 | End of 2015 | End of 2016 | End of 2017 | End of 2018 | Sep 2018 | End of 2019
Agreed / Endorsed | 0.19 | 128.5 | 254.7 | 319 | 334.1 | 417 | 450
Planned | 272.59 | 207.15 | 258.49 | 215.34 | 215 | 125 | 92
Potential | 335.78 | 313.19 | 110.54 | 25 | 10 | 17 | 17
Collaborations | 9.4 | 16.7 | 17.09 | 22 | 19.8 | 28 | 28
Direct Contracts | 0 | 5.7 | 15.7 | 20 | 21.36 | 13 | 13

## Slide 37: In-Kind Contributions @ ESS Conclusions

## Slide 38: Conclusions
New management for and special focus to IK
Alignment of IK to implementation
IK during Operations being established
Specific issues to be solved (VAT, etc.)

## Slide 39: The commitment
ESS In-Kind System
is fully committed to achieve
FIRST SCIENCE in 2023

## Slide 40: Thank you!
Mauro.Zambelli@esss.se