## Slide 1: Scientific and Technical Advisory Panel (STAP) Report for BEER and ODIN October 15 & 16, 2019
Panel Members: Sven Vogel (Chair), LANSCE Javier Santisteban, Centro Atómico Bariloche (did not attend) Francesco Grazzi, CNR Luise Theil Kuhn, DTU (did not attend) Stephen Hall, Lund University Nikolay Kardjilov, HZB
In-person meeting in Lund with four STAP member (Grazzi, Hall, Kardjilov, Vogel) and representatives of ESS, HZG & NPI, TUM & PSI participating

## Slide 2: Charge 1/2
Comment on the progress of the instrument projects in the context of their schedule:
  ODIN: On track for operation as one of the first three ESS instruments
  BEER: Possible delays
    design and construction of BEER cave above budget
    threat to continuation of HZG efforts due to the lack of a signed contract between HZG and ESS
Provide advice on early science for the instruments:
  STAP agrees that approach to first characterize and benchmark the capabilities of the instruments against design goals (e.g. resolution, validation of the data reduction etc.) and then focus on early science is perfectly fine and both teams are on track.
  Several early science projects were discussed and are outlined below.

## Slide 3: Charge 2/2
Provide feedback to the instrument teams on their progress and actions to be taken:
  Executive summary communicated to instrument teams at meeting.
  Both problems with BEER are in the opinion of the STAP outside the powers of the BEER instrument teams and require ESS intervention.
Provide feedback to the Science Director on the progress of the instrument class and any management actions that are needed to support the instrument projects:
  See report and this presentation, in particular action items for ESS

## Slide 4: Action Items for ESS 1/6
BEER budget issue:
  Shielding calculations for operational and worst case radiation doses resulted in a delay of the design of an increased wall thickness for the BEER cave (review required changes, policy change).
  Combined budget for design and construction exceeded
  Contract terminated
  BEER team without engineering support  ability to produce new procurement documents significantly hampered  Progress of BEER clearly in jeopardy  Must be addressed by ESS
BEER contract issue:
  HZG team reported that contract between ESS and HZG is still not signed
  HZG has advanced funds for BEER project in past two years  Advancing by HZG may end very soon  BEER project comes to a halt  Needs urgent resolution by the ESS and HZG managements

## Slide 5: Action Items for ESS 2/6
Issue between BEER participating teams relating to liability of the two partner institutions for failures of the other team was reported.  Legal issue, should be resolved between ESS, NPI and HZG.
Both teams pointed out
  ESS policy of requiring approval for considered scenarios for shielding design was implemented early summer of 2019  changes in definitions of worst case radiation accidents scenarios  changes of the BEER cave design and delays (ODIN could accommodate).
  Design of the distributions systems for electric power & utilities ongoing  both instrument teams have uncertainties about applicable requirements.
  Decision by ESS to move bunker wall lead to redesign of ODIN choppers  originally located outside bunker to accommodate access  now within bunker.
Consensus between both teams was ESS acts reactive rather than proactive with respect to such policies and requirements.
Both teams point out that such changes incur cost that stretches the instrument budgets or can lead to upset as is the case for the BEER cave.
STAP sees this as an opportunity for improvement for the ESS.

## Slide 6: Action Items for ESS 3/6
Both teams point out that all ESS instruments spend resources on common, repetitive tasks such as
  design and procurement of instrument hutches (for users, control of the data acquisition etc.),
  utility distribution,
  neutron beam monitors etc.
Could be done to a large fraction by ESS as they are common to all instruments (template modified by instruments?)
Approach offers great potential for substantial cost and effort savings
Mitigates the uncertainties of the instrument teams with applicable codes and regulations.
ESS “common monitor projects” appears vastly dormant to the instrument teams.

## Slide 7: Action Items for ESS 4/6
Several instances reported that information exchange between all ESS instrument teams during recent IKON meeting was very useful:
  Vendors for shielding,
  solutions for the phase stability problem of the chopper cascades, or
  information on the PSS systems.
More frequent meetings are not desired, BUT: Could ESS facilitate information flow otherwise, e.g. by mailing lists where items could be posted informally such as
  “What prices do other teams get in quotes for shielding material?” or
  “Does anyone have insight on question X related to the PSS system?”
  Announcements to all members of all instrument teams

## Slide 8: Action Items for ESS 5/6
Both teams reported that first responders such as firemen and potentially paramedics will not have access to experimental areas due to lack of training  ESS must find and communicate solution
Limited access by firemen to the experimental area resulted in charge to install sprinklers in instrument caves.  STAP suggests to evaluate combustible loads in caves to judge if this substantial effort is actually required
-monitors in the experimental areas will be installed in locations that are independent of the shielding calculations  STAP points out that an opportunity is missed since the calculations provide the most likely hot spots indicating abnormal conditions and therefore unnecessary exposure of personnel and users.  STAP suggest to ESS to consider the outcome of shielding calculations to inform the locations for -monitors.

## Slide 9: Action Items for ESS 6/6
BEER detector team requires format of ESS facility time stamps from the ICS team to continue development of soft- and hardware for the BEER detector development.
Distinguishing feature of the ODIN beamline are wavelength-dependent imaging modes
  In particular pixel-by-pixel Bragg edge analysis is absolutely crucial for the success of ODIN  Otherwise ODIN competes with e.g. NEXT@ILL  Due to higher ILL flux, NEXT should be superior to ODIN.
  Pixel-by-pixel Bragg-edge analysis is thus far under-developed.
Similarly, data reduction for the BEER beamline has never been tried.
STAP wishes to emphasize to ESS that support for software development for ODIN and BEER should receive as much support as possible to ensure their success.
Data reduction for BEER has commonalities with other diffraction beam lines
ODIN can only fulfill its promise if suitable Bragg-edge analysis tools are developed.
ESS needs to ensure that data reduction and data analysis software development receives required resources (DMSC and PSI) to process data on day 1.

## Slide 10: ODIN & BEER
Both beamlines are interfacing with the ESS project management and lead engineer.
Allocation of resources for installations etc. appears to be on a good path from the information presented to the STAP.

## Slide 11: ODIN 1/2 (TUM)
Transition from Michael Lerche to Aureliano Tartaglione successful  Absolutely crucial from perspective of STAP – SUCCESS!
Shielding calculations concluded, cave design modified
Heavy shutter was selected from ESS designs  STAP surprised by design goal of only 98% reliability  With 10 shutter operations per day, shutter fails every five days?  Action Item: Clarify reliability requirement for the heavy shutter.
Testing of T0 chopper prototype planned for June 2020
Contract for disk choppers signed with Airbus, collaboration already improved the design

## Slide 12: ODIN 2/2 (PSI)
Published tender for guide system, negotiations with Axilon/SwissNeutronics ongoing
  Received approval from ESS to use glass instead of metal substrate  cost reduction
Cave interior design evolving
Beam monitor technology evolving (see opportunity to share), locations were determined (previous action item)
Time-of-flight imaging detector concepts from ISIS, J-PARC and UC Berkeley are evaluated  Purchase as late as possible to obtain best technology  Action Item: Inquire about lead time for detector procurement
VAT issue likely solved (verbal information)
PSI Instrument Scientist plans to move to Lund in June 2021 when actual installation starts, one week/month at Lund until then

## Slide 13: BEER 1/2
STAP observes that Premek’s move to LUND in late summer 2018 provided benefits for the project
STAP specifically commends Premek for continuing to reach out to industry for engagement in the BEER instrument and especially providing capabilities such as a Gleeble machine.
Several previous issues are evolving
  policies for industry engagement (help from user office),
  alignment of samples (discussions with sample environments team, visit to J-PARC)
  type of collimators - pre‐fabricated fixed geometry vs. motion controlled slits – (visit to J-PARC)
Legal framework for industry engagement (“donation” of Gleeble) still not fully clear (liabilities, how much beam time etc.)
Action Item: Continue to work with ESS on defining policies to reward and define legal commitments with industry for providing capability (Gleeble) as well as long term engagement. Action Item: Continue to reach out to existing engineering diffraction instruments for information on their incident collimation and sample alignment solutions (what works, what would the teams at these instruments do better). Action item: Work with ESS and others to produce procurement documents for the cave to avoid delay of the construction.

## Slide 14: BEER 2/2
Main concern is contract issue
HZG B4C Detector development proceeding, tested successfully
Early Science:
  Texture measurements are planned
  STAP very much agrees that bulk neutron texture measurements are useful
  STAP suggests to participate in on-going neutron texture round robin  Establish capability or identify problems
  STAP suggests as a connection with local geo-science community to look into - in situ characterization of ice deformation, relevant to melting of glaciers - microstructure characterization of entire drill cores (slices of several meter long cores), utilizing high throughput and large core