## Slide 1
DMCS-LUT status report
Wojciech Cichalewski et. all.
10.02.2020
Notes: 1

## Slide 2
In-Kind project scope
Task no. | Deliverables | Delivery Deadline / Delivery MS
WU 1 | MTCA.4 RTM Carrier board integration | 2020-09-01
WU 2 | icBLM and nBLM controls and realization | 2020-09-01
WU 3 | IPMI EPICS integration | 2020-09-01
Possible commissioning activities has to be foreseen in the TA schedule and in-kind scope,
In-kind project deadline can be extended (beyond 09.2020) – resource wise – decision have to be taken soon to comply with in-kind and Ministry regulations,
Notes: 2

## Slide 3
WU 1 RTM Carrier integration – updated milestones (1/3)
MS ID | Short Description | Planned/ Baseline Date | Location | Comment
MS0 | Kick-off meeting | 2018.03.15 | DMCS, Lodz | 
MS1 | Specification and requirement analysis phase | 2019.03.01 | Video conference | 
MS2 | Conceptual design for software | 2019.03.01 | ESS, Lund | 
MS3 | Prototype version of the FW and software components | 2019.04.01 | Video conference | Driver and API for command line tools prepared for evaluation, EPICS layer missing. External dependency: BSP FW for board – to be delivered by ACC-PEG
MS5 | Progress meetings | Quarterly | ESS, Lund/Partner Premises | 
Notes: 3

## Slide 4
WU 1 RTM Carrier integration – updated milestones (2/3)
MS ID | Short Description | Planned/ Baseline Date | Location | Comment
MS6 | Test plan and report | 2019.09.01 | Video conference | 
MS7 | CDR of WU 1 | 2019.09.01 | Partner premises | Include in the MS6
MS8 | Production FW and software version delivery | 2019.11.01 | ESS, Lund | Software for first M-Beta LLRF systems installation
MS9.1 | SAR | 2019.12.01 | ESS, Lund | Connects to MS8
MS8.2 | Production FW and software version delivery | 2020.02.01 | ESS, Lund | Final version delivery
MS9.2 | SAR | 2020.03.01 | ESS, Lund | Connects to MS8.2
MS10 | Final report | 2020.09.01 |  | 
Notes: 4

## Slide 5
WU 1 RTM Carrier integration – updated milestones (3/3)
Chart: WU 1 - MS update
| Specification and requirements | Conceptual design for software | Prototypes | Test plan and report | CDR | Production software delivery p.1 | SAR p.1 | Production software delivery p.2 | SAR p.2 | Final report


 | 43160 | 43405 | 43405 | 43617 | 43617 | 43709 | 43770 | 43800 | 43862 | 43891
 | 365 | 120 | 151 | 92 | 92 | 61 | 30 | 62 | 29 | 31
Notes: 5

## Slide 6
WU 1 RTM Carrier integration – deliverables
Del. ID | Short Description | Delivery MS | Acceptance Criteria type | Comments
D1.1 | Investigation report | MS1 | Review | 
D1.2 | Driver part | MS10 | Review | 
D1.3 | EPICS device support and OPI | MS10 | Review | 
D1.4 | Test plan and report | MS10 | Test report | 

## Slide 7
WU 1 – Deliverables – Status (1/2)
Firmware development for the RTM piezo driver nearly finished – waiting for BSP update (firmware adjusted to first and M-beta prototypes),
Firmware following FW Framework guidelines (proposed by CA),
LO-RTM card firmware specification/requirements provided in autumn 2019 - first FW (and probably „production”) version delivered,
Possible test-stand environment is a LLRF reference system – „Golden Crate” (equipped with latests LLRF FW/SW versions),
Driver layer provided (following framework guidelines),
IOC – first version developed as E3 module, still under developement and adaptation to recent HW/FW/ updates
First screens prepared (as bob GUI),
Source codes for FW/SW provided in ESS Git repositories,
IOC documentation in confluence.
Notes: 7

## Slide 8
WU 1 – Deliverables – Status (2/2)
Deliverables review needed form ESS-ICS side,
Acceptance protocols for deliverables required for Ministry reporting procces and in-kind final delivery,
Test report and final report guidelines and expectations needed (ESS)
Limitations:
  RTM Carrier hardware:
    HW access limited – shared between different development activities,
    On-going work on BSP firmware (by NCBJ) for the RTM carrier, synchronized with FW framework (by Christian) – to be delivered...
  Piezo Driver board:
    HW setup needed for „Production software and firmware delivery”,
    HW specification is being modified – next step for prototyping and evaluation is needed – schedule change for production, delivery and installatio,
  On-going work on BSP firmware (by NCBJ) for the RTM carrier, synchronized with FW framework (by Christian) – to be delivered ….. ,
Notes: 8

## Slide 9
WU 2 - nBLM controls and realization – Milestones
Milestone ID | Short Description | Planned/Baseline Date | Location | Comment
MS0 | Kick-off meeting | 2018.03.15 | DMCS, Lodz | 
MS1 | Specification and requirement analysis phase | 2018.10.01 | Video conference | 
MS2 | Conceptual design for software | 2018.11.01 | ESS, Lund | 
MS3 | Prototype version of the FW and software components | 2018.12.01 | Video conference | Finished - tested in Linac4.
MS5 | Progress meetings | Quarterly | ESS, Lund/Partner Premises | 
MS7 | CDR of WU 2 nBLM | 2019.02.06 | Partner premises | Done
MS6 | Test plan and report | 2019.07.01 | Video conference | 
Notes: 9

## Slide 10
WU 2 - nBLM controls and realization – Milestones
Milestone ID | Short Description | Planned/Baseline Date | Location | Comment
MS8 | Production FW and software version delivery | 2019.09.01 | ESS, Lund | nBLM FW version delivery for warm accelerator commissioning
MS9 | SAR | 2019.11.01 | ESS, Lund | nBLM FW version acceptance review for warm accelerator commissioning
MS8.2 | Production FW and software version delivery | 2020.01.01 | ESS, Lund | Final version delivery (with adjustments from first delivery operation experience)
MS9.2 | SAR | 2020.02.01 | ESS, Lund | 
MS10 | Final report | 2020.09.01 |  | 
Notes: 10

## Slide 11
WU 2 - nBLM controls and realization – Milestones
Chart: 
| Specification and requirements | Conceptual design for software | Prototype version | Test plan and report | CDR | Production FW and software p.1 | SAR p.1 | Production FW and software p. 2 | SAR p.2 | Final report


 | 43160 | 43586 | 43617 | 43647 | 43435 | 43739 | 43770 | 43800 | 43922 | 44013
 | 426 | 31 | 30 | 92 | 71 | 31 | 30 | 122 | 91 | 62
Notes: 11

## Slide 12
WU 2 – nBLM controls and realization – Deliverables
Del. ID | Main deliverables | Delivery MS | Acceptance Criteria type | Comment
D2.1 | Specification revision | MS1 | Review | 
D2.2 | Firmware with functionallity realization | MS10 | Review | 
D2.3 | Device driver and User space driver | MS10 | Review | 
D2.4 | Epics device suport | MS10 | Review | 
D2.5 | OPI GUI | MS10 | Review | 
D2.6 | Test Plan | MS10 | Test report | 
Notes: 12

## Slide 13
WU 2 – Deliverables - Status
nBLM dedicated FW/SW development mostly finalized on the DMCS side,
Solutions evaluated in two LINAC 4 tests – last -> Dec. 2019,
Unresolved issues:
  input to interlock system,
  smart trigger,
  timing,
  DOD, etc…
Progress and issues discussed on the weekly meetings
Decisions concerning in-kind completion needed:
  Scenario for missing components (final) implementation,
  Scope swap and extension for commissioning activities.
Notes: 13

## Slide 14
WU 2 - icBLM controls and realization – Milestones
Milestone ID | Short Description | Planned /Baseline Date | Location | Comment
MS0 | Kick-off meeting | 2018.03.15 | DMCS, Lodz | 
MS7 | CDR of WU 2 icBLM | 2019.02.01 | Partner premises | CDR have been done at the same time but limited to the HW platform evaluation
MS1 | Specification and requirement analysis phase | 2019.05.01 | Video conference | 
MS7.2 | CDR follow-up | 2019.05.01 | ESS, Lund | Finalizing digitizer board integration on the carrier board.
MS2 | Conceptual design for software | 2019.06.01 | ESS, Lund | 
MS3 | Prototype version of the FW and software components | 2019.07.01 | Video conference | 
MS5 | Progress meetings | Quarterly | ESS, Lund/Partner Premises | 
Notes: 14

## Slide 15
WU 2 - icBLM controls and realization – Milestones
Milestone ID | Short Description | Planned /Baseline Date | Location | Comment
MS6 | Test plan and report | 2019.10.01 | Video conference | 
MS8.1 | Production FW and software version delivery | 2019.11.01 | ESS, Lund | icBLM FW&SW version delivery for warm accelerator commissioning
MS9.1 | SAR | 2019.12.01 | ESS, Lund | icBLM FW/SW version acceptance review for warm accelerator commissioning
MS8.2 | Production FW and software version delivery | 2020.04.01 | ESS, Lund | Final version delivery (with adjustments from first delivery operation experience)
MS9.2 | SAR | 2020.07.01 | ESS, Lund | 
MS10 | Final report | 2020.09.01 |  | 
Notes: 15

## Slide 16
WU 2 - icBLM controls and realization – Milestones
Chart: 
| Specification and requirements | Conceptual design for software | Prototype version | Test plan and report | CDR | Production FW and software p.1 | SAR p.1 | Production FW and software p. 2 | SAR p.2 | Final report


 | 43160 | 43586 | 43617 | 43647 | 43435 | 43739 | 43770 | 43800 | 43922 | 44013
 | 426 | 31 | 30 | 92 | 71 | 31 | 30 | 122 | 91 | 62
Notes: 16

## Slide 17
WU 2 – icBLM controls and realization – Deliverables
Del. ID | Main deliverables | Delivery MS | Acceptance Criteria type | Comment
D2.1 | Specification revision | MS1 | Review | 
D2.2 | Firmware with functionallity realization | MS10 | Review | 
D2.3 | Device driver and User space driver | MS10 | Review | 
D2.4 | Epics device suport | MS10 | Review | 
D2.5 | OPI GUI | MS10 | Review | 
D2.6 | Test Plan | MS10 | Test report | 
Notes: 17

## Slide 18
WU 2 icBLM – Deliverables - Status
icBLM dedicated FW/SW development in progress,
Most components FW/SW provided according to the specification,
IOC for icBLM – under development and evaluation,
FW/SW available in the ESS GIT repositories for testing and evaluation,
Real (in-situ) verification required for the system to identify solution weak points – possible updates,
Feedback on the user side GUI requirements is required,
Deliverables acceptance protocols required from ESS-ICS side,
Schedule update and scenario for testing and delivery are needed.
Notes: 18

## Slide 19
WU 3 – IPMI EPICS integration - Milestones
Milestone ID | Short Description | Planned/Baseline Date | Location | Comment
MS1 | Specification and requirement analysis phase | 2019.03.01 | Video conference | 
MS2 | Conceptual design for software | 2019.03.01 | ESS, Lund | 
MS3 | Prototype version of the software components | 2019.10.01 | Video conference | 
MS4 | Progress meetings | Quarterly | ESS, Lund/Partner Premises | 
MS5 | CDR of WU 3 | 2019.10.01 | Partner premises | to be clarified?
Notes: 19

## Slide 20
WU 3 – IPMI EPICS integration - Milestones
Milestone ID | Short Description | Planned/ Baseline Date | Location | Comment
MS6 | Production software version delivery | 2019.11.01 | ESS, Lund | SW version delivery for warm accelerator commissioning – scope needs to be determined,
MS7 | SAR | 2019.12.01 | ESS, Lund | 
MS8 | Test plan and report | 2020.01.01 | Video conference | 
MS6.2 | Production software version delivery | 2020.06.01 | ESS, Lund | Final version delivery (with adjustments from first delivery operation experience)
MS7.2 | SAR | 2020.08.01 | ESS, Lund | 
MS10 | Final report | 2020.09.01 |  | 
Notes: 20

## Slide 21
WU 3 – IPMI EPICS integration - Milestones
Chart: 
| Specification and requirements | Conceptual design for software | Prototypes | Test plan and report | CDR | Production software delivery p.1 | SAR p.1 | Production software delivery p.2 | SAR p.2 | Final report


 | 43160 | 43252 | 43617 | 43739 | 43831 | 43739 | 43770 | 43800 | 43983 | 44044
 | 365 | 365 | 122 | 92 | 60 | 31 | 30 | 183 | 61 | 31
Notes: 21

## Slide 22
WU 3 – IPMI EPICS integration – Deliverables
Del. ID | Main deliverables | Delivery MS | Acceptance Criteria type | Comment
D3.1 | Specification revision | MS1 | Review | 
D3.2 | Low Level library (communication with MCH) | MS10 | Review | 
D3.3 | Daemon service for constant monitoring | MS10 | Review | 
D3.4 | Epics device support | MS10 | Review | 
D3.5 | IOC integration | MS10 | Review | 
D3.6 | OPI GUI | MS10 | Review | 
D3.7 | Test Plan | MS10 | Test report | 
Notes: 22

## Slide 23
WU 3 E4I – Deliverables - Status
Work on the openIPMI library access to the HW,
Sensor, threshold read-out provided via openIPMI,
IOC under development - basing on ASYN approach,
IPMIcomm solution (by Han) evaluated locally,
Screens prepared according to the existing nomenclature,
Established new MTCA.4 platform for E4I testing purposes,
Naming convention to be discussed and decided,
Static vs. dynamic HW configuration detection,
Information, questions, show-stoppers details, future plans – see demo by Wojtek Jałmużna, Piotr Perek, Kacper Kłys,
Notes: 23

## Slide 24
Summary
EPICS training organized in Lodz – Nov 2019,
Progress in WU1:
  Provided support for PD-RTM and LO-RTM on the FW/SW level (in sync. with LLRF framework),
  provided first version of PD-RTM IOC,
Evaluation on the ESS-ICS side is needed,
Adaptation to the HW changes (PD redesign) will be required,
nBLM FW/SW mostly ready from DMCS side (LINAC 4 evaluation 12.2019),
Missing functionalities related to ESS open issues,
icBLM – FW part includes some of the specified/required parameters (to be completed in relatively short time period),
IOC – under development and ready for ESS evaluation,
Needed feedback concerning system operation and user/expert interfaces.
Notes: 24

## Slide 25
Summary
WU3 – approach modified – OpenIPMI library used (in order to keep community support) for IPMI functionality access, ASYN used for communication with devices,
IPMIcomm evaluated locally – operator screens proposal prepared,
Discussions and decisions needed in order to keep conformity with ES-ICS approach (naming convention, deployment structure, etc).
Deliverables acceptance protocols are required for Ministry,
MS schedule to be updated,
Decisions concerning in-kind completion needed:
  Scenario for missing components (final) implementation,
  Scope swap and extension for commissioning activities – to be correlated with overall comm. installation schedule update.
Notes: 25

## Slide 26
Thank you for your attention
Notes: 26