## Sheet1
ESS ID | ESS org | Origin | Obervation / Recommendation | Interpretation | Activity | Resp. | Deliverable | Due date | Comment
2013-01 | ACC | AR2013: Top 10 worries 3) See slide 44 | Accelerator: basic assumption of 1 W/m used as Level 1 requirement with major implications inter alia on licensing, shielding and operation; needs to be confirmed by realistic end-to-end beam simulations including errors, showing sufficient margin. Normal operation envelope should include beam loss scenarios. | Verify that ESS accelerator can provide average beam power of 5 MW with beam loss less than 1 W/m Verify shielding is adequate for 1W/m (as per Lali T. tech note) | develop plan for tasks, responsibilities, deliverables and dates to address recommendation | M.Eshraqi | draft plan | 2013-12-20
[5 empty] | review and agree plan with M. Lindroos | M.Eshraqi | agreed plan | 2014-01-31
[5 empty] | develop Tech Note to verify radiation shielding is adequate | L.Tchelidze | Tech Note | As per plan to be completed no later than 01 May 2014
[5 empty] | tasks as per plan | responsibilities as identified in the plan | deliverables as identified in plan | As per plan to be completed no later than 01 May 2014
2013-02 | ACC | AR2013: 1_Acc_i See slide 8 | Accidental beam loss: need to establish “worst case” scenarios based on risk analysis and to conduct simulations to determine appropriate shielding (interface with CF) and system interlocks for personnel protection | Establish and document worst case beam loss scenarios to use for shielding analysis | develop plan for tasks, responsibilities, deliverables and dates to address recommendation | L.Tchelidze | draft plan | 2013-12-20
[5 empty] | review and agree plan with M. Lindroos | L.Tchelidze | agreed plan | 2014-01-31
[5 empty] | develop Tech Note with worst case scenarios to use for shielding analysis | L.Tchelidze | Tech Note | As per plan to be completed no later than 01 May 2014
[5 empty] | tasks as per plan | responsibilities as identified in the plan | deliverables as identified in plan | As per plan to be completed no later than 01 May 2014
2013-04 | ACC | AR2013: 1_ACCRec-1 See slide 11 | Reassess beam instrumentation based on effective strategy of commissioning and needs of operation | Review the type, location, number and performance of beam-line instruments for: · sequence for beam commissioning . Operations mode . Maintenance mode | develop plan for tasks, responsibilities, deliverables and dates to address recommendation | M.Munoz | draft plan | 2013-12-20
[5 empty] | review and agree plan with M. Lindroos | M.Munoz | agreed plan | 2014-01-31
[5 empty] | tasks as per plan | responsibilities as identified in the plan | deliverables as identified in plan | As per plan to be completed no later than 01 May 2014
2013-05 | ACC | AR2013: 1_ACCRec-2 See slide 11 | Recommend push for faster prototyping of all accelerating structures and raster magnet system | Review the schedule to determine if the strategy for prototyping is time-efficient, and to determine which if any activity durations can be shortened and milestones moved forward. Analyse what dependent activities are impacted and how they are impacted, and change the plan if necessary. Analyse changes to risks - new risks, changed risk assessments (probability or impact), or changed risk mitigation. | develop plan for tasks, responsibilities, deliverables and dates to address recommendation. To include: - identifying a list of prototypes for each WP - describing the scope of each prototype - assigning WP leaders responsibilities to review the Primavera schedule and other planning to identify possible efficiencies | J. Weisend | draft plan | 2013-12-20
[5 empty] | review and agree plan with M. Lindroos | J. Weisend | agreed plan | 2014-01-31
[5 empty] | tasks as per plan | WP leaders as identified in the plan | deliverables as identified in plan | As per plan to be completed no later than 01 May 2014
2013-06 | ACC | AR2013: 1_ACCRec-3 See slide 11 | Establish criteria for success and formalize decision process in advance for decision of IOTs (end 2017) | Establish criteria for success and formalize decision process in advance for decision of IOTs (end 2017) | develop plan for tasks, responsibilities, deliverables and dates to address recommendation | A. Sunesson | draft plan | 2013-12-20
[5 empty] | review and agree plan with M. Lindroos | A. Sunesson | agreed plan | 2014-01-31
[5 empty] | develop Tech Note with criteria | A. Sunesson |  | As per plan to be completed no later than 01 May 2014
[5 empty] | other tasks as per plan | responsibilities as identified in the plan | deliverables as identified in plan | As per plan to be completed no later than 01 May 2014
2013-07 | ACC | AR2013: 1_ACCRec-4 See slide 11 | Analyse and develop IKC potential for beam instrumentation | Analyse and develop IKC potential for beam instrumentation | develop plan for tasks, responsibilities, deliverables and dates to address recommendation | A.Jansson | draft plan | 2013-12-20
[5 empty] | review and agree plan with M. Lindroos | A.Jansson | agreed plan | 2014-01-31
[5 empty] | tasks as per plan | responsibilities as identified in the plan | deliverables as identified in plan | As per plan to be completed no later than 01 May 2014
2013-08 | ACC | AR2013: 1_ACCRec-5 See slide 11 | Be aware of the critical importance and manage properly the communication of radiation-protection issues to the public | Recommendation and responsibility for actions is to be clarified with EPG | to be agreed with EPG | M.Lindroos |  | TBA 2014-02
2013-09 | ACC | AR2013: 1_ACCRec-6 See slide 11 | Translate high-level requirements for reliability and availability into performance figures for elementary components and systems, identify discrepancies with state-of-the-art and implement corrective / mitigating actions (overcapacity, redundancy, reparability, “hot” spares, etc.) | Develop requirements to L4 for, as a minimum, availability and for reliability. Trace requirements to L1 availability and reliability requirements to ensure the breakdown is mathematically correct. | develop plan for tasks, responsibilities, deliverables and dates to address recommendation | D.McGinnis | draft plan | 2013-12-20 | Develop Accelerator models for RAM (reliability, availability and maintainability). Using the RAM model, perform the following analyses: • top-down breakdown of L1 availability and related requirements to become targets for L2, L3, L4 and lower PBS systems, subsystems and components. • Bottom-up estimates for L5, L4, L3, L2 components, subsystems, systems to validate or identify need to change L1 figures Enhance the RAM model through FMEA. Design for reliability, maintainability (access, ease and complexity of maintenance, minimal skill levels for maintenance etc) Initiate operational planning using RAM-related analyses for e.g. spares assessment, maintenance task analysis, level of repair analysis. From the RAM, develop reliability and maintainability requirements at L2-L5. Include these requirements in the SOWs for IKC and supplier tenders and agreements. Replace the targets and estimates in the ESS model with estimates and empirical data provided by IKC and other suppliers.
[5 empty] | review and agree plan with M. Lindroos | D.McGinnis | agreed plan | 2014-01-31
[5 empty] | tasks as per plan | responsibilities as identified in the plan | deliverables as identified in plan | As per plan to be completed no later than 01 May 2014
2013-10 | ACC | AR2013: 1_ACCRec-7 See slide 11 | Integrate utilities into reliability/availability studies | ? | develop a written response to this recommendation for EPG | A. Jansson |  | TBA 2014-01
[5 empty] | review and agree response with M. Lindroos | A.Jansson |  | TBA 2014-01
[5 empty] | provide response to EPG | M.Lindroos |  | TBA 2014-02