## Slide 1: Annual Review Recomendation
ID | Recommendation | Interpretation | Tasks | Resp. | Deliverable | Date
AR2013: 1_ACCRec-1 See slide 11 | Reassess beam instrumentation based on effective strategy of commissioning and needs of operation | Review the type, location, number and performance of beam-line instruments for: · sequence for beam commissioning . Operations mode . Maintenance mode | develop plan for tasks, responsibilities, deliverables and dates to address recommendation | M.Munoz | draft plan | 20/12/13
 |  |  | review and agree plan with M. Lindroos | M.Munoz | agreed plan | 31/01/14
 |  |  | tasks as per plan | responsibilities as identified in the plan | deliverables as identified in plan | As per plan to be completed no later than 01 May 2014
Started working group for commissioning:
  T. Shea, E. Tanke, M. Eshraqi, H. Danared, R. Zeng, M. Munoz.
Identify members of commissioning team:
  Evaluate the need for dedicated operators during commissioning.
  Plan for training the commissioning team.

## Slide 2: Beam Commissioning Plan
Beam Commissioning planning
  Update commissioning milestones.
  Prepare list of measurements, procedures and techniques required in each one of the commissioning stages February 2014.
  Identify the Beam Instrumentation needed March 2014.
  Identify the software needed  March 2014.
  Write the requirements  June 2014.
  Documentation of procedures.
Aspects to be coordinated with the rest of ESS:
  Prepare list of systems to be tested before each stage of Beam Commissioning.
  Coordination of the staged licensing process.
  Shift organization: 2 or 3 per day, weekends, etc.
  On Call support: what support from CF and other technical services is needed?
  Operators: When to integrate the operators in the control room?