## Slide 1
WP Status & General Issues
M. Lindross and J. G. Weisend II
www.europeanspallationsource.se
November 13, 2013

## Slide 2: Outline
Status of Work Packages
Work Package Audits
General Comments and Issues
  Risk
  Issues
  Comments and Next Steps

## Slide 3
Work Packages & Leaders
WP# | WP TITLE | WP LEADER | EXTERNAL WP? | LIASON FOR EXTERNAL WP
1 | MANAGEMENT | J.G. WEISEND II | NO | 
2 | ACCELERATOR PHYSICS | M. ESHRAQI | NO | 
3 | NORMAL CONDUCTING FRONT END | S. GAMMINO | YES | A. PONTON
4 | SPOKE CRYOMODULES | S. BOUSSON | YES | S. M0LLORY
5 | ELLIPTICAL CRYOMODULES | P. BOSLAND | YES | C. DARVE
6 | HEBT & MAGNETS | S. MØLLER | YES | P. LADD
7 | BEAM DIAGNOSTICS | A. JANSSON | NO | 
8 | RF SYSTEMS | A. SUNESSON | NO | 
99 | ACCEL INFRASTRUCTURE & INSTALLATION | G. LANFRANCO | NO | 
10 | TEST STANDS | W. HEES | MIXED | W. HEES
11 | CRYOGENICS | P. ARNOLD | NO | 
12 | VACUUM | P. LADD | NO | 
13 | SAFETY & RELIABILITY | A. JANSSON | NO | 
14 | REDESIGN EFFORT | D. McGINNIS | NO | 
15 | COOLING & ELECTRICAL SUPPORT | F. JENSEN | NO | 

## Slide 4: Introductory Comments
All the work packages contributed to the Annual Review in November. Significant effort was spent since the last TB meeting in finalizing scope, cost and schedule prior to the review.
In many cases, significant changes were required in a short period of time.
The ACCSYS planning staff (M.K. Veldeman & A. Ingels) also worked hard to prepare for the review
The success of the review is the result of the hard work of the ACCSYS project staff and collaborators
ACCSYS is now responding to the review recommendations

## Slide 5
WP1: Management
Achievements
  Working with WP Leaders and ACSYS Planners, met cost and schedule planning goals – first version of strategic plan is complete.
  Held WP Audits for WP3 (NCFE), WP11(Cryogenics), WP4 /WP5 (cavities & cryomodules)
    These included 3 of our external work packages
  Held Technical Board Meeting in October
  Held Risk Workshop and completed ACCSYS Risk Matrix
  ACCSYS Collaboration Board Meeting in Uppsala
  Clarified WP scopes to eliminate overlaps, gaps and confusion prior to annual review

## Slide 6
WP2: Accelerator Physics
Achievements
  Error study with Lorentz force detuning in spoke cavity section is ongoing
  Work with ICS about OpenXAL and evaluation of alternatives
  Starting to write requirements for Beam Commissioning
  The report for the MEBT redesign on the way and expected be done in Dec
  "The error and collimation studies" have been resumed
  RF accelerating field optimization.
  DTL Beam Dynamics analysis and RF design.
  DTL Beam Dynamics error study on PMQ alignment and gradient as well as geometrical errors
  Thermo-mechanical simulations of the first cells to the evaluate frequency detuning.
  End-2-end linac handed over to ICS for BLED upload
  SC linac using fieldmaps is generated and error studies ongoing

## Slide 7
WP2: Accelerator Physics
Achievements
    To reduce the maximum buncher voltage, the layout with 3 quads between the last buncher and the 1st DTL tank has been adapted as the baseline.
    It has been verified that the lattice can be re-tuned for +/-20% changes in emittance.
    In collaboration with Vacuum, a new lattice fulfilling the engineering and vacuum requirements has been developed. The LWU has been adjusted to meet vacuum & mechanical requirements.
Issues
    While designing the SC linac using field maps it was found that the cold aperture in spoke and medium beta cryomodules is smaller than the warm aperture and may increase losses in the cold area

## Slide 8
WP3: NORMAL CONDUCTING
FRONT END
Prepared for and participated in WP3 Audit. Response to recommendations is under development
Ion source and LEBT
  Achievements
    Order of the HV power supply with adequate timing characteristics
    Construction under way of the chopper and RFQ input collimator for the beam test at CEA-IRFU
    Definition of the new extraction system for larger currents by using the KOBRA3-INP code (in progress)
    Definition of the new LEBT with updated optics to match the new RFQ input Twiss parameters (in progress)
    Coils power supplies available at LNS
    Installation schedule analysis carried out

## Slide 9
WP3: NORMAL CONDUCTING
FRONT END
    Industrial design of the injection system of the source
    Collimator completed
    RF tests of the chopper
  Actions following the decision taken during the IS&LEBT integration Meeting at INFN-LNS on week 26
    Impact of the new requirements on the IS&LEBT design
    Rescheduling of the activities
Planned key activities
  Order of the plasma chamber
  Order of the injection system
  Order of the insulation transformer
  Completion of industrial design of source component

## Slide 10
WP3: NORMAL CONDUCTING
FRONT END
RFQ
Achievements
  Thermomechanical calculations in progress
MEBT
Achievements
  Engineering support and alignment in progress
  Definition of assembly ‘sectors’ for Engineering integration in progress.
  Vacuum KF clamps vs metal sealing study in progress.
  Format standards: CATIA can work for 3d models exchange.
  (Prototypes) RF Coupler Cu plating in the workshop production line.
  RF tests have been performed on the buncher cavity.
  Copper plating of the RF Coupler for the cavity.
  Meeting with Peter Ladd (ESS), about the MEBT vacuum system (inclusion of an extra valve to the MEBT layout).

## Slide 11
WP3: NORMAL CONDUCTING
FRONT END
MEBT
Planned Key Activities
  Prototypes: Buncher cavity Cu plating.
  Quadrupole Magnetic design based on the new parameters.
  Buncher RF design based on the new parameters.

## Slide 12
WP3: NORMAL CONDUCTING
FRONT END
DTL
Achievements
Physical design
  Main figures of merit has been optimized in order to fit requirements of Final energy (>88 MeV) ,tank length (<8m), RF power (< 2.2MW)
  Beam quality parameters fullfil the requirements of the linac section (Phase Advance, equipartitioning, emittance growth, halo formation, tune depression)
Beam dynamics error study
  Definition of simulation method and DTL requirements with errors
  Error study with present MEBT input beam performed
  Simulation with complete field maps (RF and PMQ) debugged

## Slide 13
WP3: NORMAL CONDUCTING
FRONT END
DTL
RF
  Study of Beam loading effects in equivalent circuit
  Study of post couplers mechanism
  Thermo mechanical simulation to evaluate deformation and frequency detuning in operation
Cooling system
  Water requirements definition in progress (temperature, mass flow, pressure drop, water velocity, etc.)
  Drift tube cooling channels redesign in progress
Prototyping
  Test bench for BPM characterization complete, order placed for moving motors
  Test bench for PMQ measurements definition of specifications in progress
  EBW procedures for drift tube assembly, tolerances and tooling definition in progress

## Slide 14
WP4: Spoke Cryomodules
Achievements
Prototype cavities:
Spoke cavities prototype fabrication at Zanon and SDMS is ongoing. SMDS is announcing 1 month delay, whereas the situation at ZANON is still worrying: the first milestone (fabrication plans) was completed with a 3 months delay. But Zanon, up to now, did not provide an updated planning to figure out if this delay will be partially recovered in the fabrication phase. Both companies are followed very closely (including monthly reports).
Power couplers:
Both companies are late on the first milestone (completion of the fabrication drawings), by 1 month. This delay, for the moment, is not linked to a technical showstopper. A visit to both companies to validate the fabrication drawings is scheduled in December.

## Slide 15
WP4: Spoke Cryomodules
Achievements
Power couplers:
The design of the power coupler coupling cavity for the conditioning bench is achieved. Tendering is ongoing and company choice will be made on the 10th December.
Design of the doorknob transition is close to completion. It has been adapted to the ½ height waveguide.
4 Power coupler outer conductors (including the cooling channel) have been ordered to Sominex. Lead time is 23 weeks.

## Slide 16
WP4: Spoke Cryomodules
Achievements
Cold Tuning System:
  The fabrication of 2 cold tuning systems (CTS) is achieved, and all parts have been received and checked at IPNO. The CTS detailed design report has been released. A set of tests at room temperature are scheduled for the coming months.
  Everything has been prepared for the tests at room temperature: the CTS was assembled on the Eurisol triple-spoke and the tests will be performed in December and January
Cryomodule:
  Detailed design close to completion: last achieved work and design updates are on
    the change to a cryomodule central connection to the jumper
    more detailed design of the toolings for the clean room assembly
    integration of alignment control devices (fiducials, alignment windows)

## Slide 17
WP4: Spoke Cryomodules
Achievements
Cryomodule:
  Fabrication completed for
    the power coupler protections
    the mock-up of the barometric compensation system-
General:
  Prepared for and hosted WP4/WP5 Audit
  Dedicated meeting on cryogenic interfaces on the 21st November
  Workshop on the spoke cavity test plan at Uppsala on the 20th & 21st November.

## Slide 18
WP4: Spoke Cryomodules
Issues
Delivery Time for Prototype Cavities

## Slide 19
WP5: Elliptical Cryomodules
Achievements
  Completed the first version of the Requirements level 3 & 4 for the Medium and High-Beta resonators (EMR), and RF system (RFS) with Identification of interfaces.
  High-beta prototype cavity manufactured by ZANON:
    Cavity delivered at Saclay.
    Field flatness measured after manufacturing and transport: 86% (excellent!).
    Visual inspection with a CCD camera, vacuum test with final alumina gaskets
    Modification of the electropolishing bench and preparation for a standard chemical BCP treatment (after the unsuccessful test of the SPL cavity)
    Acid mixture ordered. Delivery foreseen in January 2014.
    Preparation of the field flatness tuning bench

## Slide 20
WP5: Elliptical Cryomodules
Achievements
  High-beta prototype cavity manufactured by RI:
    2 dumbbells welded, 2 extremity tubes welded with half-cells and 4 half cells deep drawn.
    Visit of Saclay team for RF measurements (week 41). Check RF measurement system at RI. The system, which is based on the one used for the SNS cavities, works properly.
    Start the trimming of 2 dumbbells after RF measurements.
    Reshaping by spinning of the 3 half cells that did not met spec. Waiting for news about fabrication and schedule impact
  M-ECCTD cavities:
    Completed the market survey (2 competitors Zanon and RI).
    The call for tender documentation is complete. It will be sent to the candidates by the commercial office before the end of the first week of December.
    Signatures for the niobium procurement are almost complete.

## Slide 21
WP5: Elliptical Cryomodules
Achievements
  M-ECCTD Ceramic windows of the 6 power couplers:
    Completed market survey and initiated discussion with companies.
    Completed and analyzed the first test of the coupler flange pressure compensation system. Modifications requested to validate the system (stiffer springs needed).
    The 2 candidates sent incomplete documentation. Questions for additional information are being prepared and will be sent. The commercial procedure will probably be modified afterwards in order to increase efficiency.
  Completion of the WP5 audit (28 & 29 October)
  Updated primavera (cost and schedule) to reflect French IKC potential as a vendor quote.

## Slide 22
WP5: Elliptical Cryomodules
Achievements
  Workshop on WP4/5 and WP11 interfaces hosted at IPNO on November 21st.
  Workshop onWP5 interfaces with ICS hosted at CEA on November 22.
  Initiated the preparation for certified body (European Directive) for the design of the elliptical cavity cryomodules.
  Calculated the HOMs for the medium-beta elliptical cavity to comply with L4 requirements.
  Initiated the operating modes and process variable to operate the cryomodules and to define the relevant MPS system.

## Slide 23
WP5: Elliptical Cryomodules
Issues
  SPL cavity chemical and electrochemical process to be modified. Anticipated delay for high-beta prototype cavity tests: minimum 4 months, but no impact expected to the Medium Beta ECCTD schedule
  Significant HOM found in the medium beta cavity: redesign of the cavity required in order to allow the propagation of the HOM outside the cavity.
  Delay on the production of the RI prototype cavity.
  Delay in call-for-tender development for the power-coupler ceramic windows.

## Slide 24
WP6: HEBT & Magnets
Achievements
  Lengths of the linac warm units (LWUs) have been evaluated and finalized. The revised linac layout including the longer LWU’s is called Optimus+. To facilitate end-2-end (ion source to target) beam simulations, the HEBT has been updated accordingly. The UHB section of the HEBT now includes 21 periods available for linac extension argued as extra performance upgrade and contingency.
  The HEBT layout (raster24) has been chosen for the November baseline of the accelerator and has been distributed among engineers at the ESS.
  Participation in the TAC review and collaboration board meeting held in Uppsala.
  Input to the planned radiation studies being conducted by Huddersfield in the A2T region.
  Abstracts submitted to IPAC’14 in Dresden.
  Clarifications of the definition defining the new lattice layout based on the Optimus+.

## Slide 25
WP6: HEBT & Magnets
Achievements
  A study has been made on pulsed-magnet operation of the LWU and HEBT magnets. The quadrupoles, and the associated power supplies, in the LWU’s (elliptical) have been chosen as the case being studied, as these magnets are largest in number. The study shows that whereas the magnets will only be slightly cheaper for pulsed-operation, the power supplies will be around an order of magnitude more expensive. In addition, the pulsed-magnet power supplies will have to be developed is contrast to the off-the-shelf dc power supplies. The only advantage of the pulsed systems is the avoidance of water cooling in these. The initial conclusion is that we still recommend dc water cooled systems.
  Preparation has started on the studies of the longitudinal acceptance of the HEBT.
  Work continued in optimizing and reducing costs of the radiation shielding in the A2T region.

## Slide 26
WP7: Beam Diagnostics
Achievements
  Interviewed several promising candidates for BI engineer positions.
  Several group members attended the ICS iWeek. Many critical issues discussed.
  BPM wire test bench parts ordered.
  Optics setup for non-invasive profile tests in Stockholm completed.
  SLAC CRADA finalized. Sent for signatures. Andrew Young to visit ESS in mid December following uTCA workshop at DESY.
  DESY completed a preliminary design of cold linac button BPMs, using a larger version of the XFEL button. Prototype BPM body was built in DESY workshop. Effort will continue with EM simulations and detailed design of button.
  Work with DESY on firmware for Beam Current Transformers. Discussion on possible DESY involvement in BPM. Ordered Struck 700MHz RTM down-converter for BPM tests.
  Progress on MoU with DESY to cover joint work until in-kind agreement can be in place. Work so far has been pro-bono from the DESY side.

## Slide 27
WP7: Beam Diagnostics
Achievements
  Cold linac BPM prototype delivered (milestone)
  Reviewed quotes for LEBT Faraday Cup with procurement. Order to be placed early 2014.
  Completed initial study of Faraday cup heat loads and stresses (short term contract).
  Produced note on OTR photon yield. Possible applications for target profile and longitudinal diagnostics.

## Slide 28
WP7: Beam Diagnostics
Issues
  Some LEBT diagnostics slated for early in kind from CEA Saclay. Agreement need to be in place by end Q1 not to affect delivery to Catania test.
  Level 3 and 4 requirements for BI not finalized.
  Annual review recommended reviewing BI scope based on a plan for commissioning and operations. Such a plan needs to be developed to a level where diagnostics requirements can be derived.

## Slide 29
WP8: RF Systems
Achievements
  Re-costing as a result of the redesign was completed. WP 8 is within the cost targets.
  Tender returns for the modulator prototype were reviewed.
  Final interviews with candidates for the five positions to fill were made and completed for all positions. Two candidates have so far signed contracts, and offers are pending for another two candidates.
  WP 8 presented WP3, 4, 5, and 8 during the review accelerator sub-committee break-out session of the Annual Review.
  An updated TDR RF chapter was written
  Discussions with Cosylab were held regarding help for interlock system

## Slide 30
WP8: RF Systems
Issues:
  704 power coupler conditioning still under discussion
  The review of the modulator prototype tender returns may need an external jury committee. This will delay the decision, and there is a risk that the contract award rolls over into 2014.
  The modulator prototype for CERN will roll over to Jan 2014.

## Slide 31
WP10: Test Stands
Achievements
Phase I:
  Defined with LU the location location of test stand. This completes a project milestone.
  Progress on equipment choice for power transformer and cooling received budget offers
  Advanced on design for cooling system. There’s an opportunity to use the chilled water of the building as heat sink
Phase II:
  Refined Primavera schedule and dependencies to other WPs
  Hilko Spoelstra started on 1 October as a test stand engineer
  Redesigning layout of test stand due to reduced available space (gallery width was reduced by 500 mm)

## Slide 32
WP10: Test Stands
Achievements
  MS2 (Agreement on requirements for cryogenic supply) has been postponed in accordance with WP11. This agreement relies on heat load data from WP05, which is not yet available. Expected delivery on 2014-01-31. No impact on overall schedule is foreseen
  Significant progress by Uppsala University has been made at the FREIA Facility (which will be used for spoke cryomodule testing) Utilities are being installed in the hall and construction of the test bunker is well advanced. Uppsala hosted a FREIA workshop in November to describe the status and next steps. Both the cryogenics and the horizontal test cryostat should be ready in mid 2014

## Slide 33
WP10: Test Stands
Issues
  Available width of the klystron gallery has been reduced by 500 mm Consequences can be reduced space for movement of equipment and people in the test stand area
  Specification of transport of CMs from manufacturer is not clear, consequences can be increased workload for preparation of CMs before testing. Risks are lack of manpower and especially lack of work space to perform these modifications.
  Resources for testing of elliptical CMs may be too low. Risks are lack of manpower for execution of testing. An evaluation of the resource needs is ongoing.

## Slide 34
WP11: Cryogenics
Achievements & Activities
  Videoconferences with both companies contracted for the industry studies on the linac cryoplant have been held. One of the companies (Linde) has sent the intermediate report, the other (ALAT) will follow the first week of December.
  Decision on safety factors used for the heat loads in the cryodistribution system has been made. Based on this a refined technical note regarding heat load requirements has been issued which will be the working document until official figures from WP4 and WP5 are finalized until end of 2013. Substantial deviations however are not expected.
  A workshop for the interfaces of the cryogenic distribution (WP11) with the cryomodules (WP4 and WP5) has been held in Orsay, clarifying a number of issues. The 3d model for the valve box to be used for the prototype tests in Orsay and Saclay takes shape, a first version has been sent to France
  The first draft of some specification documents for the linac cryoplant, including award criteria, has been prepared and is circulating for internal checks.

## Slide 35
WP11: Cryogenics
Achievements & Activities
  Discussions about liquefaction requirements of the test and instruments plant have started, resulting in the fact that the plant design is governed by the CM test requirements rather than those of the instruments.
  Discussions about helium recovery in the neutron instrument halls have taken place with SAD and CF. Minutes with a common understanding of scope, responsibilities and schedule have been issued.
  Intense discussions and workshops with ICS including teleconferences with the vendors were held, leading to a better understanding of all sides and the preparation of the respective section in the technical specification.
  A first meeting regarding the target cryoplant as preparation for the review in December has taken place, addressing critical issues like interfaces between Target, CF and WP11, manufacturers etc.

## Slide 36
WP12: Vacuum
Achievements
  Participation in ESS-FREIA spoke cavity RF review and planning meeting held in Uppsala.
  Preliminary discussion with the BI group on the testing of BPM in the LWU’s
  Started preliminary assessment of the pumping requirements for the vacuum insulating jacket of the hydrogen moderators.
  Ongoing review of the first draft of the ESS Vacuum Manual continues together with the organization of the vacuum standardization meeting to be held in Lund during the first quarter of 2014.
  Work continues with the Chopper group in setting up their vacuum test equipment.
  Work has started in determining rack space requirements and cable requirements.

## Slide 37
WP12: Vacuum
Achievements
  A two-day introductory training course in vacuum technology was held at ESS Feedback has been positive and further vacuum technology training course will be planned in the future as needed.
  Activities are now being directed towards establishing an element database and naming convention for the vacuum system and vacuum components together with the development of a CAD database for standard vacuum elements.
  Work has commenced on the development of the ESS vacuum manual and on the standardization of vacuum components.
  The design of the “Low Energy Differential Pumping” unit is under way with initial activities directed toward the optimization of the vacuum layout needed to minimize the particle flow into the first spoke cavity within the constraints dictated by the accelerator lattice and optics design.
  Meetings were held at ESS Bilbao to discuss the requirements and potential configuration of the MEBT vacuum systems and the location of beam line isolation valves.

## Slide 38
WP13: Safety & Reliability
Achievements
  Presentation on Safety and Availability work in AD at the Annual Review, as well as an ad hoc presentation on accelerator shielding requested in the management break-out session.
  Continued work on A2T shielding assessment. Seeking endorsement from SAG on accident scenarios, as A2T is not covered in the shielding strategy document, and no general guidance document exists.
  Radiation study of high bay, ventilation shafts and emergency exits done. Ventilation shafts need minor adjustment.
  Agreed on high level reliability and availability targets for ESS in XFWG, and presented to CCB.
  Reorganized and documented reliability model of ESS. Presented to XFWG and MPS meeting.
  Re-scoped WP13 to adjust for target guidance 3 FTEs average for the length of project.

## Slide 39
WP13: Safety & Reliability
Issues
    Engineering safety and Personnel safety needs to be covered centrally, as the allocated resources in AD are not sufficient
    CF declared mobile shielding in A2T as not part of building cost. This issue may be resolved as part of the A2T Value Engineering Process
    Need input/endorsement from SAG on accident scenarios in A2T (in particular length of beam accident).
    Annual review made recommendations on shielding and accident scenarios, largely in line with current work. Response is being prepared.

## Slide 40
WP14: Accelerator Redesign Effort
See Dave McGinnis’ Talk

## Slide 41
WP15: Cooling & Electrical Support
Achievements & Activities
Electrical system
  CF and WP 15 are planning an “ESS Electrical power system”-seminar aimed at users of electrical facilities (UPS-, Backup- and Electrical- Power) and system designers/buyers. CF will deliver input.
  Provided input to CF, Annika Nordt and Scanpower on electrical system risks.
  Several meetings with CF and transformer manufacturers (Siemens, Schneider and ABB) to get information on which requirements they need to properly rate transformers and the characteristics of dry-isolated and oil-isolated transformers
  Time and resource planning for WP15 electrical systems is completed. Cost and scheduling adjusted to better fit the “spending profile” of the project – the main change is that costs & tasks for the High Beta section have moved in time.

## Slide 42
WP15: Cooling & Electrical Support
Achievements & Activities
Electrical system
  F. Jensen attended the 2nd workshop Energy for Sustainable Science 2013 at CERN October 23-25 and presented as the “rapporteur” for session B4 “Green Technologies developed at Research Infrastructures”.
  Working with RF and Design Office to include power cables and cable routing in the 3D model. The design assumption is that the modulators may use 400 V, even at 660 KVA, this is driving a need for very thick conductors so the routing has to take this into account.
  Meeting with WP11 on cryoplant requirements. The vendors prefer to use high voltage (6.6 kV) for the large compressors, this is in line with what CF wants to provide and may also free up space in the Central Utility Building.
  Bi-weekly Meetings with CF on the design and layout of the electrical substations. There was an “gap-issue” with the electrical interface to the target systems, which we think can be solved by moving one of the electrical substations into the target building, where the helium compressors were located. CF is investigating if the magnetic field from the substation will be a problem for instruments.

## Slide 43
WP15: Cooling & Electrical Support
Achievements
  Grid simulation project meeting with Michael Bader from Ampegon at RWTH Aachen. Ampegon presented their proposed modulator concept to the RWTH simulation team. The ESS grid simulation will include the front-end of the Ampegon modulator proposed for the ESS test bed in Lund.
  Cooling System
  Second cooling system risk meeting held with Annika Nordt and Scanpower this month, focusing on interface between cooling system and technical equipment. Identified risks, and evaluated if they require linking to MPS. There were a few items to follow up on, but generally concurred that cooling system signals and controls will not need to tie directly into MPS.
  Participated in WP3 (warm end linac) audit. Notes relevant to cooling – Ion source cooling design is complete, RFQ cooling requirements will be defined by May 2014, DTL tanks may have (5) individual cooling skids for each of the (5) DTL tanks.

## Slide 44
WP15: Cooling & Electrical Support
Achievements
Prepared material and hosted Cooling Water systems seminar with CF personnel. Invited representatives from ACCSYS, Target, NSS & CF to explain current system design, data we need from the different projects, etc. Currently meeting with representatives from ACCSYS, Target, NSS & CF to further collect and clarify cooling requirements from their systems. In November, held meetings with:
  WP6 – magnets (Peter Ladd)
  NSS – (Michelle Everett, Arno Heiss, Iain Sutton)
  Target – (Per Nilsson, Steve Gallimore)
  WP11 – Cryo (Philipp Arnold, Xilong Wang)

## Slide 45
WP15: Cooling & Electrical Support
Achievements
Recent findings include a significant reduction in cryoplant cooling, and elimination of requirement for cryoplant cooling from the low temperature loop. Target is currently re-working all their heat flow requirements, and should have some updated figures by start of December. However, they expect that they may be able to decrease the overall cooling requirements on the order of 1 MW.
Working this month with RF and Design Office personnel to work out details of equipment layout and cooling water piping distribution in the klystron gallery. We have in principal agreed on the configuration and extent of CF cooling water pipe distribution in the klystron gallery, and are working to hammer out details of routing.
Attended 2nd workshop Energy for Sustainable Science 2013 at CERN October 23-25, presented “High Temperature Cooling of Cryoplants and RF Systems at the European Spallation Source”.

## Slide 46
WP15: Cooling & Electrical Support
Issues
Electrical & Cooling: The WP15 electrical costing contains assumptions about the required amount of CAD design work, which still needs further analysis and confirmation.
Electrical: The procurement of an electrical CAD package is progressing, but slowly. There is a risk that there will be system setup-time and a learning curve that will stretch into 2014.

## Slide 47
WP99: Accelerator Infrastructure
& Installation
Achievements
  Preliminary integrated installation plan has been revised to include 2015-2022 WP99 milestones and activities. WBS codes and descriptions together with external links have been revised as well.
  Accelerator envelopes have been completed and passed to CF for review.
  The Optimus + stubs have been baselined. The new CTL position has been defined as well. CF has received the new info and will adapt the gallery structural columns.
  Data on the following action items are being collected and requirements are being generated:
    Loads from main systems (CMs, RF distribution, LWU, cooling);
    Gallery infrastructure supported from roof;
    Heavy equipment handling;
    Floor flatness and finish;
    Gallery drainage;
    Tunnel and gallery HVAC needs;
    Cables and racks.

## Slide 48
WP99: Accelerator Infrastructure
& Installation
Achievements
  Detailed layout of equipment in the Gallery is being planned with input from the RF Group
  A new hire, (Nick Gazis) will start on Feb. 1st as Sr. Mechanical Engineer in the Specialized Technical Services.
  All first interviews for the Electrical Engineer position have been completed. Onsite interviews for leading candidates are being planned.
  ACCSYS alignment network needs and deadlines are being discussed with new Survey & Alignment Engineer in the Design Division
  Work on Accelerator Technical Spaces (ATS) is on going. Needs from ATS stakeholders have been received and discussed.

## Slide 49
WP99: Accelerator Infrastructure
& Installation
Issues
Additional cables procurement responsibilities have potential cost escalation.
Responsibilities concerning transport to Lund of main accelerator systems still undecided. This may have substantial cost impact.
Data management implementation (document management system, CAD PDM, 3D assembly structure) remains an issue

## Slide 50
Work Package Audits
Audits were held on the following WPs:
WP11 (Cryogenics): Sept 10
  External Member: H. Quack
WP3 (NCFE): Sept 26 – 27
  External Chair: J. Stovall
WP4 & WP5 (Cavities & Cryomodules) Oct 28 – 29, IPN Orsay
  External Chair S. Pattawar
  External Member: P. Michelato

## Slide 51
Work Package Audits
All WPs showed significant technical detail and in many cases advanced designs were presented
The WPs are in good shape and no technical “showstoppers” were identified
The audits included the first external WPs to be audited and the use of external chairs worked well and added value.
The addition of external experts on the panels as appropriate was valuable
Combining the audits of WP 4 and 5 was both efficient and reasonable given the linkages between them
Holding the WP 4&5 audit at IPN Orsay was very good as it allowed the ESS staff to meet the entire team and see the facilities
Detailed recommendations have been created and are being addressed

## Slide 52
Work Package Audits in 2014
Work Package | Date
WP15 Electrical & Cooling | January 31
WP6 HEBT & Magnets | February 6
WP99 Integration & Installation | February 14
WP12 Vacuum | March
WP2 Beam Physics | April
WP10 Test Stands | May
WP7 Beam Instrumentation | June
WP8 RF | August
WP11 Cryogenics | Sept
WP4/5 Cavities & CMs | Oct
WP3 NCFE | Nov
WP13 Safety & Reliability | Dec

## Slide 53: Risk
A Risk Workshop was held with all the WP Leaders in September. The result is an updated Risk Register for the ACCSYS project.
This currently contains 55 risks. Some of the original risks have been retired or combined with others
This register was presented at the review and no significant issues were found
The register will be reviewed and updated with the WP Leaders on a monthly basis during the Project Support Meetings
Future Changes will be reported at the TB Meetings in this talk

## Slide 54: Example from ACCSYS Risk List

## Slide 55
Issues
Determine responsibilities for controls and transport associated with the cryomodules
Greater detail on commissioning and operations plans required
Optimize beam diagnostics to meet defined commissioning and operations requirements and cost goals
Assist ES&H Division in setting lab safety polices and requirements
Need to finalize IKCs consistent with project schedule requirements.
Delivery time on both Spoke and Elliptical prototype cavities may be late and is being closely monitored

## Slide 56
Comments
The Annual Review had a successful outcome. The project scope, cost, schedule and risks are consistent and well defined
  ACCSYS is in the process of responding to recommendations
Work Package audits highlight the significant amount of detailed engineering and design work accomplished to date
Recruitment is going well with important additions to the team since the last TB. The pace will increase in 2014
With the review and the accelerator redesign mostly over, we will now move more into carrying out the plan. Prototypes, major procurements and detailed design all planned for 2014

## Slide 57: Next Steps (2014)
Complete response to review committee recommendations
Long lead procurements
  Place orders for initial IOT and modulator prototypes, cryogenic distribution system etc.
  Release Request for Proposals for the accelerator cryoplant
Finalize IKCs
Work to the existing plan (apply formal change control processes)
  Detailed design and specification
  Meet updated 2014 milestones
  Accurate EVMS and variance reporting

## Slide 58: Next Steps (2014)
Determine responsibility for cryomodule controls and transport
Develop detail on commissioning and operations plans and their impact on beam diagnostics
Standards development: vacuum handbook, cryogenics handbook, grounding grid etc.
Further define interfaces with ICS, NSS and Target. Develop prototype controls as appropriate
Finish recruitment consistent with staff plan