## Slide 1
Site & Conventional Facilities
IKON 6
Magnus Eneroth
Construction Manager
Conventional Facilities
www.europeanspallationsource.se
February 27, 2014

## Slide 2
Infrastructure Directorate
Örjan Larsson
Personal Assistant Inger Persson
Environment, Safety & Health (ESH) Division Peter Jacobsson
Ulrika Agnvik
Thomas Hansson
Gitte Myhré
Daniel Skölde
Fredrik Jörud
Energy Division
Thomas Parker
Erica Lindström
Fredrik Indebetou
CF Design Jan Molander
CF Construction Magnus Eneroth
Design Project Accelerator K Svedin
Design Project Target Bldg F Bergstedt
Design Project Instruments J Lundgren
Design Project Aux Bldgs R Sjöholm
Design Project Earth Works B Hedén
Design Project CUB R Sjöholm
Overall Design Coordination
Architectural
Helle Basse Larsen Boris Kildetoft
System Installation Ronny Sjöholm
Fredrik Bergstedt Jan Lundgren Jörgen Mattsson
Structural
Magnus Jakobsson Emma Segerstedt Karin Svedin
Earth Works/Geotechnical
Björn Hedén
Construction Management
Emma Segerstedt
Magnus Jakobsson
CF Support
Environment/OHS
Malin Åberg
Quality Assurance
Lars Persson
SE/BIM/Risk
Fredrik Österberg
Test & Commissioning Jörgen Mattsson
Site & Logistics K Sjöstrand
Installation Coordination L Hedenklo
Installation Coordination J Lundgren
Construction Coordination B Hedén
Installation Coordination NN
Installation CoordinationNN
Installation CoordinationNN
A
S
I
A
S
I
A
S
I
A
S
I
A
S
I
A
S
I
Installation CoordinationNN
CF Planning Anders Thonäng
CF Estimation/Cost Control Karin Wennerholm
CF Admin Ulrika Hammarlund
Conventional Facilities (CF) Division Kent Hedin
Organization

## Slide 3
2013
2014
2015
2016
2017
2018
2019
Conventional Facilities - Schedule
 | 2011 | 2012 | 2013 | 2014
Building Program |  |  |  | 
Architectural Competition |  |  |  | 
Feasibility Study |  |  |  | 
Baselining/ Scrubbing |  |  |  | 
Preliminary Design |  |  |  | 
Detailed Design |  |  |  | 
Procurement Contractor |  |  |  | 
Construction Start |  |  |  | 

## Slide 4: Design Phases
The development of all required documents and data for the Project is divided into 3 stages.
Feasibility Study
Development of concepts and viable options taking into account stakeholder needs, time and budget constraints. Resulted in a CF Baseline for Accelerator, Target & Experimental Halls in August 2013.
Preliminary Design An Assessment of the Feasibility Study and alternative part solutions resulting in a main proposal for fulfillment of the project goals.
Detailed Design
The Detailed Design encompasses and implements the Preliminary Design decisions. All drawings and documents necessary for construction will be reviewed and collected in appropriate sub-projects.

## Slide 5: Status Conventional Facilities
Start Detailed Design
Completing test piling on site
Start collaboration with construction Contractor
Building permits
Environmental monitoring program
Planning for the construction start

## Slide 6
2013 |  |  |  |  |  |  |  |  |  |  |  | 2014 | 
Jan | Feb | Mar | Apr | Maj | Jun | Jul | Aug | Sep | Okt | Nov | Dec | Jan | Feb
Procurement Legal Advisor
Developing Contract
Developing PQQ
Prequalification
Tender period
Tender Evaluation
Developing ITT
Procurement Strategy Approved
Contract Award

## Slide 7: Collaboration Contractor
One of the world's ten largest construction companies.
57,000 employees
Home markets in Europe (Sweden, Norway, Finland and Estonia, Poland, Czech Republic, Slovakia, Hungary, the UK), the U.S. and Latin America.
Largest home market is the U.S., followed by Sweden.
Revenue € 15 billion

## Slide 8
Supporting resources from CF to the Project
Planning
Sustainability
Quality
Installation Support
System Engineering/BIM
Risk
BREEAM Coordination
Cost Control
Planning
Sustainability
QA
Site Engineer
Purchasing
Installation Coordination
= Contractor Resource
= ESS Resource
Production
Manager
Part 1
Block Manager
Block Manager
Block Manager Early Earth Works
Site Engineer
Design
Design Coordinator 1
Design Coordinator 2
Design Coordinator 3
* Some resources may work less than 100%.
Collaboration Organization – C101
Installation Coordination
Installation Coordination
Construction Coordinator
Coordinating Bas-U
Site Facility Team
Administration
Installation Coordination
Project
Manager
Ass.
Project
Manager
Installation Coordination
Procurement
Site Engineer
Notes: Assumed Collaboration Organization – C101 – phase 1, part 1, month 2

## Slide 9
Month -1 |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Team Building & Contract review
Organization Phase 1
Scope Phase 1
Workshops for Design, OHS, QA, Schedule etc.
Total Works Cost Estimation Part 1
Detailed Schedule Part 1 & Main Schedule Part 2
Performance Plan
Procurement of Subcontracts
Collaboration activities, create a common view on collaboration
Design Development
Set Target Cost 1
Preparation for Construction Start June 2
Common Design Org. Update Design Mgmt. Plan, describe in Performance Plan
CF PREP WORKS
Common office @ ESS
Finalize Performance Plan & Schedule
Start of Construction

## Slide 10: Contract schedule
Option 1
Planning
Target Cost
Contract signed
Detailed Design
Phase 1
Phase 2
Part 1
Incentive
Target Cost
Phase 1
Phase 2
Part 2
Incentive
Construction
Preliminary Design
Environmental Court Verdict
Call off Option 3
Option 2A
YES
Option 2B
NO
Option 4A
YES
Option 4B
NO
Option 3
Planning

## Slide 11
1 Collaboration Contract
Phase 1
Phase 2
1.1 Special Conditions Phase 1
Part 1
Part 2
1.2 Construction Contract Part 1 with Target Cost
Target Cost
1.3 Construction Contract Cost Plus Part 1
Target Cost
1.4 Construction Contract Part 1 and Part 2 with Target Cost
Target Cost
1.5 Construction Contract Cost Plus Part 2
Target Cost

## Slide 12: Governance & Reporting
Project Organization
Steering Group (2+2)
Client’s representative
Contractor’s representative
Project Management Team
Project Managers (1+1)
Responsibility
Reporting

## Slide 13: Target cost
Target Cost
Total Works Cost
Design Cost
Risks reserve
Phase 1 costs
Phase 1 costs = The Contractors costs invoiced for the Phase 1 works performed
Risk Reserve = Construction Risks
Design Cost = The Clients design cost from March 1, 2014 to completion
Total Works Cost = The Production estimate

## Slide 14
Project Cost
Target Cost
  Project cost < Target Cost
  50/50
  Contractor gets 50% of the savings
  Project cost > Target Cost
  70/30
  Contractor paid 70% of verified costs above TC
  Capped at 10% of TC
Incentive
Incentive

## Slide 15: Design consultants
Originally Framework agreements with
  Sweco
  WSP
  ÅF
  Tyréns
New Public procurement late 2013 => Framework agreements
Sweco, WSP, ÅF, Tyréns
Cowi, Fojab, Gronmij, Hifab, Reijlers, Arup
Architect Henning Larsen procured early 2013
Notes: 10-15 in 6-9 mon => 0,5 M – 1,25 M

## Slide 16
2013
2014
2015
2016
2017
2018
2019
DETAILED DESIGN
Conventional Facilities - Detailed Schedule
AUX. BLDGS
ACCELERATOR BLDG
TARGET BLDG + EXP HALLS 1,2
EXP HALL 3 + GUIDE HALLS
AUX. BLDGS
MAIN UTIL.(GROUND)
EARTH WORKS
MASTERPLAN GENERAL ARCH.
Design Phases
Construction Phase
CONTRACT SIGNED
START OF CONSTRUCTION
CUB OPERATIONAL
EARLY ACCESS COLD BOX & COMPRESSOR BLDG
EARLY ACCESS KLYSTRON GALLERY
PART 1 FINAL INSPECTION
FULL ACCESS ACCELERATOR
EARLY ACCESS EXP HALL 1
EARLY ACCESS EXP HALL 2
EARLY ACCESS EXP HALL 3
FULL ACCESS EXP. HALL 1 & 2
FULL ACCESS EXP. HALL 3
FULL ACCESS TARGET BLDG
FULL INSPECTION
PRELIMINARY DESIGN

## Slide 17: ESS is co-located with Max IV and Science Village in close proximity to Lund
Max IV
Science Village
Lund
ESS
E22 Highway

## Slide 18
The architecture of ESS
Architectural design competition Five architect consortia was preselected in an international architect competition and competed to design the ESS exterior. In February 2013 the winner was announced by the ESS jury: Henning Larsen Architects was selected to develop the final architectural design together with the ESS team.

## Slide 19: Architectural Concepts

## Slide 20: The ESS Site covers 75 hectares
~ 1,2 km

## Slide 21
Conventional facilities | EPG 2013-10-28 | Masterplan Baseline
Perimeter detail 2013-10-25

## Slide 22: Accelerator Buildings without berm

## Slide 23: Section through Tunnel

## Slide 24: Gallery and Tunnel Colored volumes represent the machine

## Slide 25: Section through A2T

## Slide 26: HVAC and A2T