## Slide 1
Conventional
Facilities
Update
Michelle Everett
SAC 2014-02-05

## Slide 2: Level 100
Hall 1
Hall 2
Hall 3
Guide Hall
Bldg 1A
Bldg 1B
Bldg 2
Bldg 3A
Bldg 3B

## Slide 3: Level 110

## Slide 4: Level 120

## Slide 5: Level 90

## Slide 6
CF Baseline and Budget for NSS
Baseline for instrument halls and adjacent buildings  31,000m2
Construction | € 67,843,300
Installations | 
Electrical | € 5,392,900
Transport | € 4,800,000
Process | € 1,185,200
HVAC/BMS | € 7,507,600
Grand Total | € 86,729,000
At the end of December, we were at ~34,000m2

## Slide 7: Value Engineering workshop Hall 1
Façades on both short sides reduced 5m
All circulation on level 100 removed
Circulation on level 110 located inside crane coverage and dismountable

## Slide 8: Value Engineering workshop Hall 2
Façade on west sector adjacent to guide hall is reduced 10m, façade on north sector left as is. Overhead cranes will overlap by 2m
Lab and technical substation moved to north sector towards accelerator. Floor slab on upgrade area will not be built.
Façades on both short sides reduced 5m
All circulation on level 100 removed
Circulation on level 110 located inside crane coverage and dismountable
Stainless steel rebar in north sector reduced by 2/3.

## Slide 9: Draft of Instrument Positions

## Slide 10: Value Engineering workshop Hall 3
Crane coverage reduced to 20m
Perimeter facades will follow the radius given by the crane coverage

## Slide 11: Cost Saving?
Floor reduction ~2000m2 – leaving us ~ 1000m2 over
The roof is smaller
Reduced piling