## Slide 1: Update ESS Strain Rigs
Malcolm Guthrie
European Spallation Source ERIC

## Slide 2: Overview ESS stress rigs:
Up to 4 different rigs envisaged in plans:
“Rig 1” – 100kN rig manufactured by NPI, Czech Republic
”Rig 2” – 30-50kN rig, optimised for imaging
“Rig 3” – modular portable rig optimised for soft matter
“Rig 4” (“Robin’s Rig”) – not owned by ESS, but integrated portable rig.

## Slide 3: schedule
2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  | 
Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
RIG 1
BOT
INTEGRATION
COMMISSIONING IN LUND
DETAIL. DESIGN
PROC,MFG,ASSEMBLY
INTEGRATION
COMM LUND
CONCEPT. DESIGN
Gather requirements
RIG 2+3?
RIG 4
INTEGRATION
NOW
= system ready to deploy
Prev. plan:
Current plan:
2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  | 
Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
RIG 1
INTEGRATION
COMMISSIONING IN LUND
DETAIL. DESIGN
PROC,MFG,ASSEMBLY
INTEGRATION
COMM LUND
CONCEPT. DESIGN
Gather requirements
RIG 2+3?
RIG 4
INTEGRATION
NOW
BOT

## Slide 4: Rig 1 – 100kN “BEER” Rig
Device already exists. Physically located at NPI (Czech Republic)
Controls integration of project has been ongoing since early 2020
  progress has been a little slow,
    COVID
    lack of resources with partners
  to mitigate: considering reducing scope of integration to delay kHz time sampling
Mechanical integration:
  Decision to focus on BEER integration
  Requirements gathered from BEER team (https://confluence.esss.lu.se/display/SA/NPI-rig+mech+integration+Meeting+notes )
    installation boundary conditions,
    orientation of device,
    mounting interface (Level 1 Kipps on hexapod)
  Further work pending engineering resource (and 21 budget uncertain)
Safety/Quality integration
  hope to gain experience with Robin’s rig
  then plan to bring Rig 1 to Lund Q1/2021

## Slide 5: Robins rig
Device already exists. Physically located at ESS
Controls integration of project has not started
  Significant activities on defining project
Mechanical integration:
  Required requirements from instruments (https://jira.esss.lu.se/browse/PREMP-17)
    installation boundary conditions,
    orientation of device,
    mounting interface
  Very preliminary conceptual design (https://jira.esss.lu.se/browse/PREMP-20)
Safety/Quality integration
  Not started yet
  Some issues immediately clear

## Slide 6: Rigs 2 and 3
Have good set of requirements for Rig 2 in particular
Rig 3 is still less well defined.
Still haven’t coalesced on whether to go with commercial or collaborative solution.
Preliminary investigation into costs for commercial systems suggests might not be possible to buy two rigs