## Slide 1: ESS DTL beam commissioning
Preliminary ideas
Edgar Sargsyan
Accelerator Division
Beam Physics Group
Workshop on Beam Commissioning of Proton Linacs
Lund, April 8-9, 2014

## Slide 2: ESS DTL structure
7.62 m
60 drift tubes
Apert. r=10 mm
Lattice: F-0-D-0
31 PMQs
3 Steerers/plane
3 BPMs
Pbeam=53 kW
7.10 m
33 drift tubes
Apert. r=11 mm
Lattice: F-0-D-0
18 PMQs
3 Steerers/plane
3 BPMs
Pbeam=98 kW
7.58 m
28 drift tubes
Apert. r=11 mm
Lattice: F-0-D-0
15 PMQs
3 Steerers/plane
3 BPMs
Pbeam=142 kW
7.84 m
25 drift tubes
Apert. r=12 mm
Lattice: F-0-D-0
13 PMQs
3 Steerers/plane
3 BPMs
Pbeam=185 kW
7.69 m
22 drift tubes
Apert. r=12 mm
Lattice: F-0-D-0
12 PMQs
3 Steerers/plane
3 BPMs
Pbeam=225 kW
DTL Tank 3
DTL Tank 4
DTL Tank 5
DTL Tank 2
DTL Tank 1
56.8 MeV
39.1 MeV
73.8 MeV
89.8 MeV
21.3 MeV
3.6 MeV
IS
LEBT
RFQ
MEBT
DTL
Spoke
Medium β
High β
2.1 m
4.5 m
3.8 m
39 m
56 m
77 m
179 m
0.075 MeV
3.6 MeV
89.8 MeV
216.6 MeV
570.5 MeV
2000 MeV
352.2 MHz
704.4 MHz

## Slide 3: DTL commissioning objectives
Transport the beam to the spokes
Match the beam to the spokes
Gain the right beam energy in each tank
Optimize beam parameters
Minimize beam losses

## Slide 4: DTL beam diagnostics
3 BPMs per tank
1 BCT after each tank
1 FC, 1 WS or 1 NPM (Non-destructive Profile Monitor) after the Tank 1
2 BPMs in the Low Energy Differential Pumping (LEDP) section
1 WS or 1 NPM and 1 BSM in the LEDP
1 FC at the end of the LEDP
BLMs next to each tank
FC
Steerer
BPM
BCT
Steerer
BPM
Steerer
BPM
WS
NPM
Steerer
BPM
BCT
Steerer
BPM
Steerer
BPM
MEBT
Spoke
DTL 1
DTL 2
Steerer
BPM
BCT
Steerer
BPM
Steerer
BPM
DTL 3
Steerer
BPM
BCT
Steerer
BPM
Steerer
BPM
DTL 4
Steerer
BPM
BCT
Steerer
BPM
Steerer
BPM
DTL 5
Quad
BPM
WS
NPM
BSM
Quad
BPM
FC
LEDP
BLM
BLM
BLM
BLM
BLM
BLM

## Slide 5: Beam commissioning assumptions
Beam commissioning only ~3 months?
Hardware, software, controls, MPS and system tests done
MEBT beam well characterized and matched to the DTL Tank 1
Install all five tanks and then start commissioning
No use of movable benches – beam line diagnostics to be used
Max. beam power 0.5 kW, limited by the beam diagnostics (FC)
  Beam peak current 62.5 mA (nominal)
  Beam energy 89.8 MeV
  Beam pulse length 100 μs (nominal 2.86 ms)
  Repetition rate 1 Hz (nominal 14 Hz)
Other commissioning beam modes for particular applications TBD
Different possible operational beam modes: e.g. 6.3-62.5 mA in 10 steps

## Slide 6: Beam commissioning: longitudinal
Measurement | Method | Hardware & Diagnostics
a. Phase and amplitude scan (RF set-points) | Simulate and produce characteristic (“signature”) plots; Scan beam phase and energy vs. RF phase and amplitude | BPMs (+ BSM for Tank 5)
b. MEBT-to-DTL long. matching (fine tuning) | Optimize (minimize?) bunch length; Scan phase-energy separatrix | MEBT buncher(s) + BPMs MEBT buncher(s) + BCT
c. Beam energy | Time of Flight | BPMs in the following tank with RF off; BPMs in LEDP
d. Long. emittance & matching to Spokes | Linear transformation: tank field amplitude + BPM/BSM or 3 BPMs? | BPMs, BSM
e. Longitudinal tails? | Long. profile, different SEM gains | BSM?
f. Different beam modes | Reduce beam current using LEBT iris. Repeat points b&d? | LEBT iris + all above

## Slide 7: Beam commissioning: transverse
Measurement | Method | Hardware & Diagnostics
a. Trajectory steering | Algorithm TBD | Steerers + BPMs
b. Transmission/current | Tuning of different parameters | BCT, FC
c. MEBT-to-DTL matching (fine tuning) | Optimize beam transmission & profiles? | MEBT quads + BCT, FC, WS, NPM
d. Emittance after Tank 5 | Quad scan, linear transformation (feasibility TBC) + simulations? | LEDP quads + BPMs
e. Matching to Spokes | Method and feasibility TBC | LEDP quads + BPMs
f. Test different beam modes | Repeat all points above? | LEBT iris + all above

## Slide 8: Simulations
Simulations are important part of the commissioning preparation and the commissioning process itself
Use measurement data for beam optics simulations, determine expected beam parameters at different diagnostics locations
Compare measurement results to those expected from simulations
Possibility to generate a macro-particle beam distribution for simulations from an emittance measurement data

## Slide 9: Possible shortcomings
No transverse emittance measurements up to the end of the DTL
=> Proper matching of the MEBT beam to the DTL is very important!
How well can it be done?
The feasibility of the emittance measurement in LEDP and matching to the Spoke section TBC (especially with high space charge)
The feasibility/accuracy of the longitudinal emittance measurement TBC
Use of the FC as a beam stopper to be evaluated

## Slide 10: Thank you!
Comments and proposals are very welcome.