## Sheet1
No | Assignment | Recommendation | Status | Response
ATAC-010 | A. Jansson | Availability of 95% has a large implications on sub-systems – request clarification on this requirement in terms of frequency of long outages (neutron users do not care about short (< a few minutes) outages even though they add up to a few % unavailability) | Completed | The 95% target was set as a high level goal in the campaign phase. At that point, it was not clear if that would apply to the accelerator only, neutron production, or the etire facility. .In the current defintion, it applies only to the accelerator, and all interrruptions longer than a minute are included in the availability target.
ATAC-020 | M. Munoz | Optimize plan for staged installation and commissioning. It is recommended to plan for extensive down-time periods, so that the then shorter operation periods can be kept with more confidence. | in progress | Warm Linac: First draft finished, updated plan by 21 March, including comments from reviewers. Superconducting linac: First draft by 24st March. Updated version for the 30 of May. Finished document with the whole linac 8 April.
ATAC-030 | P. Ladd | The requirements for all materials, as well as welds/brazings (e.g. no grinding over welds, no brazings after welds..), which are in contact with high vacuum need to be defined urgently (outgassing, cleanliness, etc.). | Completed | The requirements essential for successful high vacuum operation including those sighted in ATAC-03 0 are addressed in the ESS Vacuum Handbook. Tthe ESS Vacuum Handbook is in the final stages of review prior to formal release. It is recommended that the Handbook be adopted as a Level 2 requirement.
ATAC-040 | A. Ponton | Study beam loss control over the complete beam current range (6.3 to 62.5 mA); consider use of fast chopper to modulate beam intensity. | In progress | The different beam current steps will be produced by an iris located in the LEBT. The ESS feed forward system does not need any current ramp up within the pulse. Beam loss studies are ongoing.
ATAC-050 | S. Molloy | In the level 3 requirements for spoke, medium-beta and high-beta linac, it is stated that 98% of the forward power has to be transferred to the beam. The RF power needed to fill the cavities (which is not transferred to the beam) should be included in this definition. | Completed | The purpose of this requirement was to enforce a choice of superconducting technology, so the requirement has since been reworded to say this explicitly, rather than attempting to force the solution by defining an arbitrary efficiency goal.
ATAC-060 | M. Eshraqi | Level 3 requirements (spoke, medium-beta, high-beta) limit the rms emittance growth per section to 5% and demand measurement as proof. These levels of emittance growth are very difficult to resolve and are probably not necessary for the overall performance. Either revise the numbers or give an emittance growth number for the complete linac. | To Do | The emittance growth will be adjusted for the whole SC linac instead of per section.
ATAC-070 | M. Eshraqi | Level 3 requirements (spoke, medium-beta, high-beta) limit the longitudinal bunch elongation per section to 5% and demand measurement as proof. These levels of emittance growth are very difficult to resolve and are probably not necessary for the overall performance. Either revise the numbers or give an emittance growth number for the complete linac. | To Do | The emittance growth will be adjusted for the whole SC linac instead of per section.
ATAC-080 | S. Molloy | The level of dipole HOM excitation should be verified for the maximum allowable beam displacement of 1.5 mm. | In progress | Preliminary results of simulations where transverse HOMs are excited for randomly misaligned cavities show no measurable effect with a displacement of 1.5 mm. Further studies are in progress to confirm this, and should be completed within the next 6 months.
ATAC-090 | S. Molloy | Level 4 requirements should contain numbers for field flatness (defined by beam dynamics). | In progress | We agree with this recommendation, and field-flatness requirements will be added to the level-4 documents. The number will be defined by the beam dynamics work package within the next year.
ATAC-100 | M. Eshraqi | Proceed immediately to error studies, as these are urgently necessary to define requirements for other systems, such as: Instrumentation requirements and device count; RF, magnet, instrumentation position tolerances; Collimation need / placement.Include systematic and individual cavity gradient deviations, missing cryomodules | In progress | The process of error studies on the latest design of the linac (Optimus+) has almost finished.
ATAC-110 | D. McGinnis | Carefully consider irreversible design considerations for > 2 GeV (e.g. target shielding) and protect if contingency allows. | In progress | This is an ongoing consideration during discussions with conventional facilities
ATAC-120 | A. Ponton | Test the Ion source as soon as possible - Plan to measure beam output quality (emittance) during tests. | In progress | Source tests are scheduled second quarter of 2015. An emittance meter will be available for the characterization of the source performances which are captured in the level 3 requirements.
ATAC-130 | A. Ponton | Design the pre-chopper iris in such a way that its longitudinal size be minimum, the LEBT be still capable to match the RFQ input parameters, the generated emittance growth be minimized, beam power handling capability be reliable, backstreaming of electrons be properly suppressed. | in progress | The mechanical design of the iris is finished. The device requires 300 mm longitudinally. Beam dynamics of the beam inside the LEBT with iris is being analyzed.
ATAC-140 | A. Ponton | Consider prototyping and tests of the RFQ 1.3 MW power coupler, unless an identical one has been constructed and tested. | in progress | This is part of the prototyping phase of the RFQ. Agreement with CEA Saclay to be signed 25th of March.
ATAC-150 | M. Eshraqi | Hold a detailed design of the RFQ review by RFQ experts in 2014 | To Do | We are planning to have the RFQ reviewed in the Q4 of 2014
ATAC-160 | M. Eshraqi | The committee recommends not to increase the aperture in tank 1 in order to concentrate potential beam scraping in tank 1 rather than having loss at higher energy. | Completed | The comment is valid and the apertures have not been widened
ATAC-170 | M. Eshraqi | The “cost” of having larger beam apertures after DTL tank 1 should be investigated. | Completed | The aTAC had also recommended to keep the apertures tight not to transmit losses to higher energies, therefore the study did not continue.
ATAC-180 | M. Eshraqi | The beam loss simulations using a “waterbag” beam with added 3-sigma Gauss components are not representative. Instead a beam should be used that has been tracked from the beginning of the RFQ through the MEBT. | Completed | The comment is valid. In the simulations we are using a gaussian beam generated at the input of the RFQ (cut at 4 sigma) and transported throught the rest of the linac. The same beam is used for error studies.
ATAC-190 | M. Eshraqi | Beam dynamics with quadrupole alignment errors showed too high losses. It remains to be shown that these losses can be reduced by the use of the BPMs and steerers, which are planned to be included in the empty drift tubes. | Completed | The error studies with and without the steerer and BPMs are done and the losses are reduced significantly by using the correctors. Additionally the tolerances have been tightened.
ATAC-200 | C. Darve | For the cryomodules, a higher operating pressure and consequently the application of the pressure vessel code should be considered. In this respect, advantage should be taken of the stiffening of the spoke cavities, bringing their maximum external pressure into the same range as that of the elliptical cavities | In Progress | The recommendation to increase the cavity operating pressure to more than 1.5 bara has been taken into acccount, while complying with the European Directives 93/27/EC and PED as originally expected. Meetings with authorized body held on February 18th (APAVE) confirms CEA first analysis. Contact with the Swedish notified body is planned this month. A level 4 requirement has been agreed upon by all ACCSYS WPs on the minumum working pressure of the helium return line.
ATAC-210 | S. Molloy | Verify with tests that the high beta power coupler has to provide a sufficient margin in power handling for safe operation on the high beta cavities. | Completed | Two couplers of the design intended for the high beta cavities were tested in 2009, and were able to reach 1.2 MW with a duty-cycle of 10% (albeit with a pulse length of 2 ms instead of the 2.86 ms pulse length intended for ESS). Nevertheless, we recognise the risk provided by the high power requirements on these couplers. In the event that the couplers cannot reach the required power, the machine may be operated successfully with lower voltage in these cavities, with the scope being regained at a later date through usage of the contingency space.
ATAC-220 | S. Molloy | Confirm the simulations of the HOMs in the cold cavities have with measurements | Completed | The verification that the cavity requirememts have been satisfied will include measurements of these modes. These measurements will be made at the prototype (technology demonstrator) stage, as well as on the final product.
ATAC-230 | T. Shea | Add beam instrumentation layout in the HEBT | Completed | Beam instrumentation devices are included in the latest lattice.
ATAC-240 | T. Shea | Consider collimation upstream of target approach (esp. off momentum in dogleg). | In progress | Completion: July, 2014 with release of a technical note updating the collimation stretegy. To gather input from experts, a workshop on beam loss and collimation has been scheduled for 13 and 14 May, 2014 (https://indico.esss.lu.se/indico/conferenceDisplay.py?ovw=True&confId=165). The specific issue of direct momentum collimation has been explored, and due to the low dispersion, it does not appear feasible. Indirect techniques and assurance of adequate momentum acceptance will be studied and discussed during the workshop.
ATAC-250 | M. Jensen | A clear definition of criteria for success of this technology should be established before the “go/no go” decision on IOTS at the end of 2017. | Completed | This definition has been created and is captured in “Selection Criteria for the High Power Source for the High Beta section of the ESS Linac“ ESS-00008307
ATAC-260 | A. Sunesson | Specify the phasing scheme between the two drive ports of the RFQ. | In progress | There is a coarse design - There shall be a splitter, which can be either a magic TEE or a Hybrid coupler. There shall be a phase-shifter for one of the output arms of the splitter, which will correct any differential phase shift between the two output arms. Details are under discussion with the lead engineer, and are also pending more information from RF distribution companies. This is expected end March.
ATAC-270 | A. Sunesson | Justify the rationale for the choice of 7/8 inch coax in the MEBT because of the associated insertion loss. | In progress | We are instead planning to use 1-5/8 inch line. Losses of 1-5/8 inch coax = 0.0113 dB/m (Losses of 7/8 inch coax = 0.0217 dB/m). For an expected transmission line length of up to 40 m, and a peak power level of 15 kW, the peak loss would be 1650 W along the whole lenght of transmission line. With a duty of 5% this would translate to 82 W loss over 40 m, or around 2W/m in thermal loss.
ATAC-280 | T. Shea | Consider beam loss implications at aperture reduction that limits target radiation back-streaming, if no upstream collimation is used. | In progress | Completion: July, 2014 with release of a technical note updating the collimation stretegy. To gather input from experts, a workshop on beam loss and collimation has been scheduled for 13 and 14 May, 2014 (https://indico.esss.lu.se/indico/conferenceDisplay.py?ovw=True&confId=165). Target division has launched a study of the backstreaming neutrons. The results will allow us to refine the geometry of this aperture and other features that limit damage to upstream components.
ATAC-290 | T. Shea | Verify that BLMs are adequate for 20 microseconds loss of raster errant condition (with simulations as much as possible). | In progress | Completion: May, 2014 with a presentation at the High Power Target Workshop.This presentation will summarize the strategy used to protect target station equipment from all credible errant beam conditions. A meeting of the ESS MPS team will also be dedicated to this topic. To clarify, the BLMs are used to detect errant tune of the quadrupoles and DC dipoles. Loss of raster will be detected by monitoring the raster magnets themselves and by monitoring the beam within the target monilith.