## Sheet1
No | Assignment | Recommendation | Status | Response
TTAC-08-01 | Eric Pitcher | Regarding System Engineering Approach: Minimize formal constraints to the technical contributors, but be strict of what is mandatory (e.g. quantified progress report). Create a high level, readily accessible parameter list immediately. | In-work | SE requirements are being tailored to meet the needs of the Target Project. Near term system engineering expectations and deliverables (Preliminary Design Review and Critical Design Review) identified and communicated to Work Package Leaders. Tailoring of longer term deliverables remains to be done. Established high level parameter list for Target Station.
TTAC-08-02 | Linda Coney | Observation: The target safety system is not clearly defined. Recommendation: A credible monitoring system has to be specified, capable to guarantee that the target is ready for beam. Early definition of this system is important for the design and control of the target instrumentation. | Complete | Process to derive the set of safety credited controls is in place and being worked and will be preseented at the TAC-9 meeting. Final definition of the safety credited controls is planned for ca. 2016. In general, Target MPS items will be identified in P&IDs that will be part of the Preliminary Design Review deliverables (ca. 2014).
TTAC-08-03 | Eric Pitcher | Prioritize the list of EDDs considering the budget constraints; identify what is mandatory or needed, and when. | Complete | EDD Plan developed and iterated several times to settle on a set of activities that address critical issues in a timely fashion (ESS-0006024). These actvities have been incorporated into the Target baseline.