## Slide 1
European Spallation Source
Technical Advisory Committee Meeting
April 2-3, 2014
Jim Yeck
CEO & Director General

## Slide 2: Outline
Progress and Milestones 2014
Licensing and Civil Construction
Technical Coordination and Risk Management
In-kind Goals
Status of Instrument Proposals
Initial Operations Phase

## Slide 3: 2013 progress
Key approvals by ESS Steering Committee (STC)
  Technical Design Report, Construction Cost, and Annual Operations Cost Target
ESS organization clarified for project delivery
Strengthened support for construction decisions by STC Members
  Cost Book, Call for Expressions of Interest, Partner Days, ILOs
  Maturing In-kind plans
Regular advisory committee meetings (AFC, IKRC, SAC, TAC, CFAC)
Completed the 1st Annual Project Review in November 2013
Focus shifted to project execution plans

## Slide 4: First 6 months of 2014
Letters of Intent or Agreements with Member countries
Demonstrate accelerator and target station technology readiness for the civil construction start – ensure key interfaces resolved
Increase engagement of the scientific user community and continue selection of instruments for engineering development - develop in-kind model
Partner days to promote opportunities to participate in ESS construction
Selected conventional facilities partner company and started final design for the accelerator buildings in Feb 2014
Secure environmental permit for facility construction, funding plans, and establish Project Performance Measurement Baseline by May 2014
Start facility construction!

## Slide 5: ESS funding picture
Current members preparing their construction commitments
  Sweden, Denmark, and Norway (~50% total)
  France, Germany, and the United Kingdom (~30% total)
  Italy, Spain, Switzerland, Netherlands (~>15% total)
  Czech Republic, Hungary, Poland, Baltic countries (>5% total)
Discussions with countries that could join after construction start
  Belgium, Finland, , Israel, Portugal, Russia, Singapore…..?

## Slide 6: 2014 top level milestones
ID | Name | Proj | Planned | Forecast | Actual
G1500 | Start of Concept Design for instrument 1-3 | NSS | 7 Jan | 7 Jan | 7 Jan
G5220 | Start of Detail Design Accelerator Building | Convf | 7 Jan | 18 Feb | 
G5180 | Contract C101 Signed | Convf | 18 Feb | 18 Feb | 
 | First in-kind contracts presented to IKRC | Accsys | 7 Mar | 7 Mar | 
G8000 | Establish the ES&H Advisory Committee | Admin | 31 Mar | 31 Mar | 
G28900 | SSM Permit | Licens | 30 Apr | 31 July | 
G63640 | Moderator Concept Finalized | Target | 30 Apr | 30 Apr | 
G5040 | Environmental Court Verdict | Licens | 14 May | 30 May | 
G8010 | Annual Review update | Admin | 26 May | 26 May | 
G5060 | Ground Break | Convf | 2 Jun | 2 Jun | 
G1665 | Decision on 2013 Instrument proposals (instr. 4 plus ) | NSS | 1 Oct* | 1 Oct | 
G36450 | Lattice database version 2 available | ICS | 30 Jun | 30 Jun | 
G63720 | Preliminary design review of beam extraction | Target & NSS | 10 Jul | 10 Jul | 
G36460 | ICS Hardware Platform freeze | ICS | 30 Sep | 30 Sep | 
G36470 | Audit on MPS technical design specification finished | ICS | 1 Oct | 28 Nov | 
G31210 | Cryogenic transfer line ordered | Accsys | 8 Oct | 8 Oct | 
G31250 | Spoke Cavity Prototype available For Uppsala test stand | Accsys | 3 Nov | 3 Nov | 
G148900 | Start construction of Tunnel G01 | Convf | 18 Nov | 18 Nov | 
G1460 | Define and implement the In-kind collaboration model for the construction of the neutron instruments | NSS | 19 Dec | 19 Dec | 
*) The decision on 2013 instrument proposals will be taken at the September STC meeting

## Slide 7: Review Charge
 A Performance Measurement Baseline (PMB) is an integrated work plan made up of a sequence of activities which cover the complete scope, cost and schedule of a project. Once the PMB established and approved, the PMB can be used to evaluate actual cost and schedule performance to determine whether the project is meeting its planned scope, cost and schedule objectives.

## Slide 8: Review Charge
11. Will ESS be ready to establish the project performance baseline∗ in early 2014 and start conventional construction in mid-2014?
Yes, if environmental permits and regulatory licence are available, the possible interfaces with the various systems is mastered and the mitigation of possible late changes is taken into account in the CF contract.
In addition, CF funding and overall 85% of commitments to the project secured.
1
2
3
4
5
6
7

## Slide 9: Licensing – on track!
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
2014
Reviews and reports
SSM Opinion to Court
Assessment
Environmental Court
Main Hearing April 25th
Court ruling and permit
Ground break June 2nd
Radiation Safety Authority (SSM)
Public announcement: Info from ESS complete for construction permit
Issue of permit to construct
Start of concrete works
EU Notification, Euratom art 37
~6 month process
Opinion needed before permit for test ops
Swedish Environmental Court required EU Opinion before main hearing. ESS, with support of SSM and EU, appealed as EU Opinion is an operations requirement. Resolved in ESS favor.

## Slide 10: Conventional facilities contract
The Collaboration contract and Option 1, Special conditions for Phase 1, signed on February 18 with Skanska
Skanska provides project management staff to assist ESS in planning the start of civil construction
Initial contract commitment is 10-15 people for 6-9 months
Joint development of detailed facility designs, target cost including detailed estimate and schedule, procurement plan for sub contractors, and performance plan for phase 2
Critical path activity
Civil construction schedule needs push the project decision-making process

## Slide 11: Critical Path
Accelerator Buildings
Ground break
First installations on-site (ACCSYS)
First Beam on Target (570 MeV)
Machine installed
for 2.0 GeV
Licencing
Licensing
ConvF
AccSys
Last of Instr Const
Instr HO to Op
NSS
Spoke & Medium Beta CM
(Prod&Inst&Comm)
High Beta CM
(Prod&Inst&Comm)
Instrument Construction

## Slide 12: ESS organization

## Slide 14: Technical coordination role
The primary responsibility for technical coordination and management resides with the new Technical Director (currently the Machine Director)
  Technical interface management and integration at the directorate level
Deputy Technical Director is in place now
  Configuration Management and Configuration Control Board
  Engineering processes including systems engineering, design processes, design reviews
  Technical documentation and design tools

## Slide 15: Enhanced flux neutron moderators
New moderator concept
  Mechanism understood
  Works for all neutron sources, including reactors
Harmonization with instrument suite
  Complex optimization is in progress for the potential instrument suite and sample sizes
  Collaboration within ESS (Instruments and Target) and with the Instrument Consortia from our partners
Timeline and milestones
  Feb. 12: 1st moderator workshop, refine parameter space for further optimization
  March, second half: 2nd moderator workshop
  April 30: New moderator configuration to CCB

## Slide 16: Risk Management, progress so far
ESS has implemented risk management as one of the project management tools
It is a continuous process, integrated as a part of the daily work
  ESS projects are driving internal work on risk, with support from the risk manager
  ESS established routines for:
    Risk communication within, and in between the projects
    Maintaining and updating risk registers, containing all relevant information related to risks and risk treatments
    Risk workshops
    Handling risks on the most suitable levels
Risk is a standing item on:
  ESS Project Group (EPG) meetings weekly
  Project Reviews monthly
  ESS Management Team risk sessions quarterly

## Slide 17: Risk Management, plans ahead
The risk management software, Exonaut Risk, is currently being implemented, enabling:
    A more structured overview of risks and responses than with spread sheets
    Effective risk communication
    Planning and distributing responsibilities for risk treatments and visualization of risk exposure
  Implementation of Exonaut Risk will be completed Q1 2014 and a presentation of risk can be provided at the next STC meeting
Risk Management activities and plans ahead include:
  Focus on reducing risk exposure by implementing risk treatments
  Strategic work with risks, analysing content of the database, Nov review
  Establish risk KPI’s to produce trend data and refine feedback loops
  Cross-functional workshops for specific topics
  Quantification of risk

## Slide 18
ESS In-kind contributions potential
Target station
€ 154M
Accelerator
€ 510M
NSS/Instruments
€ 350M
In-kind
Cash
Total construction cost: € 1,84 billion
Potential In-kind identified is ~36%. Working to increase potential above 40%.

## Slide 19: Current status of instrument proposals - 1
Instrument Proposal (Submitting Institutions) | STAP Review
Powder Diffraction | 16-17/12/13
Powhow - bispectral powder diffractometer (JCNS) | Positive outlook
Heimdal - hybrid diffraction, SANS and imaging (U-Aarhus, U-Copenhagen, PSI, DTU) | Issues to address
Modi - monochromator-based general-purpose powder diffractometer (ESS) | Issues to address
Materials & Engineering Diffraction | 4/2/14
BEER - engineering diffractometer (HZG, NPI-Rez, TU-Clausthal) | Positive outlook
Indirect-Geometry Spectroscopy | 18-19/12/13
Camea - crystal-analyser spectrometer (EPFL, U-Copenhagen, DTU, PSI) | Positive outlook

## Slide 20: Current status of instrument proposals - 2
Instrument Proposal (Submitting Institutions) | STAP Review Status
Direct-Geometry Spectroscopy | 4-6/12/13
C-Spec - cold chopper spectrometer (TUM, LLB) | Issues to address
Vor - wide bandwidth chopper spectrometer (ESS) | Issues to address
T-Rex - bispectral chopper spectrometer (JCNS) | Positive outlook
Tempus Fugit - time-focusing crystal-monochromator spectrometer (Perugia, Marche, Messina, Roma Tre) | Significant issues to address
Spin Echo Spectroscopy | 9/12/13
ESSens - high resolution neutron spin echo (JCNS) | Positive outlook
SAC Meeting to Discuss Proposals planned for 21-23rd May

## Slide 21: Preparing the construction project
Deliver on the Technical Design Report performance and Steering Committee commitments
  5 MW accelerator capability
  Construction cost of 1,843 B€
  Operations cost target of 140 M€
  22 “public” instruments
Start w/ unconstrained resources (technically limited schedule) and develop credible project execution plans 
Comprehensive review of project baseline and execution plans 
Secure funding and resources and align schedules with the available resources ☐

## Slide 22: Transition from construction into steady-state operations
Basic Principles
Three phases to the ESS project: construction, initial operations and ramp-up, and steady-state operations
Construction Phase complete in 2025 (13 year construction phase)
Initial Operations and Ramp-up Phase begins in 2019 with production of 1st neutrons and ends in 2025 when Construction Phase complete
Spallation source facilities construction and commissioning complete in 2022
  Neutron Scattering Systems construction complete in 2025
Steady-State Operations Phase (2026 – )
  Routine facility operations includes construction and commissioning of the final 22 public instruments

## Slide 23: Commissioning and initial operations
Initial User Ops
Criteria for start of Initial Operations: Deliver a measurable number of moderated neutrons to an instrument.
TDR Performance Goals Strategy
Initially keep radioactivity and doses low to allow hands on maintenance.
Ramp up power quickly to find limitations and increase reliability before user operations start.

## Slide 24: Instrument investments
ESS will deliver 22 “public” instruments
  Substantial funds planned as part of the construction commitment (350 Meuro investment in Neutron Scattering Systems)
  Provision for additional instrument investment as part of operations until 22 instruments installed and commissioned
Instrument fabrication, installation, and hot commissioning schedule constrained by technical feasibility and resources
Initial limited instrument suite available for fully open user program by 2023, and significant number of instruments by start of steady-state ops in 2026

## Slide 25: Initial operations and ramp-up phase and commitment to 22 instruments
1st Neutrons
2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Start of User Program
Construction Budget
STC Decision on
Instruments
3
12
16
17
22
Expected Instruments in hot commissioning
3
6
9
12
15
18
Plans for
Instruments 17 to 22
Engineering Design
Construction of instrument 17 to 22
Initial Operations and Ramp-up
Steady-Sate Budget
20
22
Expected Instruments in user programme
6
9
12
16
20
22
Start of Instrument Construction
Decision Outlook and Scenario for Construction of 22 Instruments

## Slide 26: ESS is ready for construction commitment
STC committed to share in support of ESS project phases: construction, initial operations and ramp-up, and steady state operations
STC commitment to start construction anticipated at the next meeting (6-7 May in Oslo).
  Each member’s share of total construction investment defined in Letter of Intent
  Developing comprehensive cash flow assessment and financing plans