## Slide 1
Target Update
John Haines
Head of Target Division
www.europeanspallationsource.se
April 2, 2014

## Slide 2: Outline
Progress on staffing
In-Kind goals
Highlights and plans for each system
Key technical issues, risks, and EDD Plans

## Slide 3: Target Division Org Chart
TARGET DIVISION
John Haines
Head of Division
Eric Pitcher
Deputy Head of Division
François Plewinski
System Engineer
Carina Blixt
Team Assistant
Target Controls Group Linda Coney (GL) Atefeh Adeghzadeh
Monolith & Handling Group Rikard Linander (GL) Magnus Göhran Daniel Lyngh Ulf Odén
Pascal Sabbagh Cyril Kharoua (C) Naja de la Cour (C) Anders Olsson (C) Björn Persson (C) Mikael Möller (C) Reinhard Blum (C) Markus Andersson (C) Paul Erterius (C) Bengt Jönsson (C) Jens Harborn (C) Lennart Åström (C)
Materials Group Yongjoong Lee (GL) Jemilia Habainy
Sofie Borre (S)
Johan Wendel (S)
Neutronics Group Luca Zanini (GL) Konstantin Batkov Alan Takibayev
Zsofia Kokai Esben Klinkby
Troels Schoenfeldt
Fluid Systems Group Håkan Carlsson (GL) Per Nilsson Allan Lundgren (C)
Ingvar Olsson (C)
Mateusz Pucilowski (S)
Paal Inge Smeby (S)
Target Physics Group Gunter Mührer (GL) Riccardo Bevilacqua
Daniela Ene

## Slide 4: Personnel actions since TAC8
Monolith and Handling Group
  Daniel Lyngh – Moderator and Reflector Systems Work Package Manager
  Ulf Odén – Target Systems Work Package Manager (May)
Fluid Systems Group
  Håkan Carlsson – Group Leader and Work Package Manager (August)
Controls Group
  Atefeh Sadeghzadeh – Controls engineer
Physics Group
  Günter Muhrer – Group Leader and Work Package Manager
  Riccardo Bevilacqua – Shielding analyst
Materials Group
  Yongjoong Lee – Group Leader
10 contract engineers brought in to support work packages
  CAD engineers
  Work Unit Leaders
  Analysts
  Support engineers

## Slide 5: Staffing Required for On-Time Execution of Target Station
Chart: FTE
| 2014.0 | 2015.0 | 2016.0 | 2017.0 | 2018.0 | 2019.0
Target | 57.206 | 90.9464 | 49.47 | 39.8534 | 57.9509 | 24.2636
Some of these positions will be covered by in-kind agreements, but
  Which ones?
  How many?
  When?
Head count now = 39
Starting from head count of 27
at end of 2013

## Slide 6: Substantial In-Kind Partnerships Required for Project Success
  Note: The only efforts that will be predominantly performed by the ESS AB team are:
  Management and integration (12.1, management of Work Packages, and neutronics analysis)
  Safety related work – Safety credited controls, shielding analysis, and interaction with ESS safety and waste management organization
Goal is 65% In-Kind for Target

## Slide 7: WP2 Target Systems – Status and Plans
PDRs:
Target Primary Cooling System - Jul 2014
Target Wheel - Sep 2014
Target Shaft and Drive – April 2015
On-going and planned optimization studies:
He pressure, flow rate, and flow passage configuration
He seals
Finalize water-cooled backup work by determining power limit based on need for emergency cooling
Tungsten slabs in 33 sectors of target wheel
Helium coolant
  Mass flow 3 kg/s
  Pressure 0.3 Mpa
Rotational speed 25.5 rpm
Wheel diameter 2.5 m
Lifetime ~ 5 years (@ 5 MW)

## Slide 8: WP2 - Progress on water-cooled backup closeout study
Efforts have focused on addressing the uncertainty related to keeping the tungsten below the 700°C oxidation temperature during a loss-of-coolant accident (LOCA)
ESS-Bilbao calculated decay heat data for a cannelloni geometry (tungsten clad by zircaloy)
Two decay heat removal analyses performed
  ESS-Bilbao: tungsten peak temp = 400°C
  McManamy Consulting, Inc.: tungsten peak temp = 520°C
Conclusion: water-cooled backup is viable at 5 MW beam power
Next step: produce final report of the Water Task Force

## Slide 9: WP3 Moderator and Reflector Systems
Cold moderators
  Super-critical H2 at 20 K and 1.5 MPa
  Aluminium alloy vessel
  Expected lifetime ~ 1 year @ 5 MW
Water moderator assemblies
Light water-cooled Be reflector
“Flat” moderator concept proposed last summer as an idea that could significantly increase neutron brightness
TDR Moderator Concept

## Slide 10: Optimization studies identified a potential opportunity for significant increase in neutron brightness
a
K. Batkov, et al., NIM A 729 (2013) 500.
TDR (baseline) design

## Slide 11: Working Closely with the Science Directorate on Moderator Concept Selection
Neutron brightness, instrument performance, and engineering attributes are being evaluated to determine the optimal solution for moderator size, shape, and number
  The primary optimization parameter is instrument performance, but ease of remote handling and cost and schedule impacts are also being considered

## Slide 12: Status of Moderator Selection Process
Extensive efforts within the Target Division and Science Directorate have been dedicated to the moderator optimization efforts and this subject is the main focus of the tTAC Breakout Session
  Neutronics (See Luca Zanini presentation)
  Instrument performance (See Ken Andersen presentation)
  Engineering evaluations (See Rikard Linander presentation)
The initial promise of the “flat” moderator concept appears to be holding up after further evaluation – perhaps even strengthened by background reduction arguments
We are on track to make a decision on the moderator concept by April 30
We welcome advice on this matter from tTAC
  An ad hoc advisory committee consisting of a few members of the tTAC and SAC will be convened in late May to review our decision and advise us on our path forward

## Slide 13: WP4 Monolith Systems - Status and Plans
PDRs:
Neutron Beam Extraction System - Jul 2014
Monolith shielding - Oct 2014
Proton Beam Instrumentation - Oct 2014
Monolith vessel - Dec 2014
Seismic response of monolith shielding
20 mm monolith vessel thickness,
analysis of internal vacuum load
Proton beam window
Moderator and reflector plug
Target wheel
Neutron beam extraction
Neutron beam window
Steel
shielding
Monolith
liner
On-going and planned optimization studies:
Beam extraction configuration – number of beamlines/spacing, beam guide inserts, shutter configuration
Remote handling concepts for proton beam window, instrumentation plugs, and beam extraction
Containment of He environment/allowable leak rate
Details of interface with CF and Instruments

## Slide 14: WP5 - Fluid Systems Status
Key issues for optimization studies:
Optimizing cooling system requirements, e.g. temperature ranges to improve energy recovery
He environment control – reducing throughput requirements
PDR for He purification and ventilation & confinement planned for Dec 2014
Primary Water Cooling:
Water Moderators 50 kW
Reflectors 300 kW
Shielding and Plugs 1.6 MW
Intermediate Water Cooling:
Target System 3.8 MW
Gas Systems 90 kW
Water Systems 2.2 MW
Rad. Gas Effluent & Confinement (RGEC):
Target Station Ventilation 110 000 m3/h
Separation Gas for Primary Water
Radioactivity Monitoring
Active storage
Water and helium storage
Auxiliary Helium Systems
PBW Cooling 5 kW, 200 g/s
Target Helium Purification 3 g/s
Monolith Helium Purification 7 g/s

## Slide 15: WP6 Remote Handling Systems – Status and Plans
25th April; “Internal review” – Concept evaluation
First PDR “Active Cells Confinement” in November
Active Cell optimization:
Confinement systems
  Floor valves
  Intra bay shielded door
  Storage pit lids
  Transfer hatch
Dynamic barrier
Modes of operation
Functional breakdown and system definitions
Interfaces; internal and external

## Slide 16: WP7 – Target Controls Status
Target Safety System
  Process underway to determine safety credited controls required to protect public and workers from target hazard
Coordination with ICS
  Defining requirements for ICS software, PSS in Target, non-TSS (MPS) controls interfaces
Target systems
Monolith systems
Fluid systems
Active Cells
Control box
EPICS
Diagnostic UI
Central service (cool & vac)
PSS Local
Timing system
PSS global
Data Collection
Control logic
Instrumentation:
Beam & Target
MPS Local
MPS global
Beam Dump
?
PRELIMINARY
Hazards screening to identify items needing quantitative analysis (2014)
Simplified analyses to determine limiting cases and identify potential mitigation measures (2014-15)
  Design basis accident analyses to define safety credited controls including redundancy and diversity (2016)

## Slide 17: WP8 Physics – Status and Plans
120 min in Helium + Argon + H2O (0.7 %)
  Tungsten oxidation
400°C
600°C
500°C
750°C
800°C
900°C
700°C
Main neutronics effort is dedicated to moderator optimization
  Also supporting assessments of other science applications, e.g. Chip Ir, fundamental physics, …
Shielding calculations
  ESS Shielding Coordinator role
Radionuclide inventory estimates for waste storage and handling
Materials
  Tungsten oxidation and fatigue
  Materials property database to support design and analysis efforts

## Slide 18: Engineering Development and Demonstration (EDD) Activities Focus on Key Technical Issues and Risks
The answers to a series of critical questions were used as the basis for selecting EDDs. Questions included:
  What issue is addressed by the proposed EDD activity?
  What effort (e.g., experiment, fabrication prototyping, computer simulation) is proposed to address this issue?
  When are results needed?
  What is the consequence of a delay in obtaining the results?
  What is the consequence of not conducting this activity?

## Slide 19: Key Technical Issues and Planned EDDs
Target He cooling flow system uncertainties and integrity of tungsten plates
  Target rotary seal prototyping and testing
  Helium purification
  Target system gas flow erosion
  Tungsten fatigue studies
Moderator performance uncertainties
  Moderator neutronics benchmark (assumes flat moderator selected)
  Ortho hydrogen fraction in moderator
Compatibility of equipment with remote handling, tool and procedure development, and training
  Mockup activities to develop and test remote handling procedures

## Slide 20: Closing Remarks: Major Activities and Goals for 2014
Hiring, hiring, hiring
Working with Science Directorate to select moderator configuration
Finalizing detailed requirements and key design features (He pressure in target loop, MR plug extraction scheme, monolith diameter, neutron beam extraction, …)
Conduct Preliminary Design Reviews for critical components and subsystems
  Target wheel and drive systems
  Target helium cooling system
  Moderator and Reflector plug
  Neutron beam extraction system
  Target monolith shielding
Establish agreements with in-kind partners