## Slide 1: Status Report ACCSYS
Mats Lindroos
Head of Accelerator
www.europeanspallationsource.se
April, 2014

## Slide 2: Overview
Good progress in all WPs !
Creation of an integration group lead by the Chief engineer consisting of lead engineers, ACCSYS system engineers, installation WP leader and associated staff. Close links to beam physics WP.
Review of CF preliminary design for ACCSYS tunnel buildings (solutions proposed for FE and Dog-leg regions and all approved in February CCB)
Review of CF preliminary design for ACCSYS RF gallery. Approved and in detailed design from March CCB
Review of level 3 requirements and close to completion of level 4 requirements. Technical specifications in progress (level 5). Implementation of DOORS repository started.
Risk register transferred to Exonaut and risks assigned to ACCSYS staff with treatments in progress
Good progress with In-kind discussions with several partners (e.g. Fr, Po, Es, It), planning of in-kind and drafts for technical appendices.
Audit of electrical and cooling support WP, HEBT WP and Vacuum WP

## Slide 3: Organization and Work package leaders
Division and project aligned at high level
  “WP as a group” would make for too big fragmentation
  Four WPs have external leaders
Weekly or bi-weekly meetings at ESS Accelerator Division
  Management board of project and division
  WP leaders
  Lead engineers
  Safety
Regular meetings for ACCSYS project
  Technical board (all WP leaders and reps of labs/uni. with contract) as governance and CCB on project level (6 meetings per year)
  Collaboration board with reps of director of of labs/uni. with contracts as oversight committee
  Audits yearly of every WP
  Reviews (Conceptual, design, ready to build) as required mostly co-organized with audits

## Slide 4
M Lindroos
Head of Division
H Danared – Deputy Head of Division
J Weisend II – Deputy Head of Acc Projects
D McGinnis – Chief Engineer
S Peggs (C)
A Jansson – Safety & Reliability Manager
BEAM PHYSICS
H Danared – GL
R de Prisco
M Eshraqi
R Miyamoto
M Munoz
E Sargsyan
C Darve
SPECIALIZED TECHNICAL SERVICES
J Weisend II – GL
P Arnold
J Fydrych
W Hees
G Hulla
F Jensen
J Jurns
P Ladd
H Spoelstra
X Wang
M Ferreira
RF
A Sunesson – GL
C de Almeida Martins
M Jensen
R Yogi
R Zeng
R Montano
C Prabert - Personal Assistant
G Jacobsson - Team Assistant
Solveig Aas– Team Assistant
BEAM INSTRUMENTATION
A Jansson – GL
C Böhme
B Cheymol
I Dolenc Kittelmann
H Hassanzadegan
M Jarosz
E Lundh
C Roose
T Shea
L Tchelidze
C Thomas
E Bargallo
H Kocevar
INTEGRATION
D McGinnis - GL (I)
A Ponton – Lead Eng
S Molloy – Lead Eng
G Lanfranco
E Tanke
N Gazis
M Conlon (C)
C Prabert, 2014-02-19
50 people including 1 not started yet

## Slide 5: THE ESS LINAC
M. Eshraqi
April 2-3
Spokes
Medium β
High β
DTL
MEBT
RFQ
LEBT
Source
HEBT & Contingency
Target
2.4 m
4.6 m
3.8 m
39 m
56 m
77 m
179 m
75 keV
3.6 MeV
90 MeV
216 MeV
571 MeV
2000 MeV
352.21 MHz
704.42 MHz
 | Length (m) | W_in (MeV) | F (MHz) | β Geometric | No. Sections | T (K)
LEBT | 2.38 | 0.075 | -- | -- | 1 | ~300
RFQ | 4.6 | 0.075 | 352.21 | -- | 1 | ~300
MEBT | 3.81 | 3.62 | 352.21 | -- | 1 | ~300
DTL | 38.9 | 3.62 | 352.21 | -- | 5 | ~300
LEDP + Spoke | 55.9 | 89.8 | 352.21 | 0.50 (Optimum) | 13 | ~2
Medium Beta | 76.7 | 216.3 | 704.42 | 0.67 | 9 | ~2
High Beta | 178.9 | 571.5 | 704.42 | 0.86 | 21 | ~2
Contingency | 119.3 | 2000 | 704.42 | (0.86) | 14 | ~300 / ~2
Upgrade | 59.6 | 2000 | 704.42 | (0.86) | 7 | ~300 / ~2

## Slide 6
Sebastien Bousson
Pierre Bosland
Santo Gammino
Søren Pape Møller
Roger Ruber
Ibon Bustinduy
CERN
The National Center for Nuclear Research, Swierk
Anders J Johansson
Prototyping the ESS accelerator
Roger Barlow

## Slide 7: The Cavity Cryomodule Technology Demonstrators
Power coupler
Cold tuning System
Helium tank
5-cell elliptical cavity
 Cavities Cryomodule Technology Demonstrator results by 2016
Space frame
Notes: Accelerateur principe avec proton
Technologie de pointe supraconductice
Spoke – insatalle

## Slide 8: (Some of the) Achievements past month
RF (WP8): Decision on a vendor for the modulator prototype
RF (WP8): Received offers for prototype IOTs
Cryogenics (WP11): Arrival of final industry study reports for the Accelerator Cryoplant and specification of accelerator cyoplant finished
NC front-end (WP3): Start of production of DTL prototype components at INFN Turin
SCRF (WP4 and 5): Continued work on SRF Cavity and coupler prototypes e.g. spoke cavity prototype elements fabricated and cavities to be delivered in July from both vendors
Beam diagnostics (WP7): Start of re-planning of the Beam diagnostics to respond to new accelerator design and desire for additional in kind contributions
Vacuum workshop held to agree on standards and hand book (WP12)
Safety&Reliability (WP13): Completion of Report on Accelerator Shielding design requirements
Infrastructure and Installation (WP99): Continued detailing of RF Cell layouts and cabling requirements. Requirements for CF.
Significant progress on cabling and rack requirements (WP14)

## Slide 9: Next month’s major activities
In-kind discussions with Spain, Poland, Italy, Denmark, Sweden, Germany, Switzerland, Norway and France to prepare in-kind contracts and HOAs
Tracking of actions on annual review recommendations, 6 of 8 to be completed for end of May (talk by J. Weisend for TAC)
Completion of review of requirements at level 3 and completion of level 4 requirements and migration to DOORS
Continue commissioning and operation planning
Decision on IOT prototype contract
Continued WP activities according to plan

## Slide 10: Project wide issues and other higher project level issues
Delays will be incurred if in-kind contracts aren't agreed or intermediate solution for in-kind crediting found, e.g. LEBT diagnostics, RFQ, MEBT and Raster scanning prototypes.
Need to find workable solution for earned value reporting for (in-kind) contracted activities
Need of a real-time integration of CF and ACCSYS configuration data and decision on E-CAD software for ESS
Delay in cavity prototype manufacturing for 2(3) spoke cavities and 1(2) elliptical cavity
Need to discuss accelerator MPS design philosophy at ESS level, possibly hold an independent review
Preparation of technical appendices for all in-kind contracts

## Slide 11: Very high level Schedule

## Slide 12: Risk and treatment status
Top 5 risk Cost:
political and financial considerations overrule technical considerations for IKC assigments
In-kind contributors do not meet scope and schedule requirements
Both funding and costing have uncertainties. The uncertainties are still present very late in the process. Changes will impact scope and schedule but these are fixed! E.g. the cost uncertainty is +30% - 0%, our contingency is apporx 15%, i.e. not aligned.
Unidentified design faults are not prototyped and fail in production
Suppliers do not deliver on time with right quality/quantity, e.g. klystrons, modulators, CMs, cavities
Top 5 risk Schedule:
Integration failure and/or interfaces don't match.
Suppliers do not deliver on time with right quality/quantity, e.g. klystrons, modulators, CMs, cavities
Cryomodule production is late
In-kind contributors do not meet scope and schedule requirements
Delay in issuing major contracts, both in-kind and others.

## Slide 13
Planned In-Kind from Primavera
Summary of activities (work packages or work units) where at least one specific partner has been identified and discussions with this partner has started
Håkan Danared, IK manager ACCSYS

## Slide 14
Potential In-Kind from Primavera
Summary of activities where no specific partner has been identified or, in the case of beam instrumentation, where the WP is being re-organized such that start dates and values cannot be assigned at the moment
Håkan Danared, IK manager ACCSYS

## Slide 15
Number of Contracts per Quarter
Many activities start Q1 2014, reflecting the importance of reaching agreements soon

## Slide 16
In-Kind Proportions
Potential partners identified for 60% of the total planned/potential in-kind value Planned/potential in-kind is 78% of accelerator budget
Håkan Danared, IK manager ACCSYS

## Slide 17
Final Remark on In-Kind
Planned in-kind contributions cover 48% of accelerator budget.
Many items still open.
Design phase is largely over – now hardware contributions are needed.
To reach >50% in-kind to accelerator, substantial commercial items must be obtained as in-kind.
Nevertheless, in-kind to construction is far from ”only procurement”.
In-kind is also an opportunity to local industry (study showed 80% of procurement budget spent within 100 km of large research facilities).
Håkan Danared, IK manager ACCSYS

## Slide 18: Conclusions
Discussion with in-kind partners on contracts for more than 48% of ACCSYS project budget
ACCSYS buildings in detailed design
ACCSYS is contributing to the implementation of, and use of ESS standard tools for product life time management, document management, work flows, requirements and interface descriptions
The AD organization is being further aligned with the project with a focus on the challenges ahead of technical coordination and integration
It is possible to deliver on time and budget…
  …thanks to a lot of work of a wonderful team which still need to become bigger and most continue to attract both experts and skilled beginners.