## Slide 1: Actions in ICS in response to Annual review recommendations
Miha Reščič
Deputy Project Manager, ICS
www.europeanspallationsource.se
April 3, 2014

## Slide 2: Overview
WBS
Staffing
Standards
IKC
Interfaces

## Slide 3: WBS
Observation / Recommendation
  The WBS should be scrubbed and reviewed by the project prior to base lining the budget. This could be done in very short order by clearly identifying the staff roles from the bottom up. Some areas appear to be too high and some too low.

## Slide 4: WBS activities
Activity
  Establish a new independent Work Package containing all the Equipment cost for Construction
    Status: Done*
  Revisit WP2 structure, split WP into Applications and Physics
    Status: Done*
  Revisit WP6 Integration Support structure and split Work Units into WPs
    Status: Done*
In addition, to establish baseline
  Bottom-up costing exercise, due April
  Cost & Schedule review, due May

## Slide 5: Staffing
Observation / Recommendation
  Reconsider the large outsourcing and convert contractors/managers to engineers .
Activity
  Revisit staffing competencies and estimates in Primavera
    Status: Ongoing
  Establish clear competencies terms (e.g. scientist, engineer) and standardize in staffing plans
    Status: Ongoing
  Establish a final external/internal ratio for Construction phase
    Status: Ongoing
  Plan the number of external staff onsite(for 2014)
    Status: Ongoing

## Slide 6: Standards
Observation / Recommendation
  Be more proactive and assertive in setting standards (e.g., low energy beam transport) .
Activity
  Make a list of standards and systems ICS has authority to standardize ICS
    Status: Ongoing
  Prepare a plan and milestones when and by who the decisions should be formally approved, for ICS and ESS standards that affect ICS
    Status: Ongoing
In addition
  Proposal for ESS Electronic hardware harmonization committee

## Slide 7: IKC
Observation / Recommendation
  ICS should identify resource to work with other technical groups in defining IKCs with control thereby assessing if it would be advantageous from an ESS project point of view to incorporate IKCs into ICS.
Activity
  Hire the dHoD to help HoD with IKC management
    Status: Ongoing
  Revisit the possible IKCs for ICS
    Status: Ongoing
In addition
  ICS IKC Strategy proposal

## Slide 8: Interfaces
Observation / Recommendation
  Be more proactive in defining interfaces and in communication with other systems. Pursue production of ICD’s with highest priority to clarify scope and interfaces with external systems

## Slide 9: Interfaces activities
Activity
  Define a list of 'other' systems
    Status: Ongoing
  Appoint lead integrators to systems
    Status: Ongoing
  Establish internal ICS architecture
    Status: Ongoing
  Setup regular correspondence with the systems with commitment from everybody involved
    Status: Ongoing
In addition, to establish baseline
  Integration sessions with CF
  Interface Description Documents with Target, NSS