## Slide 1
WP Status & General Issues
J. G. Weisend II
Deputy Head of Accelerator Projects
February 25, 2013

## Slide 2: Outline
Status of Work Packages
Work Package Audits & Design Review Process
General Comments and Issues
  Risk
  Issues
  Comments and Next Steps

## Slide 3: Introductory Comments
January 2014 reorganization:
  Moved coordination of WP99, WP15, WP2, and WP14 under Chief Engineer as part of the Accelerator Integration Effort – the activities of these work packages will be covered in Dave’s talk
  Ensured that liaisons (now Deputy WP Leaders) for the External WPs are separate from Lead Engineers
    C. Darve now Deputy for both WP4 and WP5
    A. Ponton is the temporary deputy for WP3 and search is underway for a permanent replacement

## Slide 4
Work Packages & Leaders
WP# | WP TITLE | WP LEADER | EXTERNAL WP? | DEPUTY WP LEADER FOR EXTERNAL WP
1 | MANAGEMENT | J.G. WEISEND II | NO | 
2 | ACCELERATOR PHYSICS | M. ESHRAQI | NO | 
3 | NORMAL CONDUCTING FRONT END | S. GAMMINO | YES | A. PONTON ( TEMP)
4 | SPOKE CRYOMODULES | S. BOUSSON | YES | C. DARVE
5 | ELLIPTICAL CRYOMODULES | P. BOSLAND | YES | C. DARVE
6 | HEBT & MAGNETS | S. MØLLER | YES | P. LADD
7 | BEAM DIAGNOSTICS | A. JANSSON | NO | 
8 | RF SYSTEMS | A. SUNESSON | NO | 
99 | ACCEL INFRASTRUCTURE & INSTALLATION | G. LANFRANCO | NO | 
10 | TEST STANDS | W. HEES | MIXED | W. HEES
11 | CRYOGENICS | P. ARNOLD | NO | 
12 | VACUUM | P. LADD | NO | 
13 | SAFETY & RELIABILITY | A. JANSSON | NO | 
14 | ACCELERATOR INTEGRATION | D. McGINNIS | NO | 
15 | COOLING & ELECTRICAL SUPPORT | F. JENSEN | NO | 

## Slide 5
WP1: Management
Achievements
Revised ACCSYS organization to create a Accelerator Integration Group consisting of Lead engineers and installation/integration staff. This new structure (whose work will be captured in WP 14, WP99 and part of WP15) will tie together engineering requirements more tightly with integration and installation. The reorganization also ensures that separate staff perform lead engineer and external work package liaison functions.
Conducted annual audits of WP15 and WP6
Updated risk registry and completely transitioned to web based Exonaut program.
Developed proposal for ACCSYS Design Reviews

## Slide 6
WP3: NORMAL CONDUCTING
FRONT END
First response to Annual Audit ( December) findings is complete and recommendations are being acted upon as appropriate
Ion source and LEBT
  Achievements
    Site layout and radioprotection issues fixed. Call for tender for the infrastructure realization in progress.
    Ion source mechanical design completed, validation in progress (COMSOL thermo-mechanical and electrostatic simulations in progress)
    IRIS design completed, validation in progress (thermo-mechanical, control electronics)

## Slide 7
WP3: NORMAL CONDUCTING
FRONT END
RFQ
Achievements
  RF design checked and is OK
  Thermo mechanical calculations in progress
  Preparation of the detailed and revised program and budget for the RFQ prototyping phase
  Preparation of the detailed and revised program and budget for the copper procurement and treatment
  Preparation of the detailed and revised program and budget for the RFQ construction

## Slide 8
WP3: NORMAL CONDUCTING
FRONT END
MEBT
Achievements
  In-depth buncher Metrology: Body and Cover.
  Refinement of buncher coupled (RF+Fluid+Thermomechanical) model in COMSOL
  Quadrupole: First magnetic models based on last requirements.
  Bead pull test of the buncher cavity on progress
  Beam Physics:
    Error Study performed on the 2014.v0 layout
    Systematic study of the required RFQ output beam parameters

## Slide 9
WP3: NORMAL CONDUCTING
FRONT END
DTL
Achievements
  Beam Physics:
    Study performed with PMQ errors independently studied, 50000 particle, input beam from MEBT
  RF
    RF studies of power couplers (effect of different iris height and width)
  Prototyping
    BPM Test bench mechanical layout
    first study on PMQ assembly and tuning procedures
    definition of DTs assembly procedure for BPM and PMQ case (brazing based solution)
    production start at INFN Turin mech. workshop (BPM, PMQ steel body, Drift tube for BPM, Drift tube for PMQ)

## Slide 10
WP3: NORMAL CONDUCTING
FRONT END
ISSUES
Compliance with ESS schedule for RFQ depends on the early in-kind agreement
Beam Instrumentation Review (March 2014) will change parameters and requirements that will affect directly to MEBT
Search for New Deputy Work Package Manager is underway

## Slide 11
WP4: Spoke Cryomodules
Achievements
Prototype cavities:
Spoke cavities prototype fabrication at Zanon and SDMS is ongoing. On-site meeting with both companies occurred in January:
SDMS has achieved the fabrication of all cavity parts, and the result is very satisfactory (shape, thickness homogeneity,…). The remaining work is all the electron beam welding operations. SDMS is announcing a delivery in end July 2014 (a 3 months delay), which seems easily achievable.
The situation with ZANON has been clarified. Zanon has formed the majority of the cavity parts, except the end cup: they still try to form it in one single part, despite several failures on tries made with copper. They plan one more try and then take the backup solution (2 parts, and 1 EB welding). Zanon is now announcing a delivery in July as well.

## Slide 12
WP4: Spoke Cryomodules
Achievements
Power couplers:
Power coupler prototypes fabrication: The PMB company is progressing well with the fabrication of 2 units. The only problem so far is a copper layer RRR achieved on a sample a little bit below the specification. PMB is announcing a delivery in April. The SCT company which is producing 2 other units is late but the visit at their premises in January 14th helped to solve some issues and to perform the validation of their fabrication drawings. Copper coating RRR measurements on sample exhibits values within the specifications. Delivery is expected in May.
Design of the doorknob transition is completed. It has been adapted to the ½ height waveguide. Specifications are being written for a call for tender release for 4 prototypes in March.
Fabrication of the 4 Power coupler outer conductors (including the cooling channel) has started at Sominex. The fabrication of the coupling cavity that will be used for the coupler conditioning has been awarded to the Sominex company (best offer over 4 proposals).

## Slide 13
WP4: Spoke Cryomodules
Achievements
Cryomodule:
An important effort for calculating as precisely as possible the cryomodule heat load was conducted and a tech note was released at the end of January.
Study of the ‘pros’ and ‘cons’ of moving some valves and sub-cooled exchanger in the valve box. Feasibility studies of such a valve box. A technical note is under preparation for sending to cryo group in Lund for discussion and for a final decision.
Conceptual study of the cryomodule supporting frame
Assembly tooling design is progressing
We aim at a full completion of the cryomodule design in April.
On-going standardization of the Process and instrumentation for the Spokes and Elliptical cryomodules.

## Slide 14
WP4: Spoke Cryomodules
Achievements
Preparation for Series Production
Important work has started to produce a detailed PBS (7 levels) of the spoke cryomodule, its associated WBS, and the cryomodule fabrication lifecycle. One of the first outcome expected from this analysis is to list all procedures, control and test reports that will be required for the series production, and anticipate their achievement in the actual prototyping phase.

## Slide 15
WP4: Spoke Cryomodules
Issues
We know now the estimated fabrication delay of the 3 spoke prototypes: delivery expected in July 2014. Taking into account the time required for preparation and test in vertical cryostat, the availability of the first spoke cavity for delivery to Uppsala could not be before end October 2014. Roger Ruber has been informed. No important consequence on the overall spoke development plan is expected from this delay, but consequences for the Uppsala test plan has to be analyzed.
The back and forth between coaxial and waveguide RF distribution for the spoke RF lines, together with the delays on the spoke power coupler fabrication is putting the power couplers on the critical path of WP4. At the present stage, no impact on the completion time of the spoke cryomodule test at low power at IPNO is expected (still planned for July 2015) but there is no margin on the planning anymore. This task is now tracked very closely.

## Slide 16
WP5: Elliptical Cryomodules
Achievements
Completed the detailed report of elliptical cryomodule heat load calculations.
M-ECCTD design: completion of the redesign of the internal cryogenic pipes in order to decrease the maximum pressure in case of accident: the calculated maximum pressure can be maintained at a pressure lower than 1.2 bars. Meeting with authorized body the 18th of February (APAVE).
High-beta prototype cavity manufactured by ZANON:
  Field flatness tuning and measurements done (95%)
  Last components ordered to be soon delivered for the modification of the electropolishing into a chemical BCP treatment.
  Acid mixture for BCP treatment delivered.
High-beta prototype cavity manufactured by RI:
Final welds of the Nb cavity foreseen in the next weeks

## Slide 17
WP5: Elliptical Cryomodules
Achievements
M-ECCTD cavities:
  Fabrication of the niobium started at Tokyo Denkai
  Opening of the offer received scheduled the 11th of February.
  New RF design for HOM rejection completed, mechanical calculation finalized, final engineering study and drawings still to be done before the kick-off meeting foreseen by end of February.
M-ECCTD Ceramic windows of the 6 power couplers:
  The 2 candidates sent uncompleted files. Questions for complement information are being prepared and have been sent. Answers scheduled for the 14th of February.
Finalized design of the outer conductor, of the door-knob and of the coupling box of the power couplers.

## Slide 18
WP5: Elliptical Cryomodules
Achievements
Preparation of the shipment to Saclay of the cryogenic line for the ECCTD test stand.
Initiated the sequences of modes for the cryomodule operation. Identified interlock and process variables.

## Slide 19
WP5: Elliptical Cryomodules
Issues
Completion of the medium beta cavity drawings before kick-off meeting.
Delay on the production of the RI prototype high beta cavity cavity

## Slide 20
WP6: HEBT & Magnets
Achievements
A report on the 2013 HEBT beam optics has been prepared and submitted as an ESS Technical Note (ESS/AD/0053).
After its completion, new boundary conditions are emerging as a result of a cost optimization process focusing on the HEBT. Especially the achromat section is currently being revised aiming for a longer and less steep achromat line, which could lead to reduced costs, in particular for the building.
The possibility of using the DMSC cluster for future beam error studies has been investigated.
For the raster magnets the choice of cables is of great importance as a poor choice could severely reduce the performance of the dithering magnets. A restudy of the choice of cables has been initiated.

## Slide 21
WP6: HEBT & Magnets
Achievements
Meetings are on going to explore the in-kind potential for the HEBT beam line including magnets and power-supplies. Consistent with the recommendations of the Annual Review
Issues
Identification of in-kind partners to contribute to WP6

## Slide 22
WP7: Beam Diagnostics
Achievements
Held a full day BI retreat held on Feb 10. to review and re-plan the work package activities in light of new Accelerator design and desire for more IKC. The planning process expected to continue during Q1, and will take into account new BI requirements expected from commissioning working group in end March.
Planned follow up test of fluorescent screens in Stockholm
Applied (sucessfully) for beam time at COSY to test diagnostics
Visit to Trieste to discuss possible in-kind contributions
Visit to Legnaro to discuss status of DTL BPM work and discuss further possible in-kind contributions.
Detailed discussions with CERN on joint BLM procurement.
Continued contacts with DESY, GSI/FAIR.
Several team members attended USPAS & visited SNS & FRIB

## Slide 23
WP7: Beam Diagnostics
Issues
An agreement, either full formal IKC or an intermediate solution, that includes production of the LEBT prototype beam diagnostics at Saclay needs to be completed in March so that these prototype diagnostics are completed in time.

## Slide 24
WP8: RF Systems
Achievements
  A decision was reached on the modulator prototype tender
  Significant progress on layout of the RF system placement in the gallery was made
  PSI from Switzerland seem interested in discussing a Swiss in-kind contribution for Power Converters

## Slide 25
WP8: RF Systems
Issues:
  The recruitment problems impacts progress in the RF work package. Ranking of the candidates for the three positions that were re-advertised will start in February
  CERN modulator prototype from PPT delayed even more
  The 704 klystron procurement process kick-off is delayed

## Slide 26
WP10: Test Stands
Achievements
Phase I:
First draft of requirement specification for the electrical switchboard - preliminary design of water cooling system
Phase II:
Discussions with Polish in-kind contributors to XFEL cryomodule testing- new input on required staffing levels and testing logistics

## Slide 27
WP10: Test Stands
Issues
  Specification of transport of CMs from manufacturer is not clear, consequences can be increased workload for preparation of CMs before testing. Risks are lack of manpower and especially lack of work space to perform these modifications.
  Resources for testing of elliptical CMs may be too low. Risks are lack of manpower for execution of testing. An evaluation of the resource needs is ongoing.

## Slide 28
WP11: Cryogenics
Achievements & Activities
ESS received the draft final reports for the industry studies from both companies (Linde and ALAT). Comments and further questions have been made for the final version of the reports. Although there are still some open questions these final draft reports are sufficient to provide valuable input to the draft of the EACP (ESS accelerator cryoplant) specification.
A first draft of the EACP Technical Specifications has been written and is under review
A revised document for heat load requirements from WP4 has been checked and commented. The heat load for the power couplers was increased significantly while the load due to beam losses has been reduced. In a telephone conference the mutual approach of WP4 and WP5 was promoted in order to come to a final agreement on the heat loads.

## Slide 29
WP11: Cryogenics
Achievements & Activities
A telephone conference was held with the technical university of Wroclaw regarding a possible in-kind contribution for the CDS (cryogenic distribution system). A draft collaboration agreement has been sent to Wroclaw with the goal to start detail design work even when a final in-kind agreement is not yet in place.
Budget estimates from possible industrial suppliers of the CDS (Kriosystem in Poland and Cryoworld in Netherlands) have been received, encouragingly confirming ESS’ own estimates.
The 3d model of the prototype valve box, representing the finalized preliminary design, has been sent to France.
The P&I-D for the CDS has been updated.

## Slide 30
WP11: Cryogenics
Achievements & Activities
A list of requirements for WP11 towards CF was prepared, including revised electricity and cooling water requirements that could be based on the latest industry study results
A delegation of WP10, WP11 and ICS has visited DESY in order to meet the responsible people for cryo, testing and controls, gain valuable information and enforce the partnership of both laboratories
Issues
T&I Cryoplant and Target Cryoplant conceptual design was not further developed in January. There will potentially one month delay with no significant effect on the overall schedule.

## Slide 31
WP12: Vacuum
Achievements
The Vacuum Standardization Meeting was held February 19 – 20 in Lund.
Follow-up on orders placed for vacuum equipment for the chopper group.
Visit to CERN, January 16-17, to discuss the LHC vacuum insulation systems at LINAC 4 and RFQ vacuum instrumentation requirements.
Review of CERN reports and calculations applicable to ESS vacuum activities.
Estimate of the purge line diameter for the cryo distribution line.
Provided Inputs to the selection criteria for a suitable CAD system
Inputs for beam line element database to Cosylab
Provide inputs for the vacuum naming convention
Preliminary line sizing for the vacuum jacket of the hydrogen moderator completed.

## Slide 32
WP13: Safety & Reliability
Achievements
Finished detailed report on shielding work for Accelerator in 2013 (deliverable for annual review follow up). With Gunther Muerrer in TD for review.
Drafted report on hands on maintenance limits and beam loss limits for various accident scenarios.
Attended USPAS course and visited Fermilab (first week of Feb) to discuss shielding issues with N Mokhov

## Slide 33
Work Package Audits
Audits were held on the following WPs:
WP15 (Electrical & Cooling Support): January 31
WP6 (HEBT & Magnets): February 6
  External Chair: R. Ostojic (CERN)
WP99 Audit postponed due to high work load associated with review of CF Preliminary Design

## Slide 34
Work Package Audits
Both audits were the first for each work package, both are on schedule and no major technical problems were found
WP15 audit highlighted the need for additional definition of UPS / backup power and for clearer divisions of LCW, activated and standard water loops
WP6 audit showed that ACCSYS should finalize the division of labor between Aarhus University , ESS and other potential IKCs

## Slide 35
Work Package Audits in 2014
Work Package | Date
WP15 Electrical & Cooling | January 31
WP6 HEBT & Magnets | February 6
WP99 Integration & Installation | TBD ( March/April)
WP12 Vacuum | March
WP2 Beam Physics | April
WP10 Test Stands | May
WP7 Beam Instrumentation | June
WP8 RF | August
WP11 Cryogenics | Sept
WP4/5 Cavities & CMs | Oct
WP3 NCFE | Nov
WP13 Safety & Reliability | Dec

## Slide 36: Moving Forward – Audits and Design Reviews
Goals
Everything (systems and components) gets reviewed
Reviews must add value and not be redundant
The nature of a review will vary depending on the item being reviewed
  Reviews could involve presentations to a committee or independent reviews of a technical specification by a group of experts
  External experts could be invited as appropriate
Reviews should be documented and meet the intent of the ESS SE policy
Reviews should do double duty whenever possible (for example an audit and an FDR together

## Slide 37: Moving Forward – Audits and Design Reviews
Types of Reviews
WP Audits – yearly, involve both technical and project aspects
Fundamental Design Reviews (FDR)
Preliminary Design Reviews (PDR) – may be review of a technical specification
Critical Design Reviews (CDR) – only occur at a component level; may involve multiple reviews during the acquisition of the component
FDRs, PDRs and CDRs are driven by need not by the calendar
Nominally, a given system or component will only undergo 1 set of FDR, PDR and CDR during the project - though there may be exceptions to this
QA tests, FATs and SATs are in addition to the above and are the shared responsibility of the WPLs, LEs and Chief Engineer.

## Slide 38: Audits and Design Reviews – Where are we now?
0 = Doesn’t apply
X = Applies to Systems
XC = Applies to components

## Slide 39: Risk
ACCSYS has transitioned to the new Exonaut Risk Software
All risks have been reevaluated. 6 risks were moved to the ESS project level and one risk was retired
ACCSYS is currently tracking 45 risks
All risks have assigned owners and treatment plans. Most treatment plans have been started
Cost impacts are estimates only
Risks are reviewed monthly at the Project Support meeting and reported to ESS management

## Slide 40: Top 5 Perfomance Risks

## Slide 41: Top 5 Schedule Risks

## Slide 42
Issues
Need to finalize In Kind Contributions is an issue for a number of work packages. Significant progress has been made and a number of new potential IKC partners have been identified. Solution may involve collaboration agreements or similar arrangements that allow work to continue while final agreements are being put into place.
Assist ES&H Division in setting lab safety polices and requirements
Determine responsibilities for controls and transport associated with the cryomodules
Continue to more specifically define controls requirements and links to ICS

## Slide 43
Comments
Work Packages are out of “review mode” and stressing technical progress
  Prototype work in WP 3, 4 and 5
  Completion of EACP Technical Spec in WP11
  Procurement or near procurement of Modulator and IOT prototypes in WP8
  Re-planning exercise in WP7 (beam diagnostics)
This work is aided by the ongoing development of clear requirements via the Accelerator Integration Group
More technically detailed discussions with IKC are starting (Cryo Distribution Line, beam diagnostics, RF)
The new risk software works well and allows for easy tracking and updating of project risks. We will develop more detailed risks as the project progresses

## Slide 44
Comments
Change in project reporting should result in better information exchange between the projects and eliminate “dual system”
ESS CCB process is better defined and more efficient
Overall, ESS is looking like a more mature institution/project

## Slide 45: Next Steps (2014)
Complete response to review committee recommendations
Long lead procurements
  Place orders for initial IOT and modulator prototypes, cryogenic distribution system etc.
  Release Request for Proposals for the accelerator cryoplant
Finalize IKCs or equivalent to allow work to occur on schedule
Work to the existing plan (apply formal change control processes)
  Detailed design and specification
  Meet updated 2014 milestones
  Accurate EVMS and variance reporting

## Slide 46: Next Steps (2014)
Determine responsibility for cryomodule controls and transport
Develop detail on commissioning and operations plans and their impact on beam diagnostics
Further define interfaces with ICS, NSS and Target. Develop prototype controls as appropriate
Finish recruitment consistent with staff plan